STANDARD PROCUREMENT DOCUMENTS

****

Islamic Development Bank

June 2021

Standard Bidding Document - Information Systems Design, Supply and Installation

(One-Envelope Bidding Process) (With or Without Prequalification)

*This Standard Bidding Document was prepared by the Islamic Development Bank based on the Standard Procurement Document - Request for Bids Information Systems Design, Supply and Installation of the World Bank. IsDB thanks the World Bank for allowing the use and modification of the document for use in the IsDB operations.*

T*his document is subject to copyright. This document may be used and reproduced for non-commercial purposes only. Any commercial use, including without limitation reselling, charging to access, redistribute, or for derivative works such as unofficial translations based on these documents is not allowed*.

6/1/2021

**Preface**

This Standard Bidding Document (SBD) for Information Systems (IS) (Design, Supply and Installation) has been prepared for use in contracts financed by the Islamic Development Bank (IsDB). This SBD is aligned with the provisions of IsDB’s Guidelines for Procurement of Good, Works and related services under Projects Financed by IsDB, April 2019 (the “Guidelines”).

This SBD is to be used for the procurement of IS through international competitive bidding, with or without prequalification.

This SPD supports the procurement of IS (Design, Supply and Installation) of complex IS. In this context IS denotes an integrated whole that performs a business function (e.g., customs, tax, public finance, social insurance administration, etc.). An IS typically contains assemblies of information, communications and telecommunications (ICT) including system engineering and change management.

“Design, Supply and Installation” denotes the integrated set of activities by a Supplier (in concert with the Purchaser) to achieve functioning IS on a single-responsibility basis and such arrangements may include joint venture partnerships and subcontracting arrangements.

The single-stage IFB process is appropriate for IS procurements when the Purchaser has sufficient technical capacity to specify the detailed engineering design activities in the Technical Requirements. In contrast, the two-stage Bidding process or the Request for Proposals are appropriate when the Purchaser is more confident in concentrating on specifying its functional and system performance – and let Bidders offer engineering solutions to those requirements. In a single stage process, the Purchaser must be also confident that its documented requirements are so clear and unambiguous that Bidders will be able to prepare fully technical conformant Bids with only the help of pre-Bid meetings and written clarifications.

This SPD support the specification of recurring, operational inputs i.e., “Recurrent Cost Items” in addition to one-time investment inputs, (i.e., “Supply and Install Items”). Such Recurrent Cost Items typically arise in the Warranty Period. They may be incorporated in the main System Contract or may be subject of separate contracts. Recurrent Cost Items are often critical for sustaining the value in use of the IS and be significant elements of the “lifecycle” cost of the System. Especially between one-time, permanent software licenses and annual software licenses, there is substantial scope for bidders to shift costs from Supply and Install Items” to Recurrent Cost Items. Accordingly, it is often important to factor Recurrent Costs into bid price comparisons. That said, how Recurrent Cost Items are factored into the bid price evaluation needs to be carefully balanced against the significant complexity they add to the procurement process and documents

Those wishing to submit comments or questions on these documents, or to obtain additional information on procurement under Islamic Development Bank Project Financing are encouraged to contact:

Project Procurement (PPR)

Country Programs Complex (CPC)

The Islamic Development Bank

8111 King Khalid St.  
AI Nuzlah AI Yamania Dist. Unit No. 1  
Jeddah 22332-2444

Kingdom of Saudi Arabia

ppr@isdb.org

http://www.isdb.org

**Summary Description**

**Specific Procurement Notice**

**Specific Procurement Notice - Invitation for Bids (IFB) or notice to Prequalified Bidders**

Two Invitation for Bids templates are available. The Purchaser shall select the appropriate option.

Option 1: SPN IFB is for a Bidding process without prequalification.

Option 2: IFB is for a Bidding process with prequalification.

**Bidding Document: Request for Bids - Information Systems Design, Supply, and Installation (One-Envelope Bidding Process) (With or Without Prequalification)**

**PART 1 – BIDDING PROCEDURES**

**Section I - Instructions to Bidders (ITB)**

This Section provides relevant information to help Bidders prepare their Bids. It is based on a one-envelope Bidding process. Information is also provided on the submission, opening, and evaluation of Bids and on the award of Contracts. **Section I contains provisions that are to be used without modification.**

**Section II - Bid Data Sheet (BDS)**

This Section consists of provisions that are specific to each procurement and that supplement the information or requirements included in Section I, Instructions to Bidders.

**Section III - Evaluation and Qualification Criteria**

This Section specifies which methodology will be used to determine the Bid offering the most Value for Money. The Bid offering the most Value for Money is the Bid determined to be:

(a) substantially responsive to the bidding document, and

(b) the highest score in conformity with the evaluation method and criteria spelled out in this Section.

Two alternative Sections III, Evaluation and Qualification Criteria are provided to address the possibility of having or not having prequalification of Bidders.

**Section IV - Bidding Forms**

This Section contains the forms to be completed by the Bidder and submitted as part of the Bid

**Section V - Eligible Countries**

This Section contains information regarding eligible countries.

**Section VI - IsDB Policy – Corrupt and Fraudulent Practices**

This section provides the Proposers with the reference to IsDB’s policy regarding corrupt and fraudulent practices applicable to this process.

**PART 2 – PURCHASER’S REQUIREMENTS**

**Section VII - Requirements for the Information System**

This Section contains Technical Requirements, Implementation Schedule, and System Inventory Tables, as well as Background and Informational Materials

**PART 3 –CONTRACT**

**Section VIII - General Conditions of Contract (GCC)**

This Section contains the general clauses to be applied in all contracts. **The text of the clauses in this Section shall not be modified.**

**Section IX - Particular Conditions of Contract (PCC)**

This Section contains the Particular Conditions of Contract (PCC). The contents of this Section modify or supplement the General Conditions and shall be prepared by the Purchaser.

**Section X - Contract Forms**

This Section contains the Letter of Acceptance, Contract Agreement and other relevant forms.

**Template Option 1**

**Specific Procurement Notice – Invitation for Bids without Prequalification**

**Invitation for Bid**

**Information Systems**

**(Design, Supply and Installation)**

**(Without Prequalification)**

Purchaser**:** *[insert* ***the name of the Purchaser’s agency****]*

Project**:***[insert* ***name of project****]*

Contract title**:** *[insert* ***the name of the contract****]*

Country**:** *[insert* ***country where IFB is issued****]*

Financing No.: *[insert* ***reference number for the financing****]*

IFB No:*[insert* ***IFB reference number from Procurement Plan****]*

Issued on:*[insert* ***date when IFB is issued to the market****]*

1. The *[insert* ***name of Beneficiary/Recipient****] [specify* ***has received/has applied for/intends to apply for****]* financing from the Islamic Development Bank (IsDB) toward the cost of the *[insert* ***name of project or grant****]*, and intends to apply part of the proceeds toward payments under the contract [[1]](#footnote-2)for *[insert* ***title of contract****]*[[2]](#footnote-3).

2. The *[insert* ***name of implementing agency****]* now invites sealed Bids from eligible Bidders for *[insert* ***brief description of Information System required, installation period, location, etc****.][[3]](#footnote-4)*.

3. Bidding will be conducted through international competitive bidding using Invitation for Bids (IFB) as specified in the as specified in the IsDB’s Guidelines for Procurement of Good, Works and related services under Projects Financed by IsDB, April 2019 (the “Guidelines”), and is open to all eligible Bidders as defined in the Procurement Guidelines.

4. Interested eligible Bidders may obtain further information from *[insert* ***name of implementing agency****, insert* ***name and e-mail of officer in charge****]* and inspect the bidding document during office hours *[insert* ***office hours if applicable*** *e.g., 0900 to 1700 hours]* at the address given below *[state* ***address at the end of this IFB****]*[[4]](#footnote-5)*.*

5. The bidding document in *[insert* ***name of language****]* may be purchased by interested eligible Bidders upon the submission of a written application to the address below and upon payment of a nonrefundable fee[[5]](#footnote-6) of *[insert* ***amount in Beneficiary’s currency or in a convertible currency****]*. The method of payment will be *[insert* ***method of payment****]*.[[6]](#footnote-7) The document will be sent by *[insert* ***delivery procedure****]*.[[7]](#footnote-8)

6. Bids must be delivered to the address below *[state* ***address at the end of this IFB****]*[[8]](#footnote-9) on or before *[insert* ***time and date****].* Electronic Bidding *[specify* ***will / will not****]* be permitted. Late Bids will be rejected. Bids will be publicly opened in the presence of the Bidders’ designated representatives and anyone who chooses to attend at the address below *[state* ***address at the end of this IFB****]* on *[insert* ***time and date****]*.

7. All Bids must be accompanied by a *[insert “****Bid Security****” or “****Bid-Securing Declaration****,” as appropriate]* of *[insert* ***amount and currency in case of a Bid Security****].*

8.

The address (es) referred to above is (are): *[insert* ***detailed address (es****)]*

*[Insert* ***name of office****]*

*[Insert* ***name of officer and title****]*

*[Insert* ***postal address and/or street address, postal code, city and country****]*

*[Insert* ***telephone number, country and city codes****]*

*[Insert* ***facsimile number, country and city codes****, if applicable, delete]*

*[Insert* ***email address****]*

*[Insert* ***web site address****, if applicable, otherwise delete]*

**Template Option 2**

**Request for Bids – after Prequalification**

**Request for Bid**

**Information Systems**

**(Design, Supply and Installation)**

**(After Prequalification)**

Purchaser**:** *[insert the* ***name of the Purchaser’s agency****]*

Project:*[insert* ***name of project****]*

Contract title:*[insert* ***the name of the contract****]*

Country**:** *[insert* ***country where IFB is issued****]*

Financing No.: *[insert* ***reference number for financing****]*

IFB No: *[insert* ***IFB reference number from Procurement Plan****]*

Issued on: *[insert* ***date when IFB is issued to the Bidders****]*

1. The *[insert* ***name of Beneficiary/Recipient****] [specify* ***has received / has applied for / intends to apply for****]* financing from the Islamic Development Bank (IsDB) toward the cost of the *[insert* ***name of project or grant****],* and intends to apply part of the proceeds toward payments under the contract [[9]](#footnote-10)for *[insert* ***title of contract****]*[[10]](#footnote-11).

2. The *[insert* ***name of implementing agency****]* now invites sealed Bids from prequalified eligible Bidders for *[insert* ***brief description of Information Systems required, installation period location, etc****.][[11]](#footnote-12)*.

3. Bidding will be conducted through international competitive bidding using Invitation for Bids (IFB) as specified in the as specified in the IsDB’s Guidelines for Procurement of Good, Works and related services under Projects Financed by IsDB, April 2019 (the “Guidelines”), and is open to all prequalified eligible Bidders.

4. Prequalified eligible Bidders may obtain further information from *[insert* ***name of implementing agency, insert name and e-mail of officer in charge****]* and inspect the bidding document during office hours *[insert* ***office hours*** *if applicable e.g., 0900 to 1700 hours]* at the address given below *[state* ***address at the end of this IFB****]* [[12]](#footnote-13)*.*

5. The bidding document in *[insert* ***name of language****]* may be purchased by prequalified eligible Bidders upon the submission of a written application to the address below and upon payment of a nonrefundable fee[[13]](#footnote-14) of *[insert* ***amount in Beneficiary’s currency or in a convertible currency****].* The method of payment will be *[insert* ***method of payment****]*.[[14]](#footnote-15) The document will be sent by *[insert* ***delivery procedure****].*[[15]](#footnote-16)

6. Bids must be delivered to the address specified below *[****state address at the end of this IFB****]*[[16]](#footnote-17) on or before *[insert* ***time and date****].* Electronic bidding *[specify* ***will / will not****]* be permitted. Late Bids will be rejected. Bids will be publicly opened in the presence of the Bidders’ designated representatives and anyone who chooses to attend at the address below *[state* ***address at the end of this IFB****]* on *[insert* ***time and date****]*.

7. All Bids must be accompanied by a *[insert “****Bid Security****” or “****Bid-Securing Declaration****,” as appropriate]* of *[insert* ***amount and currency in case of a Bid Security****]*.

8.

9. The address (es) referred to above is (are): *[insert detailed address (es)]*

*[Insert* ***name of office****]*

*[Insert* ***name of officer and title****]*

*[Insert* ***facsimile number, country and city codes****, if applicable, otherwise delete]*

*[Insert* ***email address****]*

*[Insert* ***web site address****, if applicable, otherwise delete]*

**Invitation for Bids**

**Information Systems**

**Design, Supply and Installation**

**(One-Envelope Bidding Process)**

**(With or Without Prequalification)**

**Procurement of:**

***[****insert identification of the Information System]* **\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**

Purchaser: *[insert* ***the name of the Purchaser’s agency****]*

Project:*[insert* ***name of project****]*

Contract title:*[insert* ***the name of the contract****]*

Country:*[insert* ***country where IFB is issued****]*

Financing No.: *[insert* ***reference number for financing****]*

IFB No: *[insert* ***IFB reference number from Procurement Plan****]*

Issued on:*[insert* ***date when IFB is issued to the market****]*

**Table of Contents**

[Section I - Instructions to Bidders (ITB) 2](#_Toc43460414)

[Section II - Bid Data Sheet (BDS) 39](#_Toc43460415)

[Section III - Evaluation and Qualification Criteria (After Prequalification) 51](#_Toc43460416)

[Section III - Evaluation and Qualification Criteria (Without Prequalification) 57](#_Toc43460417)

[Section IV - Bidding Forms 72](#_Toc43460418)

[Section V - Eligible Countries 121](#_Toc43460419)

[Section VI - Fraud and Corruption 123](#_Toc43460420)

[Section VII - Requirements of the Information System 126](#_Toc43460421)

[Section VIII - General Conditions of Contract 160](#_Toc43460422)

[Section IX - Special Conditions of Contract 243](#_Toc43460423)

[Section X - Contract Forms 263](#_Toc43460424)

PART 1 – Bidding Procedures

Section I - Instructions to Bidders (ITB)

## Contents

[A. General 4](#_Toc43486689)

[1. Scope of Bid 4](#_Toc43486690)

[2. Source of Funds 5](#_Toc43486691)

[3. Fraud and Corruption 5](#_Toc43486692)

[4. Eligible Bidders 5](#_Toc43486693)

[5. Eligible Goods and Services 9](#_Toc43486694)

[B. Contents of Bidding Document 9](#_Toc43486695)

[6. Sections of Bidding Document 9](#_Toc43486696)

[7. Clarification of Bidding Document, Site Visit, Pre-bid Meeting 11](#_Toc43486697)

[8. Amendment of Bidding Document 12](#_Toc43486698)

[C. Preparation of Bids 12](#_Toc43486699)

[9. Cost of Bidding 12](#_Toc43486700)

[10. Language of Bid 12](#_Toc43486701)

[11. Documents Comprising the Bid 12](#_Toc43486702)

[12. Letter of Bid and Price Schedules 14](#_Toc43486703)

[13. Alternative Bids 14](#_Toc43486704)

[14. Documents Establishing the Eligibility of the Information System 15](#_Toc43486705)

[15. Documents Establishing the Eligibility and Qualifications of the Bidder 15](#_Toc43486706)

[16. Documents Establishing Conformity of the Information System 15](#_Toc43486707)

[17. Bid Prices 16](#_Toc43486708)

[18. Currencies of Bid and Payment 19](#_Toc43486709)

[19. Period of Validity of Bids 19](#_Toc43486710)

[20. Bid Security 20](#_Toc43486711)

[21. Format and Signing of Bid 22](#_Toc43486712)

[D. Submission and Opening of Bids 22](#_Toc43486713)

[22. Submission, Sealing and Marking of Bids 22](#_Toc43486714)

[23. Deadline for Submission of Bids 23](#_Toc43486715)

[24. Late Bids 23](#_Toc43486716)

[25. Withdrawal, Substitution, and Modification of Bids 24](#_Toc43486717)

[26. Bid Opening 24](#_Toc43486718)

[E. Evaluation and Comparison of Bids 26](#_Toc43486719)

[27. Confidentiality 26](#_Toc43486720)

[28. Clarification of Bids 26](#_Toc43486721)

[29. Deviations, Reservations, and Omissions 26](#_Toc43486722)

[30. Determination of Responsiveness 27](#_Toc43486723)

[31. Nonmaterial Nonconformities 28](#_Toc43486724)

[32. Correction of Arithmetical Errors 28](#_Toc43486725)

[33. Conversion to Single Currency 29](#_Toc43486726)

[34. Margin of Preference 29](#_Toc43486727)

[35. Evaluation of Bids 29](#_Toc43486728)

[36. Comparison of Bids 31](#_Toc43486729)

[37. Abnormally Low Bids 31](#_Toc43486730)

[38. Unbalanced or Front Loaded Bids 32](#_Toc43486731)

[39. Eligibility and Qualification of the Bidder 32](#_Toc43486732)

[40. Purchaser’s Right to Accept Any Bid, and to Reject Any or All Bids 33](#_Toc43486733)

[41. Standstill Period 33](#_Toc43486734)

[42. Notification of Intention to Award 33](#_Toc43486735)

[F. Award of Contract 34](#_Toc43486736)

[43. Award Criteria 34](#_Toc43486737)

[44. Purchaser’s Right to Vary Quantities at Time of Award 34](#_Toc43486738)

[45. Notification of Award 35](#_Toc43486739)

[46. Debriefing by the Purchaser 35](#_Toc43486740)

[47. Signing of Contract 36](#_Toc43486741)

[48. Performance Security 37](#_Toc43486742)

[49. Adjudicator 37](#_Toc43486743)

[50. Procurement Related Complaint 38](#_Toc43486744)

**Section I - Instructions to Bidders**

A. General

|  |  |
| --- | --- |
| 1. Scope of Bid | * 1. The Purchaser, as indicated in the BDS, issues this bidding document for the supply and installation of the Information System as specified in Section VII, Purchaser’s Requirements. The name, identification and number of lots (contracts) of this IFB are specified in the BDS. |
|  | * 1. Unless otherwise stated, throughout this bidding document definitions and interpretations shall be as prescribed in the Section VIII, General Conditions of Contract. |
|  | Throughout this bidding document: the term “in writing” means communicated in written form (e.g. by mail, e-mail, fax, including if specified in the BDS, distributed or received through the electronic-procurement system used by the Purchaser) with proof of receipt;if the context so requires, “singular” means “plural” and vice versa; and  1. “Day” means calendar day, unless otherwise specified as “Business Day”. A Business Day is any day that is an official working day of the Beneficiary. It excludes the Beneficiary’s official public holidays.  “ES” means environmental and social (including Sexual Exploitation and Abuse (SEA), and Sexual Harassment (SH));“Sexual Exploitation and Abuse” “(SEA)” means the following:Sexual Exploitation is defined as any actual or attempted abuse of position of vulnerability, differential power or trust, for sexual purposes, including, but not limited to, profiting monetarily, socially or politically from the sexual exploitation of another;Sexual Abuse is defined as the actual or threatened physical intrusion of a sexual nature, whether by force or under unequal or coercive conditions.“Sexual Harassment” “(SH)” is defined as unwelcome sexual advances, requests for sexual favors, and other verbal or physical conduct of a sexual nature by the Supplier’s or its Subcontractors’ personnel with other Supplier’s or Subcontractors’ personnel or Purchaser’s personnel. |
| 1. Source of Funds | * 1. The Beneficiary or Recipient (hereinafter called “Beneficiary”) indicated in the BDS has applied for or received financing (hereinafter called “funds”) from the Islamic Development Bank (hereinafter called “IsDB”) in an amount specified in the BDS toward the project named in the BDS. The Beneficiary intends to apply a portion of the funds to eligible payments under the contract(s) for which this bidding document is issued.   2. Payments by IsDB will be made only at the request of the Beneficiary and upon approval by IsDB in accordance with the terms and conditions of the Financing Agreement. The Financing Agreement prohibits a withdrawal from the Financing account for the purpose of any payment to persons or entities, or for any import of equipment, materials or any other goods, if such payment or import, to the knowledge of IsDB, is prohibited by a decision of the Organization of the Islamic Cooperation, the League of Arab States or the African Union.. No party other than the Beneficiary shall derive any rights from the Financing Agreement or have any claim to the funds. |
| 1. Fraud and Corruption | * 1. IsDB requires compliance with its policy in regard to corrupt and fraudulent practices, as set forth in Section VI. |
|  | * 1. In further pursuance of this policy, Bidders shall permit and shall cause their agents (where declared or not), subcontractors, subconsultants, service providers, suppliers, and personnel, to permit IsDB to inspect all accounts, records and other documents relating to any initial selection process, prequalification process, bid submission, proposal submission and contract performance (in the case of award), and to have them audited by auditors appointed by IsDB. |
| 1. Eligible Bidders | * 1. A Bidder may be a firm that is a private entity, a state-owned enterprise or institution subject to ITB 4.6, or any combination of such entities in the form of a joint venture (JV) under an existing agreement or with the intent to enter into such an agreement supported by a letter of intent. In the case of a joint venture, all members shall be jointly and severally liable for the execution of the Contract in accordance with the Contract terms. The JV shall nominate a Representative who shall have the authority to conduct all business for and on behalf of any and all the members of the JV during the Bidding process and, in the event the JV is awarded the Contract, during contract execution. Unless specified in the BDS, there is no limit on the number of members in a JV. |
|  | * 1. A Bidder shall not have a conflict of interest. Any Bidder found to have a conflict of interest shall be disqualified. A Bidder may be considered to have a conflict of interest for the purpose of this Bidding process, if the Bidder:  directly or indirectly controls, is controlled by or is under common control with another Bidder; orreceives or has received any direct or indirect subsidy from another Bidder; orhas the same legal representative as another Bidder; orhas a relationship with another Bidder, directly or through common third parties, that puts it in a position to influence the Bid of another Bidder, or influence the decisions of the Purchaser regarding this Bidding process; orany of its affiliates participates as a consultant in the preparation of the design or technical specifications of the Information System that are the subject of the Bid; oror any of its affiliates has been hired (or is proposed to be hired) by the Purchaser or Beneficiary as Project Manager for the Contract implementation; orwould be providing goods, works, or non-consulting services resulting from or directly related to consulting services for the preparation or implementation of the project specified in the BDS ITB 2.1 that it provided or were provided by any affiliate that directly or indirectly controls, is controlled by, or is under common control with that firm; orhas a close business or family relationship with a professional staff of the Beneficiary (or of the project implementing agency, or of a recipient of a part of the loan) who: (i) are directly or indirectly involved in the preparation of the bidding document or specifications of the Contract, and/or the Bid evaluation process of such Contract; or (ii) would be involved in the implementation or supervision of such Contract unless the conflict stemming from such relationship has been resolved in a manner acceptable to IsDB throughout the Bidding process and execution of the Contract. |
|  | * 1. A firm that is a Bidder (either individually or as a JV member) shall not participate as a Bidder or as JV member in more than one Bid except for permitted alternative Bids. Such participation shall result in the disqualification of all Bids in which the firm is involved. However, this does not limit the participation of a Bidder as subcontractor in another Bid or of a firm as a subcontractor in more than one Bid. |
|  | * 1. A Bidder may have the nationality of any country, subject to the restrictions pursuant to ITB 4.8. A Bidder shall be deemed to have the nationality of a country if the Bidder is constituted, incorporated or registered in and operates in conformity with the provisions of the laws of that country, as evidenced by its articles of incorporation (or equivalent documents of constitution or association) and its registration documents, as the case may be. This criterion also shall apply to the determination of the nationality of proposed sub-contractors or sub-consultants for any part of the Contract including related Services. |
|  | * 1. A Bidder that has been sanctioned by IsDB, in accordance with the above ITB 3.1, including in accordance with the Guidelines for Procurement of Goods, Works and Related Services under IsDB Project Financing (“Procurement Guidelines”), shall be ineligible to be prequalified for, bid for, or be awarded an IsDB-financed contract or benefit from an IsDB-financed contract, financially or otherwise, during such period of time as IsDB shall have determined. The list of debarred firms and individuals is available at the electronic address specified in the BDS. |
|  | * 1. To be eligible, a government-owned enterprise or institution shall establish to IsDB’s satisfaction, through all relevant documents, including its Charter and other information IsDB may request, that it: (i) is a legal entity separate from the government; (ii) does not currently receive substantial subsidies or budget support; (iii) operates like any commercial enterprise, and, inter alia, is not obliged to pass on its surplus to the government, can acquire rights and liabilities, borrow funds and be liable for repayment of its debts, and can be declared bankrupt; and (iv) is not bidding for a contract to be awarded by the department or agency of the government which under their applicable laws or regulations is the reporting or supervisory authority of the enterprise or has the ability to exercise influence or control over the enterprise or institution. |
|  | * 1. A Bidder shall not be under suspension from bidding by the Purchaser as the result of the operation of a Bid–Securing Declaration. |
|  | * 1. Firms and individuals may be ineligible if so indicated in Section V and (a) as a matter of law or official regulations, the Beneficiary’s country prohibits commercial relations with that country, provided that IsDB is satisfied that such exclusion does not preclude effective competition for the supply of goods or the contracting of works or services required; or (b) by the Boycott Regulations of the Organization of the Islamic Cooperation, the League of Arab States and the African Union, the Beneficiary’s country prohibits any import of goods or contracting of works or services from that country, or any payments to any country, person, or entity in that country. |
|  | * 1. This Bidding is open for all eligible Bidders, unless otherwise specified in ITB 15.2.   2. A Bidder shall provide such documentary evidence of eligibility satisfactory to the Purchaser, as the Purchaser shall reasonably request. |
|  | * 1. A sanction of debarment by the Beneficiary shall not cause a firm to be ineligible to participate in this procurement, unless IsDB, after review at the Beneficiary’s request, is satisfied that the debarment; (a) relates to fraud or corruption, and (b) followed a judicial or administrative proceeding that afforded the firm adequate due process.   2. Successful bidders, i.e. Prequalified Contractors, shall be reviewed and subject to onbaording Customer Due Diligence. Only bidders presenting satisfactory Compliance Due Diligence shall be qualified to pursue the selection process and to complete the attached IsDB AML/CFT /KYC Questionnaire/Form for further Compliance Due Diligence in accordance with IsDB Policy on Anti-Money Laundering (AML), Countering the Financing of Terrorism (CFT) and Know Your Customer (KYC) approved on 19/12/2019 through BED Resolution IsDB/BED/15/12/019/(333)/80.   Definitions:  **“Compliance Policy”**: IsDB Policy on Anti-Money Laundering (AML), Countering the Financing of Terrorism (CFT) and Know Your Customer (KYC) approved on 19/12/2019 through BED Resolution IsDB/BED/15/12/019/(333)/80.  **“Customer Due Diligence** (CDD) / **Compliance Due Diligence”:** means an onboarding process of conducting research, analysis and review aimed at knowing the customer (Know Your Customer/KYC) and understanding risks - including but not limited to Money Laundering/Terrorist Financing (ML/TF), tax evasion, sanctions, crime, integrity - dealing with the customer may pose, in accordance with IsDB Compliance Policy.  **“Money laundering”:** meansacquisition, possession. use or conversion or transferproceeds of crime, for the purpose of concealing or disguising the illicit origin of the property, as defined in the IsDB Compliance Policy.  **“Terrorist Financing:** generally, means the offence stipulated by Article 2 of the 1999 International Convention for the Suppression of the Financing of Terrorism, as defined in the IsDB Compliance Policy.  “IsDB AML/CFT/KYC/Questionnaire/Form”: see Attachment/ Annex. |
| 1. Eligible Goods and Services | * 1. The Information Systems to be supplied under the Contract and financed by the Bank may have their origin in any country subject to the restrictions specified in Section V, Eligible Countries, and all expenditures under the Contract will not contravene such restrictions. At the Employer’s request, Bidders may be required to provide evidence of the origin of materials, equipment and services. |
|  | * 1. For the purposes of this bidding document, the term “Information System” means all:  the required information technologies, including all information processing and communications-related hardware, software, supplies, and consumable items that the Supplier is required to design, supply and install under the Contract, plus all associated documentation, and all other materials and goods to be designed, supplied, installed, integrated, and made operational; andthe related software development, transportation, insurance, installation, customization, integration, commissioning, training, technical support, maintenance, repair, and other services necessary for proper operation of the Information System to be provided by the selected Bidder and as specified in the Contract. |
|  | * 1. For purposes of ITB 5.1 above, “origin” means the place where the goods and services making the Information System are produced in or supplied from. An Information System is deemed to be produced in a certain country when, in the territory of that country, through software development, manufacturing, or substantial and major assembly or integration of components, a commercially recognized product results that is substantially different in basic characteristics or in purpose or utility from its components. |

B. Contents of Bidding Document

|  |  |
| --- | --- |
| 1. Sections of Bidding Document | 6.1 The bidding document consists of Parts 1, 2, and 3, which include all the sections indicated below, and should be read in conjunction with any Addenda issued in accordance with ITB 8: |
|  | **PART 1 - Bidding Procedures**  Section I - Instructions to Bidders (ITB)  Section II - Bid Data Sheet (BDS)  Section III - Evaluation and Qualification Criteria  Section IV - Bidding Forms  Section V - Eligible Countries  Section VI - IsDB Policy-Corrupt and Fraudulent Practices  **PART 2 - Purchaser’s Requirements**  Section VII - Requirements of the IS, including:   * Technical Requirements * Implementation Schedule * System Inventory Tables * Background and Informational Materials   **PART 3 - Contract**  Section VIII - General Conditions of Contract  Section IX -Special Conditions of Contract  Section X - Contract Forms   * 1. The Specific Procurement Notice – Invitation for Bids (IFB) issued by the Purchaser is not part of this bidding document.   6.3 Unless obtained directly from the Purchaser, the Purchaser is not responsible for the completeness of documents, responses to requests for clarification, Minutes of the pre-Bid meeting (if any), or Addenda to the bidding documents in accordance with ITB 8. In case of any contradiction, documents obtained directly from the Purchaser shall prevail.  6.4 The Bidder is expected to examine all instructions, forms, terms, and specifications in the bidding document and to furnish with its Bid all information or documentation as is required by the bidding document. |
| 1. Clarification of Bidding Document, Site Visit, Pre-bid Meeting | * 1. A Bidder requiring any clarification of the bidding document shall contact the Purchaser in writing at the Purchaser’s address specified in the BDS or raise its enquiries during the pre-Bid meeting if provided for in accordance with ITB 7.4. The Purchaser will respond in writing to any request for clarification, provided that such request is received prior to the deadline for submission of Bids within a period specified in the BDS. The Purchaser’s shall forward copies of its response to all Bidders who have acquired the bidding document in accordance with ITB 6.3, including a description of the inquiry but without identifying its source. If so specified in the BDS, the Purchaser shall also promptly publish its response at the web page identified in the BDS. Should the Purchaser deem it necessary to amend the bidding document as a result of a request for clarification, it shall do so following the procedure under ITB 8 and ITB 23.2. |
|  | * 1. The Bidder may wish to visit and examine the site where the Information System is to be installed and its surroundings and obtain for itself on its own responsibility all information that may be necessary for preparing the Bid and entering into a contract. The costs of visiting the site shall be at the Bidder’s own expense.   2. The Bidder and any of its personnel or agents will be granted permission by the Purchaser to enter upon its premises and lands for the purpose of such visit, but only upon the express condition that the Bidder, its personnel, and agents will release and indemnify the Purchaser and its personnel and agents from and against all liability in respect thereof, and will be responsible for death or personal injury, loss of or damage to property, and any other loss, damage, costs, and expenses incurred as a result of the inspection.   3. The Bidder’s designated representative is invited to attend a pre-Bid meeting and/or a site visit, if provided for in the BDS. The purpose of the meeting will be to clarify issues and to answer questions on any matter that may be raised at that stage.   4. The Bidder is requested, as far as possible, to submit any questions in writing, and such question has to reach the Purchaser not later than one week before the meeting.   5. Minutes of the pre-Bid meeting, including the text of the questions raised without identifying the source, and the responses given, together with any responses prepared after the meeting, will be transmitted promptly to all Bidders who have acquired the bidding document in accordance with ITB 6.3. Any modification to the bidding document that may become necessary as a result of the pre-Bid meeting shall be made by the Purchaser exclusively through the issue of an Addendum pursuant to ITB 8 and not through the minutes of the pre-Bid meeting.   6. Nonattendance at the pre-Bid meeting will not be a cause for disqualification of a Bidder. |
| 1. Amendment of Bidding Document | * 1. At any time prior to the deadline for submission of Bids, the Purchaser may amend the bidding document by issuing addenda.   2. Any addendum issued shall be part of the bidding document and shall be communicated in writing to all who have obtained the bidding document from the Purchaser in accordance with ITB 6.3. The Purchaser shall also promptly publish the addendum on the Purchaser’s web page (if any) in accordance with ITB 7.1.   3. To give prospective Bidders reasonable time in which to take an addendum into account in preparing their Bids, the Purchaser may, at its discretion, extend the deadline for the submission of Bids, pursuant to ITB 23.2 |

C. Preparation of Bids

|  |  |
| --- | --- |
| 1. Cost of Bidding | * 1. The Bidder shall bear all costs associated with the preparation and submission of its Bid, and the Purchaser shall not be responsible or liable for those costs, regardless of the conduct or outcome of the Bidding process. |
| 1. Language of Bid | * 1. The Bid, as well as all correspondence and documents relating to the bid exchanged by the Bidder and the Purchaser, shall be written in the language specified in the BDS. Supporting documents and printed literature that are part of the Bid may be in another language provided they are accompanied by an accurate translation of the relevant passages in the language specified in the BDS, in which case, for purposes of interpretation of the Bid, such translation shall govern. |
| 1. Documents Comprising the Bid | * 1. The Bid submitted by the Bidder shall comprise the following: |
|  | 1. **Letter of Bid** prepared in accordance with ITB 12; |
|  | 1. **Price Schedules** completed in accordance with ITB 12 and ITB 17; |
|  | 1. **Bid Security or Bid-Securing Declaration** in accordance with ITB 20; |
|  | 1. **Alternative Bid:** if permissible, in accordance with ITB 13; |
|  | 1. **Authorization:** written confirmation authorizing the signatory of the Bid to commit the Bidder, in accordance with ITB 21.3; |
|  | 1. **Eligibility of Information System:** documentary evidence established in accordance with ITB 14.1 that the Information System offered by the Bidder in its Bid or in any alternative Bid, if permitted, are eligible; |
|  | 1. **Bidder’s Eligibility:** documentary evidence in accordance with ITB 15 establishing the Bidder’s eligibility and qualifications to perform the contract if its Bid is accepted; |
|  | 1. **Conformity:** documentary evidence established in accordance with ITB 16 that the Information System offered by the Bidder conform to the bidding document; |
|  | 1. **Subcontractors:** list of subcontractors, in accordance with ITB 16.4; |
|  | 1. **Intellectual Property**: a list of: Intellectual Property as defined in GCC Clause 15; 2. all Software included in the Bid, assigning each item to one of the software categories defined in GCC Clause 1.1 (c):    1. System, General Purpose, and Application Software; or    2. Standard and Custom Software; 3. all Custom Materials, as defined in GCC Clause 1.1 (c), included in the Bid; |
|  | All Materials not identified as Custom Materials shall be deemed Standard Materials, as defined in GCC Clause 1.1 (c);  Re-assignments among the Software and Materials categories, if necessary, will be made during the implementation of the Contract according to GCC Clause 39 (Changes to the Information System); and   1. any other document required **in the BDS.** |
|  | * 1. In addition to the requirements under ITB 11.1, Bids submitted by a JV shall include a copy of the Joint Venture Agreement entered into by all members indicating at least the parts of the Information System to be executed by the respective members. Alternatively, a letter of intent to execute a Joint Venture Agreement in the event of a successful Bid shall be signed by all members and submitted with the Bid, together with a copy of the proposed Agreement indicating at least the parts of the Information System to be executed by the respective members. |
|  | * 1. The Bidder shall furnish in the Letter of Bid information on commissions and gratuities, if any, paid or to be paid to agents or any other party relating to this Bid. |
| 1. Letter of Bid and Price Schedules | * 1. The Bidder shall complete the Letter of Bid, including the appropriate Price Schedules, using the relevant forms furnished in Section IV, Bidding Forms. The forms must be completed without any alterations to the text, and no substitutes shall be accepted except as provided under ITB 21.3. All blank spaces shall be filled in with the information requested. |
| 1. Alternative Bids | * 1. The BDS indicates whether alternative Bids are allowed. If they are allowed, the BDS will also indicate whether they are permitted in accordance with ITB 13.3, or invited in accordance with ITB 13.2 and/or ITB 13.4.   2. When alternatives to the Time Schedule are explicitly invited, a statement to that effect will be included in the BDS, and the method of evaluating different time schedules will be described in Section III, Evaluation and Qualification Criteria.   3. Except as provided under ITB 13.4 below, Bidders wishing to offer technical alternatives to the Purchaser’s requirements as described in the bidding document must also provide: (i) a price at which they are prepared to offer an Information System meeting the Purchaser’s requirements; and (ii) all information necessary for a complete evaluation of the alternatives by the Purchaser, including drawings, design calculations, technical specifications, breakdown of prices, and proposed installation methodology and other relevant details. Only the technical alternatives, if any, of the Bidder with the Bid offering the most Value for Money and conforming to the basic technical requirements shall be considered by the Purchaser.   4. When Bidders are invited in the BDS to submit alternative technical solutions for specified parts of the system, such parts shall be described in Section VII, Purchaser’s Requirements. Technical alternatives that comply with the performance and technical criteria specified for the Information System shall be considered by the Purchaser on their own merits, pursuant to ITB 35. |
| 1. Documents Establishing the Eligibility of the Information System | * 1. To establish the eligibility of the Information System in accordance with ITB 5, Bidders shall complete the country of origin declarations in the Price Schedule Forms, included in Section IV, Bidding Forms. |
| 1. Documents Establishing the Eligibility and Qualifications of the Bidder | * 1. To establish its eligibility and qualifications to perform the Contract in accordance with Section III, Evaluation and Qualification Criteria, the Bidder shall provide the information requested in the corresponding information sheets included in Section IV, Bidding Forms.   2. In the event that prequalification of potential Bidders has been undertaken as stated in the BDS, only Bids from prequalified Bidders shall be considered for award of Contract. These qualified Bidders should submit with their Bids any information updating their original prequalification applications or, alternatively, confirm in their Bids that the originally submitted prequalification information remains essentially correct as of the date of Bid submission. |
| 1. Documents Establishing Conformity of the Information System | * 1. Pursuant to ITB 11.1 (h), the Bidder shall furnish, as part of its Bid, documents establishing the conformity to the bidding documents of the Information System that the Bidder proposes to design, supply and install under the Contract.   2. The documentary evidence of conformity of the Information System to the bidding documents including:   3. Preliminary Project Plan describing, among other things, the methods by which the Bidder will carry out its overall management and coordination responsibilities if awarded the Contract, and the human and other resources the Bidder proposes to use. The Preliminary Project Plan must also address any other topics specified in the **BDS**. In addition, the Preliminary Project Plan should state the Bidder’s assessment of what it expects the Purchaser and any other party involved in the implementation of the Information System to provide during implementation and how the Bidder proposes to coordinate the activities of all involved parties;   4. written confirmation that the Bidder accepts responsibility for the successful integration and inter-operability of all components of the Information System as required by the bidding documents;   5. an item-by-item commentary on the Purchaser’s Technical Requirements, demonstrating the substantial responsiveness of the Information System offered to those requirements. In demonstrating responsiveness, the Bidder should use the Technical Responsiveness Checklist (or Checklist Format) in the Sample Bidding Forms (Section IV). The commentary shall include explicit cross-references to the relevant pages in the supporting materials included in the bid. Whenever a discrepancy arises between the item-by-item commentary and any catalogs, technical specifications, or other preprinted materials submitted with the bid, the item-by-item commentary shall prevail;   6. support material (e.g., product literature, white papers, narrative descriptions of technologies and/or technical approaches), as required and appropriate; and   7. any separate and enforceable contract(s) for Recurrent Cost items which the BDS ITB 17.2 requires Bidders to bid.   8. References to brand names or model numbers or national or proprietary standards designated by the Purchaser in the bidding documents are intended to be descriptive and not restrictive. Except as specified in the BDS for specific items or standards, the Bidder may substitute alternative brand/model names or standards in its bid, provided that it demonstrates to the Purchaser’s satisfaction that the use of the substitute(s) will result in the Information System being able to perform substantially equivalent to or better than that specified in the Technical Requirements.   9. For major items of the Information System as listed by the Purchaser in Section III, Evaluation and Qualification Criteria, which the Bidder intends to purchase or subcontract, the Bidder shall give details of the name and nationality of the proposed subcontractors, including manufacturers, for each of those items. In addition, the Bidder shall include in its Bid information establishing compliance with the requirements specified by the Purchaser for these items. Quoted rates and prices will be deemed to apply to whichever subcontractor is appointed, and no adjustment of the rates and prices will be permitted.   10. The Bidder shall be responsible for ensuring that any subcontractor proposed complies with the requirements of ITB 4, and that any goods or services to be provided by the subcontractor comply with the requirements of ITB 5 and ITB 16.1. |
| 1. Bid Prices | * 1. All Goods and Services identified in the Supply and Installation Cost Sub-Tables in System Inventory Tables in Section VII, and all other Goods and Services proposed by the Bidder to fulfill the requirements of the Information System, must be priced separately and summarized in the corresponding cost tables in the Sample Bidding Forms (Section IV), in accordance with the instructions provided in the tables and in the manner specified below. |
|  | * 1. Unless otherwise specified in the BDS, the Bidder must also bid Recurrent Cost Items specified in the Technical Requirements, Recurrent Cost Sub-Table of the System Inventory Tables in Section VII (if any). These must be priced separately and summarized in the corresponding cost tables in the Sample Bidding Forms (Section IV), in accordance with the instructions provided in the tables and in the manner specified below:  1. **if specified in the BDS,** the Bidder must also bid separate enforceable contracts for the Recurrent Cost Items not included in the main Contract; 2. prices for Recurrent Costs are all-inclusive of the costs of necessary Goods such as spare parts, software license renewals, labor, etc., needed for the continued and proper operation of the Information System and, if appropriate, of the Bidder’s own allowance for price increases; 3. prices for Recurrent Costs beyond the scope of warranty services to be incurred during the Warranty Period, defined in GCC Clause 29.4 and prices for Recurrent Costs to be incurred during the Post-Warranty Period, defined in SCC Clause 1.1. (e) (xiii), shall be quoted as Service prices on the Recurrent Cost Sub-Table in detail, and on the Recurrent Cost Summary Table in currency totals. |
|  | * 1. Unit prices must be quoted at a level of detail appropriate for calculation of any partial deliveries or partial payments under the contract, in accordance with the Implementation Schedule in Section VII), and with GCC and SCC Clause 12 – Terms of Payment. Bidders may be required to provide a breakdown of any composite or lump-sum items included in the Cost Tables |
|  | * 1. The price of items that the Bidder has left blank in the cost tables provided in the Sample Bid Forms (Section IV) shall be assumed to be included in the price of other items. Items omitted altogether from the cost tables shall be assumed to be omitted from the bid and, provided that the bid is substantially responsive, an adjustment to the bid price will be made during bid evaluation in accordance with ITB 31.3. |
|  | * 1. The prices for Goods components of the Information System are to be expressed and shall be defined and governed in accordance with the rules prescribed in the edition of Incoterms specified in the BDS, as follows:  1. Goods supplied from outside the Purchaser’s country:   Unless otherwise specified **in the BDS**, the prices shall be quoted on a CIP (named place of destination) basis, exclusive of all taxes, stamps, duties, levies, and fees imposed in the Purchaser’s country. The named place of destination and special instructions for the contract of carriage are as specified in the SCC for GCC 1.1 (e) (iii)**.** In quoting the price, the Bidder shall be free to use transportation through carriers registered in any eligible countries. Similarly, the Bidder may obtain insurance services from any eligible source country;  (b) Locally supplied Goods:  Unit prices of Goods offered from within the Purchaser’s Country, shall be quoted on an EXW (ex factory, ex works, ex warehouse or off-the-shelf, as applicable) basis, including all customs duties, levies, fees, sales and other taxes incurred until delivery of the Goods, but excluding all VAT or sales and other taxes and duties/fees incurred for the Goods at the time of invoicing or sales transaction, if the Contract is awarded;  (c) Inland transportation.   * 1. Unless otherwise stated in the BDS, inland transportation, insurance and related local costs incidental to the delivery of the Goods to the designated Project Sites must be quoted separately as a Service item in accordance with ITB 17.5, whether the Goods are to be supplied locally or from outside the Purchaser’s country, except when these costs are already included in the price of the Goods, as is, e.g., the case, when ITB 17.5 (a) specifies CIP, and the named places of destination are the Project Sites. |
|  | * 1. The price of Services shall be separated into their local and foreign currency components and where appropriate, broken down into unit prices. Prices must include all taxes, duties, levies and fees whatsoever, except only VAT or other indirect taxes, or stamp duties, that may be assessed and/or apply in the Purchaser’s country on/to the price of the Services invoiced to the Purchaser, if the Contract is awarded.   2. Unless otherwise specified in the BDS, the prices must include all costs incidental to the performance of the Services, as incurred by the Supplier, such as travel, subsistence, office support, communications, translation, printing of materials, etc. Costs incidental to the delivery of the Services but incurred by the Purchaser or its staff, or by third parties, must be included in the price only to the extent such obligations are made explicit in these bidding documents (as, e.g., a requirement for the Bidder to include the travel and subsistence costs of trainees). |
|  | * 1. Unless otherwise specified in the BDS, prices quoted by the Bidder shall be fixed during the Bidder’s performance of the Contract and not subject to increases on any account. Bids submitted that are subject to price adjustment will be rejected. |
| 1. Currencies of Bid and Payment | * 1. The currency(ies) of the Bid and currencies of payment shall be the same. The Bidder shall quote in the currency of the Purchaser’s Country the portion of the Bid price that corresponds to expenditures incurred in the currency of the Purchaser’s Country, unless otherwise specified in the BDS.   2. The Bidder may express the Bid price in any currency. If the Bidder wishes to be paid in a combination of amounts in different currencies, it may quote its price accordingly but shall use no more than three foreign currencies in addition to the currency of the Purchaser’s Country. |
| 1. Period of Validity of Bids | * 1. Bids shall remain valid until the date specified in the BDS or any extended date if amended by the Purchaser in accordance with ITB 8. A Bid that is not valid until the date specified in the BDS, or any extended date if amended by the Purchaser in accordance with ITB 8, shall be rejected by the Purchaser as nonresponsive. |
|  | * 1. In exceptional circumstances, prior to the date of expiry of the Bid validity, the Purchaser may request Bidders to extend the date of validity until a specified date. The request and the responses shall be made in writing. If a Bid Security is requested in accordance with ITB 20.1, it shall also be extended for twenty-eight days (28) beyond the deadline of the extended validity period. A Bidder may refuse the request without forfeiting its Bid Security. A Bidder granting the request shall not be required or permitted to modify its Bid, except as provided in ITB 19.3. |
|  | * 1. If the award is delayed by a period exceeding fifty-six (56) days beyond the expiry of the initial Bid validity specified in accordance with ITB 19.1, the Contract price shall be determined as follows:   (a) in case of fixed price contracts, the contract price shall be the Bid price adjusted by a factor or factors specified **in the BDS**;  (b) in the case of an adjustable price contracts, no adjustments shall be made;  (c) in any case, Bid evaluation shall be based on the Bid Price without taking into consideration the applicable correction from those indicated above. |
| 1. Bid Security | * 1. The Bidder shall furnish as part of its Bid, either a Bid-Securing Declaration or a Bid Security as specified in the BDS, in original form and, in the case of a Bid Security, in the amount and currency specified in the BDS. |
|  | * 1. A Bid-Securing Declaration shall use the form included in Section IV, Bidding Forms. |
|  | * 1. If a Bid Security is specified pursuant to ITB 20.1, the bid security shall be a demand guarantee in any of the following forms at the Bidder’s option: |
|  | * + 1. an unconditional guarantee issued by a non-bank financial institution (such as an insurance, bonding or surety company); |
|  | * + 1. an irrevocable letter of credit; or |
|  | * + 1. a cashier’s or certified check, |
|  |  |
|  | from a reputable source from an eligible country. If an unconditional guarantee is issued by a non-bank financial institution located outside the Purchaser’s Country the issuing non-bank financial institution shall have a correspondent financial institution located in the Purchaser’s Country to make it enforceable unless the Purchaser has agreed in writing, prior to Bid submission, that a correspondent financial institution is not required. |
|  | * 1. In the case of a bank guarantee, the Bid Security shall be submitted either using the Bid Security Form included in Section IV, Bidding Forms or in another substantially similar format approved by the Purchaser prior to Bid submission. In either case, the form must include the complete name of the Bidder. The Bid Security shall be valid for twenty-eight (28) days beyond the original date of expiry of the Bid validity, or beyond any extended date if requested under ITB 19.2. |
|  | * 1. If a Bid Security or a Bid-Securing Declaration is specified pursuant to ITB 20.1, any Bid not accompanied by a substantially responsive Bid Security or Bid-Securing Declaration shall be rejected by the Purchaser as non-responsive. |
|  | * 1. If a Bid Security is specified pursuant to ITB 20.1, the Bid Security of unsuccessful Bidders shall be returned as promptly as possible upon the successful Bidder’s furnishing of the Performance Security pursuant to ITB 48. |
|  | * 1. The Bid Security of the successful Bidder shall be returned as promptly as possible once the successful Bidder has signed the Contract and furnished the required Performance Security. |
|  | * 1. The Bid Security may be forfeited:  1. if a Bidder withdraws its Bid prior to the expiry date of Bid validity specified by the Bidder on the Letter of Bid or any extended date provided by the Bidder; or 2. if the successful Bidder fails to:  sign the Contract in accordance with ITB 47; or  * 1. furnish a performance security in accordance with ITB 48. |
|  | * 1. The Bid Security or the Bid-Securing Declaration of a JV shall be in the name of the JV that submits the bid. If the JV has not been legally constituted into a legally enforceable JV at the time of Bidding, the Bid Security or the Bid-Securing Declaration shall be in the names of all future members as named in the letter of intent referred to in ITB 4.1 and ITB 11.2. |
|  | * 1. If a Bid Security is not required in the BDS, and;   (a) a Bidder withdraws its Bid prior to the expiry date of the Bid validity specified by the Bidder on the Letter of Bid, or any extended date provided by the Bidder; or  (b) the successful Bidder fails to: sign the Contract in accordance with ITB 47; or furnish a Performance Security in accordance with ITB 48;  the Purchaser may, if provided for in the BDS, declare the Bidder disqualified to be awarded a contract by the Purchaser for a period of time as stated in the BDS. |
| 1. Format and Signing of Bid | * 1. The Bidder shall prepare one original of the documents comprising the Bid as described in ITB 11 and clearly mark it “Original.” Alternative Bids, if permitted in accordance with ITB 13, shall be clearly marked “Alternative”. In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS and clearly mark them “Copy.” In the event of any discrepancy between the original and the copies, the original shall prevail.   2. Bidders shall mark as “CONFIDENTIAL” information in their Bids which is confidential to their business. This may include proprietary information, trade secrets, or commercial or financially sensitive information. |
|  | * 1. The original and all copies of the Bid shall be typed or written in indelible ink and shall be signed by a person duly authorized to sign on behalf of the Bidder. This authorization shall consist of a written confirmation as specified in the BDS and shall be attached to the Bid. The name and position held by each person signing the authorization must be typed or printed below the signature. All pages of the Bid where entries or amendments have been made shall be signed or initialed by the person signing the Bid. |
|  | * 1. In case the Bidder is a JV, the Bid shall be signed by an authorized representative of the JV on behalf of the JV, and so as to be legally binding on all the members as evidenced by a power of attorney signed by their legally authorized representatives.   2. Any interlineations, erasures, or overwriting shall be valid only if they are signed or initialed by the person signing the Bid. |

D. Submission and Opening of Bids

|  |  |  |
| --- | --- | --- |
| 1. Submission, Sealing and Marking of Bids | * 1. The Bidder shall deliver the Bid in a single, sealed envelope (one (1) envelope process). Within the single envelope the Bidder shall place the following separate, sealed envelopes:      1. in an envelope marked “ORIGINAL”, all documents comprising the Bid, as described in ITB 11; and      2. in an envelope marked “COPIES”, all required copies of the Bid; and,      3. if alternative Bids are permitted in accordance with ITB 13, and if relevant:  1. in an envelope marked “ORIGINAL – ALTERNATIVE BID”, the alternative Bid; and 2. in the envelope marked “COPIES – ALTERNATIVE BID” all required copies of the alternative Bid. | |
|  | * 1. The inner and outer envelopes shall:      1. bear the name and address of the Bidder;      2. be addressed to the Purchaser in accordance with ITB 23.1;   (c) bear the specific identification of this Bidding process indicated in accordance with ITB 1.1; and  (d) bear a warning not to open before the time and date for Bid opening.   * 1. If all envelopes are not sealed and marked as required, the Purchaser will assume no responsibility for the misplacement or premature opening of the Bid. | |
| 1. Deadline for Submission of Bids | * 1. Bids must be received by the Purchaser at the address and no later than the date and time indicated in the BDS. When so specified in the BDS, Bidders shall have the option of submitting their Bids electronically. Bidders submitting Bids electronically shall follow the electronic Bid submission procedures specified in the BDS. | |
|  | * 1. The Purchaser may, at its discretion, extend this deadline for submission of Bids by amending the bidding documents in accordance with ITB 8, in which case all rights and obligations of the Purchaser and Bidders will thereafter be subject to the deadline as extended. | |
| 1. Late Bids | * 1. The Purchaser shall not consider any Bid that arrives after the deadline for submission of Bids, in accordance with ITB 23. Any Bid received by the Purchaser after the deadline for submission of Bids shall be declared late, rejected, and returned unopened to the Bidder. | |
| 1. Withdrawal, Substitution, and Modification of Bids | * 1. A Bidder may withdraw, substitute, or modify its Bid after it has been submitted by sending a written notice, duly signed by an authorized representative, and shall include a copy of the authorization in accordance with ITB 21.3, (except that withdrawal notices do not require copies). The corresponding substitution or modification of the Bid must accompany the respective written notice. All notices must be:   (a) prepared and submitted in accordance with ITB 21 and ITB 22 (except that withdrawals notices do not require copies), and in addition, the respective envelopes shall be clearly marked “WITHDRAWAL,” “SUBSTITUTION,” “MODIFICATION;” and  (b) received by the Purchaser prior to the deadline prescribed for submission of Bids, in accordance with ITB 23. | |
|  | * 1. Bids requested to be withdrawn in accordance with ITB 25.1 shall be returned unopened to the Bidders.   2. No Bid may be withdrawn, substituted, or modified in the interval between the deadline for submission of Bids and the date of expiry of the Bid validity specified by the Bidder on the Letter of Bid or any extended date thereof. | |
| 1. Bid Opening | * 1. Except as in the cases specified in ITB 24 and ITB 25.2, the Purchaser shall conduct the Bid opening in public, in the presence of Bidders` designated representatives and anyone who chooses to attend, and at the address, date and time specified in the BDS. Any specific electronic Bid opening procedures required if electronic bidding is permitted in accordance with ITB 23.1, shall be as specified in the BDS. |
|  | * 1. First, envelopes marked “Withdrawal” shall be opened and read out and the envelope with the corresponding Bid shall not be opened, but returned to the Bidder. No Bid withdrawal shall be permitted unless the corresponding withdrawal notice contains a valid authorization to request the withdrawal and is read out at Bid opening.   2. Next, envelopes marked “Substitution” shall be opened and read out and exchanged with the corresponding Bid being substituted, and the substituted Bid shall not be opened, but returned to the Bidder. No Bid substitution shall be permitted unless the corresponding substitution notice contains a valid authorization to request the substitution and is read out at Bid opening.   3. Envelopes marked “Modification” shall be opened and read out with the corresponding Bid. No Bid modification shall be permitted unless the corresponding modification notice contains a valid authorization to request the modification and is read out at Bid opening. Only Bids that are opened and read out at Bid opening shall be considered further.   4. Next, all remaining envelopes shall be opened one at a time, reading out: the name of the Bidder and the Bid Price(s), including any discounts and alternative Bids, and indicating whether there is a modification; the presence or absence of a Bid Security or Bid-Securing Declaration; and any other details as the Purchaser may consider appropriate.   5. Only Bids, alternative Bids and discounts that are opened and read out at Bid opening shall be considered further in the evaluation. The Letter of Bid and the Price Schedules are to be initialed by representatives of the Purchaser attending Bid opening in the manner specified in the BDS.   6. The Purchaser shall neither discuss the merits of any Bid nor reject any Bid (except for late Bids, in accordance with ITB 24.1).   7. The Purchaser shall prepare a record of the Bid opening that shall include, as a minimum:  1. the name of the Bidder and whether there is a withdrawal, substitution, or modification; 2. the Bid Price, per lot if applicable, including any discounts; 3. any alternative Bids; and 4. the presence or absence of a Bid Security or a Bid-Securing Declaration.    1. The Bidders’ representatives who are present shall be requested to sign the record. The omission of a Bidder’s signature on the record shall not invalidate the contents and effect of the record. A copy of the record shall be distributed to all Bidders. |
| E. Evaluation and Comparison of Bids | | |
| 1. Confidentiality | * 1. Information relating to the evaluation of Bids and recommendation of contract award, shall not be disclosed to Bidders or any other persons not officially concerned with the Bidding process until the Notification of Intention to Award the Contract is transmitted to all Bidders in accordance with ITB 42. |
|  | * 1. Any effort by a Bidder to influence the Purchaser in the evaluation of the Bids or Contract award decisions may result in the rejection of its Bid. |
|  | * 1. Notwithstanding ITB 27.2, from the time of Bid opening to the time of Contract award, if any Bidder wishes to contact the Purchaser on any matter related to the Bidding process, it should do so in writing. |
| 1. Clarification of Bids | * 1. To assist in the examination, evaluation, and comparison of the Bids, and qualification of the Bidders, the Purchaser may, at its discretion, ask any Bidder for a clarification of its Bid. Any clarification submitted by a Bidder that is not in response to a request by the Purchaser shall not be considered. The Purchaser’s request for clarification and the response shall be in writing. No change in the prices or substance of the Bid shall be sought, offered, or permitted, except to confirm the correction of arithmetic errors discovered by the Purchaser in the evaluation of the Bids, in accordance with ITB 32. |
|  | * 1. If a Bidder does not provide clarifications of its Bid by the date and time set in the Purchaser’s request for clarification, its Bid may be rejected. |
| 1. Deviations, Reservations, and Omissions | * 1. During the evaluation of Bids, the following definitions apply:   (a) “Deviation” is a departure from the requirements specified in the bidding document;  (b) “Reservation” is the setting of limiting conditions or withholding from complete acceptance of the requirements specified in the bidding document; and  (c) “Omission” is the failure to submit part or all of the information or documentation required in the bidding document. |
| 1. Determination of Responsiveness | * 1. The Purchaser’s determination of a Bid’s responsiveness is to be based on the contents of the Bid itself, as defined in ITB 11. |
|  | * 1. A substantially responsive Bid is one that meets the requirements of the bidding document without material deviation, reservation, or omission. A material deviation, reservation, or omission is one that;   (a) if accepted, would:  (i) affect in any substantial way the scope, quality, or performance of the Information System specified in the Contract; or  (ii) limit in any substantial way, inconsistent with the bidding document, the Purchaser’s rights or the Bidder’s obligations under the proposed Contract; or  (b) if rectified, would unfairly affect the competitive position of other Bidders presenting substantially responsive Bids. |
|  | * 1. The Purchaser shall examine the technical aspects of the Bid in particular, to confirm that all requirements of Section VII, Purchaser’s Requirements have been met without any material deviation, reservation, or omission. |
|  | * 1. To be considered for Contract award, Bidders must have submitted Bids: |
|  | (a) for which detailed Bid evaluation using the same standards for compliance determination as listed in ITB 29 and ITB 30.3 confirms that the Bids are commercially and technically responsive, and include the hardware, Software, related equipment, products, Materials, and other Goods and Services components of the Information System in substantially the full required quantities for the entire Information System or, if allowed in the BDS ITB 35.8, the individual Subsystem, lot or slice Bid on; and are deemed by the Purchaser as commercially and technically responsive; and  (b) that offer Information Technologies that are proven to perform up to the standards promised in the bid by having successfully passed the performance, benchmark, and/or functionality tests the Purchaser may require, pursuant to ITB 39.3. |
| 1. Nonmaterial Nonconformities | * 1. Provided that a Bid is substantially responsive, the Purchaser may waive any nonconformity in the Bid that does not constitute a material deviation, reservation or omission. |
|  | * 1. Provided that a Bid is substantially responsive, the Purchaser may request that the Bidder submit the necessary information or documentation, within a reasonable period of time, to rectify nonmaterial nonconformities in the Bid related to documentation requirements. Requesting information or documentation on such nonconformities shall not be related to any aspect of the price of the Bid. Failure of the Bidder to comply with the request may result in the rejection of its Bid. |
|  | * 1. Provided that a Bid is substantially responsive, the Purchaser shall rectify quantifiable nonmaterial nonconformities related to the Bid Price. To this effect, the Bid Price shall be adjusted, for comparison purposes only, to reflect the price of a missing or non-conforming item or component by adding the average price of the item or component quoted by substantially responsive Bidders. If the price of the item or component cannot be derived from the price of other substantially responsive Bids, the Purchaser shall use its best estimate. |
| 1. Correction of Arithmetical Errors | * 1. Provided that the Bid is substantially responsive, the Purchaser shall correct arithmetical errors on the following basis:  1. where there are errors between the total of the amounts given under the column for the price breakdown and the amount given under the Total Price, the former shall prevail and the latter will be corrected accordingly; 2. where there are errors between the total of the amounts of Schedule Nos. 1 to 5 and the amount given in Schedule No. 6 (Grand Summary), the former shall prevail and the latter will be corrected accordingly; and 3. if there is a discrepancy between words and figures, the amount in words shall prevail, unless the amount expressed in words is related to an arithmetic error, in which case the amount in figures shall prevail subject to (a) and (b) above. |
|  | * 1. A Bidder shall be requested to accept the correction of arithmetical errors. Failure to accept the correction in accordance with ITB 32.1 shall result in the rejection of the Bid. |
| 1. Conversion to Single Currency | * 1. For evaluation and comparison purposes, the currency(ies) of the Bid shall be converted into a single currency as specified in the BDS. |
| 1. Margin of Preference | * 1. No margin of domestic preference shall apply. |
| 1. Evaluation of Bids | * 1. The Purchaser shall use the criteria and methodologies listed in this ITB and Section III, Evaluation and Qualification criteria. No other evaluation criteria or methodologies shall be permitted. By applying the criteria and methodologies the Purchaser shall determine the Bid offering the most Value for Money.   Preliminary Examination   * 1. The Purchaser will examine the bids, to determine whether they have been properly signed, whether any computational errors have been made, whether required sureties have been furnished and are substantially complete (e.g., not missing key parts of the bid or silent on substantially large portions of the Technical Requirements). In the case where a pre-qualification process was undertaken for the Contract(s) for which these bidding documents have been issued, the Purchaser will ensure that each bid is from a pre-qualified bidder and, in the case of a Joint Venture, that partners and structure of the Joint Venture are unchanged from those in the pre-qualification   Technical Evaluation   * 1. The Purchaser will examine the information supplied by the Bidders Pursuant to ITB 11 and ITB 16, and in response to other requirements in the Bidding document, taking into account the following factors:   (a) overall completeness and compliance with the Technical Requirements; and deviations from the Technical Requirements;  (b) suitability of the Information System offered in relation to the conditions prevailing at the site; and the suitability of the implementation and other services proposed, as described in the Preliminary Project Plan included in the bid;  (c) achievement of specified performance criteria by the Information System;  (d) compliance with the time schedule called for by the Implementation Schedule and any alternative time schedules offered by Bidders, as evidenced by a milestone schedule provided in the Preliminary Project Plan included in the bid;  (e) type, quantity, quality, and long-term availability of maintenance services and of any critical consumable items necessary for the operation of the Information System;  (f) any other relevant technical factors that the Purchaser deems necessary or prudent to take into consideration;  (g) any proposed deviations in the bid to the contractual and technical provisions stipulated in the bidding documents.   * 1. If specified in the BDS, the Purchaser’s evaluation of responsive Bids will take into account technical factors, in addition to cost factors. The scores to be given to technical factors and sub factors, and the weights to be assigned for the technical factors and cost are specified in the BDS. An Evaluated Bid Score (B) will be calculated for each responsive Bid using the formula, specified in Section III, Evaluation and Qualification Criteria, which permits a comprehensive assessment of the Bid cost and the technical merits of each Bid.   2. Where alternative technical solutions have been allowed in accordance with ITB 13, and offered by the Bidder, the Purchaser will make a similar evaluation of the alternatives. Where alternatives have not been allowed but have been offered, they shall be ignored. |
|  | Economic Evaluation   * 1. To evaluate a Bid, the Purchaser shall consider the following:  1. the Bid price, excluding provisional sums and the provision, if any, for contingencies in the Price Schedules; 2. price adjustment for correction of arithmetic errors in accordance with ITB 32.1; 3. price adjustment due to discounts offered in accordance with ITB 26.8; 4. converting the amount resulting from applying (a) to (c) above, if relevant, to a single currency in accordance with ITB 33; and 5. price adjustment due to quantifiable nonmaterial nonconformities in accordance with ITB 31.3; 6. the evaluation factors indicated in Section III, Evaluation and Qualification Criteria. |
|  | * 1. If price adjustment is allowed in accordance with ITB 17.9, the estimated effect of the price adjustment provisions of the Conditions of Contract, applied over the period of execution of the Contract, shall not be taken into account in Bid evaluation. |
|  | * 1. The Purchaser will evaluate and compare the Bids that have been determined to be substantially responsive, pursuant to ITB 30. The evaluation will be performed assuming either that: |
|  | (a) the Contract will be awarded to the Bid offering the most Value for Money for the entire Information System; or  (b) if specified **in the BDS**, Contracts will be awarded to the Bidders for each individual Subsystem, lot, or slice defined in the Technical Requirements whose Bids offer the most Value for Money for the entire System.  In the latter case, discounts that are conditional on the award of more than one Subsystem, lot, or slice may be offered in Bids. Such discounts will be considered in the evaluation of bids as specified **in the BDS**. |
| 1. Comparison of Bids | * 1. The Purchaser shall compare all substantially responsive Bids in accordance with ITB 35.6 to determine the lowest evaluated cost. |
| 1. Abnormally Low Bids | * 1. An Abnormally Low Bid is one where the Bid price in combination with other constituent elements of the Bid appears unreasonably low to the extent that the Bid price raises material concerns as to the capability of the Bidder to perform the Contract for the offered Bid Price. |
|  | * 1. In the event of identification of a potentially Abnormally Low Bid, the Purchaser shall seek written clarifications from the Bidder, including detailed price analyses of its Bid price in relation to the subject matter of the contract, scope, proposed methodology, schedule, allocation of risks and responsibilities and any other requirements of the bidding document.   2. After evaluation of the price analyses, in the event that the Purchaser determines that the Bidder has failed to demonstrate its capability to perform the Contract for the offered Bid Price, the Purchaser shall reject the Bid. |
| 1. Unbalanced or Front Loaded Bids | * 1. If the Bid that is evaluated as the lowest evaluated cost is, in the Purchaser’s opinion, seriously unbalanced or front loaded the Purchaser may require the Bidder to provide written clarifications. Clarifications may include detailed price analyses to demonstrate the consistency of the Bid prices with the scope of information systems, installations, proposed methodology, schedule and any other requirements of the bidding document. |
|  | * 1. After the evaluation of the information and detailed price analyses presented by the Bidder, the Purchaser may: |
|  | * + 1. accept the Bid; or     2. if appropriate, require that the total amount of the Performance Security be increased, at the expense of the Bidder, to a level not exceeding twenty percent (20%) of the Contract Price; or     3. reject the Bid. |
| 1. Eligibility and Qualification of the Bidder | * 1. The Purchaser shall determine to its satisfaction whether the Bidder that is selected as having submitted the lowest evaluated and substantially responsive Bid is eligible and meets the qualifying criteria specified in Section III, Evaluation and Qualification Criteria. |
|  | * 1. The determination shall be based upon an examination of the documentary evidence of the Bidder’s qualifications submitted by the Bidder, pursuant to ITB 15, as well as other information the Purchaser deems necessary and appropriate. This determination may include visits or interviews with the Bidder’s clients referenced in its bid and site inspections.   2. Unless otherwise specified in the BDS, the Purchaser will NOT carry out tests at the time of post-qualification, to determine that the performance or functionality of the Information System offered meets those stated in the Technical Requirements. However, if so specified in the BDS the Purchaser may carry out such tests as detailed in the BDS.   3. An affirmative determination shall be a prerequisite for award of the Contract to the Bidder. A negative determination shall result in disqualification of the Bid, in which event the Purchaser shall proceed to the next lowest evaluated cost or best evaluated Bid, as the case may be, to make a similar determination of that Bidder’s qualifications to perform satisfactorily.   4. The capabilities of the manufacturers and subcontractors proposed by the Bidder that is determined to have offered the Bid offering the most Value for Money for identified major items of supply or services will also be evaluated for acceptability in accordance with Section III, Evaluation and Qualification Criteria. Their participation should be confirmed with a letter of intent between the parties, as needed. Should a manufacturer or subcontractor be determined to be unacceptable, the Bid will not be rejected, but the Bidder will be required to substitute an acceptable manufacturer or subcontractor without any change to the Bid price. Prior to signing the Contract, the corresponding Appendix to the Contract Agreement shall be completed, listing the approved manufacturers or subcontractors for each item concerned. |
| 1. Purchaser’s Right to Accept Any Bid, and to Reject Any or All Bids | * 1. The Purchaser reserves the right to accept or reject any Bid, and to annul the Bidding process and reject all Bids at any time prior to contract award, without thereby incurring any liability to Bidders. In case of annulment, all Bids submitted and specifically, Bid securities, shall be promptly returned to the Bidders. |
| 1. Standstill Period | * 1. The Contract shall not be awarded earlier than the expiry of the Standstill Period. The Standstill Period shall be ten (10) Business Days unless extended in accordance with ITB 46. The Standstill Period commences the day after the date the Purchaser has transmitted to each Bidder the Notification of Intention to Award the Contract. Where only one Bid is submitted, or if this contract is in response to an emergency situation recognized by IsDB, the Standstill Period shall not apply. |
| 1. Notification of Intention to Award | * 1. The Purchaser shall send to each Bidder the Notification of Intention to Award the Contract to the successful Bidder. The Notification of Intention to Award shall contain, at a minimum, the following information:  1. the name and address of the Bidder submitting the successful Bid; 2. the Contract price of the successful Bid; 3. the total combined score of the successful Bid; 4. the names of all Bidders who submitted Bids, and their Bid prices as readout and as evaluated prices and technical scores (if applicable); 5. a statement of the reason(s) the Bid (of the unsuccessful Bidder to whom the notification is addressed) was unsuccessful; 6. the expiry date of the Standstill Period; and 7. instructions on how to request a debriefing or submit a complaint during the standstill period; |

F. Award of Contract

|  |  |  |
| --- | --- | --- |
| 1. Award Criteria | | * 1. Subject to ITB 40, the Purchaser shall award the Contract to the successful Bidder. This is the Bidder whose Bid has been determined to be the Bid offering the most Value for Money. The determination of the Bid offering the most Value for Money will be made in accordance to one of the two options as defined in the BDS. The methodology options are:   (a) when **rated criteria are used**: The Bidder that meets the qualification criteria and whose Bid:  (i) is substantially responsive; and  (ii) is the best evaluated Bid (i.e. the Bid with the highest combined technical/quality/price score); or  (b) when **rated criteria are not used**: The Bidder that meets the qualification criteria and whose Bid has been determined to be:  (i) substantially responsive to the bidding document; and  (ii) the lowest evaluated cost. |
| 1. Purchaser’s Right to Vary Quantities at Time of Award | | * 1. The Purchaser reserves the right at the time of Contract award to increase or decrease, by the percentage(s) for items as indicated in the BDS. |
| 1. Notification of Award | | * 1. Prior to the date of expiry of the Bid validity and upon expiry of the Standstill Period, specified in ITB 41.1 or any extension thereof, and, upon satisfactorily addressing any complaint that has been filed within the Standstill Period, the Purchaser shall notify the successful Bidder, in writing, that its Bid has been accepted. The notification letter (hereinafter and in the Contract Forms called the “Letter of Acceptance”) shall specify the sum that the Purchaser will pay the Supplier in consideration of the execution of the Contract (hereinafter and in the Conditions of Contract and Contract Forms called “the Contract Price”). |
|  | | * 1. Within ten (10) Business days after the date of transmission of the Letter of Acceptance, the Purchaser shall publish the Contract Award Notice which shall contain, at a minimum, the following information:      + - 1. name and address of the Purchaser;          2. name and reference number of the contract being awarded, and the selection method used;          3. names of all Bidders that submitted Bids, and their Bid prices as read out at Bid opening, and as evaluated;          4. name of Bidders whose Bids were rejected and the reasons for their rejection;          5. the name of the successful Bidder, the final total contract price, the contract duration and a summary of its scope; and          6. successful Bidder’s Beneficial Ownership Disclosure Form, if specified in BDS ITB 47.1.   2. The Purchaser shall publish the Contract Award Notice in UNDB online or Dg Market website in addition to IsDB’s external website and on the Purchaser’s website if available.   3. Until a formal contract is prepared and executed, the Notification of Award shall constitute a binding Contract. |
| 1. Debriefing by the Purchaser | * 1. On receipt of the Purchaser’s Notification of Intention to Award referred to in ITB 42, an unsuccessful Bidder has three (3) Business Days to make a written request to the Purchaser for a debriefing. The Purchaser shall provide a debriefing to all unsuccessful Bidders whose request is received within this deadline.   2. Where a request for debriefing is received within the deadline, the Purchaser shall provide a debriefing within five (5) Business Days, unless the Purchaser decides, for justifiable reasons, to provide the debriefing outside this timeframe. In that case, the standstill period shall automatically be extended until five (5) Business Days after such debriefing is provided. If more than one debriefing is so delayed, the standstill period shall not end earlier than five (5) Business Days after the last debriefing takes place. The Purchaser shall promptly inform, by the quickest means available, all Bidders of the extended standstill period.   3. Where a request for debriefing is received by the Purchaser later than the three (3) Business Day deadline, the Purchaser should provide the debriefing as soon as practicable, and normally no later than fifteen (15) Business Days from the date of publication of Public Notice of Award of contract. Requests for debriefing received outside the three (3)-day deadline shall not lead to extension of the standstill period.   4. Debriefings of unsuccessful Bidders may be done in writing or verbally. The Bidder shall bear their own costs of attending such a debriefing meeting. |
| 1. Signing of Contract | | * 1. The Purchaser shall send to the successful Bidder the Letter of Acceptance including the Contract Agreement. |
|  | | * 1. The successful Bidder shall sign, date and return to the Purchaser, the Contract Agreement within twenty-eight (28) days of its receipt. |
|  | | * 1. Notwithstanding ITB 47.2 above, in case signing of the Contract Agreement is prevented by any export restrictions attributable to the Purchaser, to the country of the Purchaser, or to the use of the Information System to be supplied, where such export restrictions arise from trade regulations from a country supplying those Information System, the Bidder shall not be bound by its Bid, always provided, however, that the Bidder can demonstrate to the satisfaction of the Purchaser and of IsDB that signing of the Contract Agreement has not been prevented by any lack of diligence on the part of the Bidder in completing any formalities, including applying for permits, authorizations and licenses necessary for the export of the Information System under the terms of the Contract. |
| 1. Performance Security | | * 1. Within twenty-eight (28) days of the receipt of the Letter of Acceptance from the Purchaser, the successful Bidder shall furnish the performance security in accordance with the General Conditions, subject to ITB 38.2 (b), using for that purpose the Performance Security Form included in Section X, Contract Forms, or another form acceptable to the Purchaser. If the Performance Security furnished by the successful Bidder is in the form of a bond, it shall be issued by a bonding or insurance company that has been determined by the successful Bidder to be acceptable to the Purchaser. A foreign institution providing a Performance Security shall have a correspondent financial institution located in the Purchaser’s Country, unless the Purchaser has agreed in writing that a correspondent financial institution is not required. |
|  | | * 1. Failure of the successful Bidder to submit the above-mentioned Performance Security or sign the Contract shall constitute sufficient grounds for the annulment of the award and forfeiture of the Bid Security. In that event the Purchaser may award the Contract to the Bidder offering the next Bid offering the most Value for Money. |
| 1. Adjudicator | | * 1. Unless the BDS states otherwise, the Purchaser proposes that the person named in the BDS be appointed as Adjudicator under the Contract to assume the role of informal Contract dispute mediator, as described in GCC Clause 43.1. In this case, a résumé of the named person is attached to the BDS. The proposed hourly fee for the Adjudicator is specified in the BDS. The expenses that would be considered reimbursable to the Adjudicator are also specified in the BDS. If a Bidder does not accept the Adjudicator proposed by the Purchaser, it should state its non-acceptance in its Bid Form and make a counterproposal of an Adjudicator and an hourly fee, attaching a résumé of the alternative. If the successful Bidder and the Adjudicator nominated in the BDS happen to be from the same country, and this is not the country of the Purchaser too, the Purchaser reserves the right to cancel the Adjudicator nominated in the BDS and propose a new one. If by the day the Contract is signed, the Purchaser and the successful Bidder have not agreed on the appointment of the Adjudicator, the Adjudicator shall be appointed, at the request of either party, by the Appointing Authority specified in the SCC clause relating to GCC Clause 43.1.4, or if no Appointing Authority is specified there, the Contract will be implemented without an Adjudicator. |
| 1. Procurement Related Complaint | | * 1. The procedures for making a Procurement-related Complaint are as specified in the BDS. |

Section II - Bid Data Sheet (BDS)

The following specific data for the Information System to be procured shall complement, supplement, or amend the provisions in the Instructions to Bidders (ITB). Whenever there is a conflict, the provisions in the BDS shall prevail over those in ITB.

*[Where an e-procurement system is used, modify the relevant parts of the BDS accordingly to reflect the e-procurement process]*

*[Instructions for completing the Bid Data Sheet are provided, as needed, in the notes in italics mentioned for the relevant ITB. The guidance text addressed to the Purchaser in the preparation of the bidding document should be removed by the Purchaser in the final version of the bidding document.]*

|  |  |  |
| --- | --- | --- |
| **ITB Reference** | **A. General** | |
| **ITB 1.1** | The reference number of the Invitation for Bids is: *[insert* ***reference number of the Invitation for Bids****]*  The Purchaser is: *[insert* ***name of the Purchaser****]*  The name of the IFB is: *[insert* ***name of the IFB****]*  The Purchaser ***[****specify:* ***shall / shall not]*** accept bid for multiple lots under this bidding document.  The lots are: ***[name and describe the lots (including references to the relevant parts of PART 2 – Purchaser’s Requirements),*** *otherwise state* ***“Not applicable”.]*** | |
| **ITB 1.3 (a)** | Electronic Procurement *[specify* ***shall / shall not****]* be applicable to this procurement.  The Purchaser shall use the following electronic-procurement system to manage this procurement process: ***[****insert* ***name of the e-system and url address or link,*** *otherwise state* ***“not applicable”.****]*  The electronic-procurement system shall be used to manage the following aspects of the Procurement process: ***[****insert* ***aspects e.g.* *issuing bidding document, submissions of Bids, opening of Bids,*** *otherwise state* ***“not applicable”.****]* | |
| **ITB 2.1** | The Beneficiary is: *[insert* ***name of the Beneficiary and statement of relationship with the Purchaser, if different from the Beneficiary.*** *This insertion should correspond to the information provided in the Invitation for Bids]*  Financing Agreement amount:*[insert* ***US$ equivalent****]*  The name of the Project is: *[insert*  ***name of the project]*** | |
| **ITB 4.1** | Maximum number of members in the JV shall be: *[insert*  ***number****]* | |
| ITB 4.5 | A list of debarred firms and individuals is available on IsDB’s external website: <http://www.isdb.org.> |
| **B. Bidding Document** | |
| **ITB 7.1** | For Clarification of Bid purposes only, the Purchaser’s address is:  *[****Note****: This address may be the same as or different from that specified under provision ITB 23.1 for Bid submission]*  Attention: *[insert* ***full name of person****, if applicable]*  Address: *[insert* ***street address and number****]*  Floor/ Room number*: [insert* ***floor and room number****, if applicable]*  City: *[insert* ***name of city or town****]*  Postal Code: *[insert* ***postal (ZIP) code****, if applicable]*  Country: *[insert* ***name of country****]*  Telephone: *[insert* ***telephone number, including country and city codes****]*  Facsimile number: *[insert* ***fax number, including country and city code****s, if applicable]*  Electronic mail address: *[insert* ***email address****, if applicable]*  Requests for clarification should be received by the Purchaser no later than: *[insert* ***number]*** *of**days**prior to the deadline for submission of Bids in accordance with ITB 23.* | | |
| **ITB 7.1** | Web page: *[if used, identify* ***the widely used website or electronic portal of free access where Bidding process information is published****]* | | |
| **ITB 7.4** | A Pre-Bid meeting *[specify* ***“shall”/“shall not”****]* take place at the following date, time and place:  Date: *[insert* ***Date****]*  Time:*[insert* ***Time****]*  Address: *[insert* ***street address and number****]*  Floor/ Room number*: [insert* ***floor and room number****, if applicable]*  City: *[insert* ***name of city or town****]*  Country: *[insert* ***name of country****]*  A site visit conducted by the Purchaser *[specify* ***“shall be” / “shall not be”****]*organized. | | |
| **C. Preparation of Bids** | | | |
| **ITB 10.1** | The language of the Bid is: *[insert language].*  All correspondence exchange shall be in ***[****insert****]*** language.  Language for translation of supporting documents and printed literature is ***[specify one language****].* | | |
| **ITB 11.1 (k)** | The Bidder shall submit with its Bid the following additional documents:  The additional documents shall include the following:  Code of Conduct for Supplier’s and subcontractor’s personnel (ES)  The Bidder shall submit its Code of Conduct that will apply to the Supplier’s and Subcontractors’ personnel employed in the execution of the Contract at the Project Site/s. The Bidder shall use for this purpose the Code of Conduct form provided in Section IV. No substantial modifications shall be made to this form, except that the Bidder may introduce additional requirements, including as necessary to take into account specific Contract issues/risks.  *[specify* ***any additional document not already listed in ITB 11.1 that must be submitted with the Bid****]* | | |
| **ITB 13.1** | *[specify* ***“Alternative Bids are not permitted”*** / ***“Alternative Bids are invited in accordance with ITB 13.1 and/or 13.2”*** **/** ***“Alternative Bids are permitted in accordance with ITB 13.4”***. | | |
| **ITB 13.2** | Alternatives to the Time Schedule *[ specify:*  ***are / are not*** *]* permitted.  If alternatives to the Time Schedule are permitted, the evaluation method will be as specified in Section III, Evaluation and Qualification Criteria. | | |
| **ITB 13.4** | Alternative technical solutions shall be permitted for the following parts of the Information System: *[if applicable, specify* ***subsystems****, otherwise state “****none****”]* as further detailed in the Section VII – Purchaser’s Requirements *[if applicable, specify* ***cross references*** *otherwise state “****not applicable”****]*. If alternative technical solutions are permitted, the evaluation method will be as specified in Section III, Evaluation and Qualification Criteria. | | |
| **ITB 15.2** | Prequalification *[insert* ***“has” / “has not”****]*been undertaken. | | |
| **ITB 16.2 (a)** | In addition to the topics described in ITB Clause 16.2 (a), the Preliminary Project Plan must address the following topics:   1. Project Organization and Management Sub-Plan, including management authorities, responsibilities, and contacts, as well as task, time and resource-bound schedules (in GANTT format); 2. Implementation Sub-Plan; 3. Training Sub-Plan; 4. Testing and Quality Assurance Sub-Plan; 5. Warranty Defect Repair and Technical Support Service Sub-Plan   *[****Note****: modify and extend the above example as appropriate for the Information System under this bidding document. Also link the Sub-Plans clearly to specific subsections of Section VII – Purchaser’s Requirements* *that specify the corresponding Services.]* | | |
| **ITB 16.3** | In the interest of effective integration, cost-effective technical support, and reduced re-training and staffing costs, Bidders shall offer the following items:  *[insert* ***brand name and models (or standards)****, including cross references to the relevant parts of Section VII – Purchaser’s Requirements.****]*** | | |
| **ITB 17.2** | The Bidder *[specify “****must****” / “****must not****”]* bid Recurrent Cost Items | | |
| **ITB 17.2** | The Bidder *[specify “****must****” / “****must not****”]* bid for contracts for Recurrent Cost Items not included in the main Contract. | | |
| **ITB 17.5** | The Incoterms edition is: *[insert* ***relevant edition****].* | | |
| **ITB 17.5 (a)** | Named place of destinationis:*[insert* ***named Place of destination as per Incoterm used****]* | | |
| **ITB 17.6** | Named place of final destination (or Project site) is: *[specify* ***location(s) where the Information System is to be Installed****].* | | |
| **ITB 17.8** | ITB 17.8 is modified as follows: *[specify* ***modifications /*** *otherwise state* ***“There are no modifications to ITB 17.8”]*** | | |
| **ITB 17.9** | The prices quoted by the Bidder *[insert* ***“shall” / “shall not”****]*be subject to adjustment during the performance of the Contract. | | |
| **ITB 18.1** | The Bidder *[specify* ***“is” / “is not”]*** required to quote in the currency of the Purchaser’s Country the portion of the Bid price that corresponds to expenditures incurred in that currency. | | |
| **ITB 19.1** | The Bid shall be valid until: *[insert* ***day, month and year****, taking into account reasonable time needed to complete the bid evaluation, obtain necessary approvals and the Bank’s No-objection (if subject to prior review).]* | | |
| **ITB 19.3 (a)** | The Bid price shall be adjusted by the following factor(s):  *[If applicable, insert* ***“The local currency portion of the Contract price shall be adjusted by a factor reflecting local inflation during the period of extension, and the foreign currency portion of the Contract price shall be adjusted by a factor reflecting the international inflation (in the country of the foreign currency) during the period of extension.”*** *otherwise insert* ***“not applicable****”].* | | |
| **ITB 20.1** | *[****Note****: If a Bid Security shall be required, a Bid-Securing Declaration shall not be required, and vice versa.]*  A *Bid Security [specify* ***“shall be” / “shall not be”****]* required.  A Bid-Securing Declaration *[specify* ***“shall be” / “shall not be”****]*required.  The amount and currency of the Bid Security shall be *[insert* ***amount and currency of the Bid Security,*** *otherwise insert* ***“Not Applicable”****.****]***  *[****Note****: In the case of lots, specify the amount and currency of the Bid Security for each lot. Also Bidders have the option of submitting one Bid Security for all lots (for the combined total amount of all lots) for which Bids have been submitted, however if the amount of Bid Security is less than the total required amount, the Purchaser will determine for which lot or lots the Bid Security amount shall be applied.]* | | |
| **ITB 20.10** | If the Bidder incurs any of the actions prescribed in subparagraphs (a) or (b) of this provision, the Purchaser will declare the Bidder ineligible to be awarded contracts by the Purchaser for a period of *[insert* ***number****]* years. | | |
| **ITB 21.1** | In addition to the original of the Bid, the number of copies is: *[insert* ***number****]* | | |
| **ITB 21.3** | The written confirmation of authorization to sign on behalf of the Bidder shall consist of: *[insert* ***the name and description of the documentation required to demonstrate the authority of the signatory to sign the Bid****]* | | |
| **D. Submission and Opening of Bids** | | | |
| **ITB 23.1** | For Bid submission purposes only, the Purchaser’s address is:  *[****Note****: This address may be the same as or different from that specified under provision ITB 7.1 for clarifications]*  Attention: *[insert* ***full name of person****, if applicable]*  Street Address: *[insert* ***street address and number****]*  Floor/Room number: *[insert* ***floor and room number****, if applicable]*  City: *[insert* ***name of city or town****]*  Postal Code: : *[insert* ***postal (ZIP) code****, if applicable]*  Country: *[insert* ***name of country****]*  The deadline for Bid submission is:  *[****Note****: The date and time should be the same as those provided in the Request for Bids, unless subsequently amended pursuant to ITB 23.2]*  Date: *[insert* ***day, month, and year, e.g. 15 June, 2020****]*  Time: *[insert* ***time, and identify if a.m. or p.m., e.g. 10:30 a.m.****]* | | |
| **ITB 23.1** | Bidders *[specify* ***“shall” / “shall not”****]*have the option of submitting their Bids electronically.  *[****Note****: The following provision should be included and the required corresponding information inserted only if Bidders have the option of submitting their Bids electronically. Otherwise omit.]*  The electronic Bidding submission procedures shall be: *[insert* ***a description of the electronic bidding submission procedures****, otherwise insert* ***“not applicable”.****]* | | |
| **ITB 26.1** | The Bid opening shall take place at:  Street Address: *[insert* ***street address and numbe****r]*  Floor/Room number: *[insert* ***floor and room number,*** *if applicable]*  City : *[insert* ***name of city or town****]*  Country: *[insert* ***name of country****]*  Date: [insert ***day, month, and year, e.g., 15 June, 2020]***  Time: *[insert* ***time, and identify if a.m. or p.m. e.g., 10:30 a.m.****]*  *[****Note****: Date and time should be the same as those given for the deadline for submission of Bids in ITB 23)]* | | |
| **ITB 26.6** | The Letter of Bid and Price Schedules shallbe initialed by *[insert* ***number****]* representatives of the Purchaser conducting Bid opening*.* Specifically *[Insert**procedure:* ***e.g., “each Bid shall be initialed by all representatives and shall be numbered, any modification to the unit or total price shall be initialed by the Representative of the Purchaser, etc.”****]* | | |
| **E. Evaluation, and Comparison of Bids** | | | |
| **ITB 33.1** | The currency(ies) of the Bid shall be converted into a single currency as follows: *[Insert* ***name of currency****]*  The currency that shall be used for Bid evaluation and comparison purposes to convert all Bid prices expressed in various currencies into a single currency is: *[Insert* ***name of currency****]*  The source of exchange rate shall be: *[specify* ***the source of exchange rate****s (e.g., the Central Bank in the Purchaser’s Country).]*  The date for the exchange rate shall be: *[insert* ***day, month and year, (****e.g. 15 June, 2020) not earlier than 28 days prior to the deadline for submission of the Bids, nor later than the date for the expiry of Bid validity specified in accordance with BDS 19.1]****.*** | | |
| **ITB 35.4** | The Purchaser’s evaluation of responsive Bids *[specify* ***“will take” / “will not take”****]* into account scored technical factors, in addition to cost factors*.*  The technical factors (sub-factors) andthe corresponding weight out of 100% are:   |  |  | | --- | --- | | Technical Factor *[insert technical factors and subfactors, as appropriate]* | Weight in percentage *[insert weight in %]* | |  |  | |  |  | |  |  |   ***[The weights should be allocated in terms of the relative significance of the technical factors.*** *Insert technical sub-factors and corresponding weights, as appropriate]*  The technical proposal scoring methodology is specified in Section III- Evaluation and Qualification Criteria. | | |
| **ITB 35.4** | Discount Rate (I) for net present value calculations of recurrent costs (if any) is *[insert* ***discount rate****]* percent per annum.  If rated criterion is used:  The weight to be given for cost, X is:  *[indicate weight for cost such that weight for cost plus weight for total technical score is 1(one).]* | | |
| **ITB 35.8** | Bids for Subsystems, lots, or slices of the overall Information System *[specify* **will / will *not****]* be accepted.  Discount that are conditional on the award of more than one Subsystem, lot, or slice may be offered in Bids and such discounts *[specify* ***“shall” / “shall not”****]* be considered in the price evaluation.  *[****Note****: Keeping a single Bid package obviously simplifies the evaluation and maintains clearer overall system implementation and warranty responsibilities. However, there may well be practical reasons to break a specific procurement package into parts that can be bid individually. If, therefore, Bids will be accepted for one or more individual Subsystems, lots, or slices of the total Information System, include here the title of each Subsystem, lot, or slice for which bids can be submitted, as well as proper cross references to the Technical Requirements where a description of each Subsystem, lot, or slice can be found. Any other criterion that may affect award of more than one Subsystem, lot, or slice should also be specified here.]*  *[****Note****: When rated criteria are used for evaluation insert “shall not” as the evaluation becomes overly complex].* | | |
| **ITB 39.3** | ***[Insert the following when the Purchaser will conduct testing as part of the post qualification verification of the Bidder, to verify that the performance or functionality of the proposed Information System meets the Technical Requirements]***  As additional qualification measures, the Information System (or components/parts of it) offered by the Bidder with the Bid offering the most Value for Money may be subjected to the following tests and performance benchmarks prior to Contract award*: [specify:* ***measures that will be used in the evaluation of Bids****, such as demonstration tests, performance benchmarks, documentation reviews, reference site visits, etc., and who will carry them out and how they will be conducted; otherwise state* ***“none”****]*.  *[****Note****: For demonstration or benchmark tests, specify full testing details and success criteria (alternatively, reference detailed discussion of testing in the Technical Requirements).]* | | |
| F. Award of Contract | | | |
| **ITB 43** | The award will be made on the basis of *[specify* ***“rated” / “not rated” criteria****]* pursuant to ITB 35.7, if applicable, in accordance with Section III, Evaluation and Qualification Criteria. | | |
| **ITB 44** | The maximum percentage by which quantities may be increased is: *[inser****t percentage****]*  The maximum percentage by which quantities may be decreased is: *[inser****t percentage****]*  The items for which the Purchaser may increase of decrease the quantities are the following.  *[Specify* ***items for which the quantities may be increased or decreased****]*  *[****Note****: The percentage of increase or decrease for hardware, software and similar components should normally not exceed 15 to 20 percent for each item and in the aggregate. If the System contains a number of virtually identical Subsystems, a specific percentage should be given, allowing a reasonable increase or decrease in the number of Subsystems to be contracted for at the time of Contract award.]* | | |
| **ITB 49** | The proposed Adjudicator is: *[*insert: ***name and other identifying information “as per the résumé attached to this BDS***”, or, exceptionally, state ***“There will be no Adjudicator under this Contract***.*”]*  *[****Note****: For the adjudication system to achieve its purpose (the quick and effective resolution of potential disputes), the Adjudicator should be a technical expert in the type of System covered by the Contract, with actual experience in Information System contract implementation. He/she should ideally, though not necessarily, come from a country other than that of the Purchaser, to avoid any appearance of a conflict of interest. However, it is preferable to propose an Adjudicator from the Purchaser’s Country than to consider no adjudication.*  *Normally, there should be an Adjudicator in the contract. The option of having no Adjudicator should be viewed as an exception, to be used only in relatively straightforward and short - about less than a year - contracts with little or no application software development or adaptation.* *]*  The proposed hourly fee is *[insert:* ***amount and currency****]*.  *[Note: In addition to a fee for actual hours spent studying a case submitted for advice, an Adjudicator would expect to be reimbursed for all dispute-related telephone, fax, and other communications costs, as well as all costs associated with any trips to the site(s), if any****.]*** | | |
| **ITB 50.1** | The procedures for making a Procurement-related Complaint are detailed in the “[Guidelines for Procurement of Goods, Works and related services under IsDB Project Financing](http://www.worldbank.org/en/projects-operations/products-and-services/brief/procurement-new-framework) (Annex C).”  If a Bidder wishes to make a Procurement-related Complaint, the Bidder should submit its complaint following these procedures, in writing (by the quickest means available, that is either by email or fax), to:  For the attention: *[insert* ***full name of person receiving complaints****]*  Title/position: *[insert* ***title/position****]*  Purchaser: *[insert* ***name of Purchaser****]*  Email address*: [insert* ***email address****]*  Fax number: *[insert* ***fax number****, otherwise state “****Not applicable****” if not used]*  In summary, a Procurement-related Complaint may challenge any of the following:   1. the terms of this Bidding Document; 2. the Purchaser’s decision to exclude a Bidder from the procurement process prior to the award of contract; and 3. the Purchaser’s decision to award the contract. | | |

**Résumé of the proposed Adjudicator.**

***[insert résumé]***

|  |
| --- |
| Section III - Evaluation and Qualification Criteria (After Prequalification) |

This Section contains the criteria that the Purchaser shall use to evaluate Bids and qualify Bidders. The Bidder shall provide all the information requested in the forms included in Section IV, Bidding Forms.

|  |
| --- |
| In addition to the criteria listed in ITB 35.3 (a) to (e), the following factors shall apply:   1. Technical Evaluation **(ITB 35.3 and ITB 35.4)**   If, in addition to the cost factors, the Purchaser has chosen to give weight to important technical factors (i.e., the price weight, X, is less than 1 in the evaluation), the total technical points assigned to each Bid in the Evaluated Bid Formula will be determined by adding and weighting the scores assigned by an evaluation committee to technical features of the Bid in accordance with the BDS and the scoring methodology below:  **Technical proposal scoring methodology**  (a) During the evaluation process, the evaluation committee will assign each desirable/preferred feature a whole number score from 0 to 4, where 0 means that the feature is absent, and 1 to 4 either represent predefined values for desirable features amenable to an objective way of rating (as is the case for, e.g., extra memory, or extra mass storage capacity, etc., if these extras would be conducive for the utility of the system), or if the feature represents a desirable functionality (e.g., of a software package) or a quality improving the prospects for a successful implementation (such as the strengths of the proposed project staff, the methodology, the elaboration of the project plan, etc., in the bid), the scoring will be 1 for the feature being present but showing deficiencies; 2 for meeting the requirements; 3 for marginally exceeding the requirements; and 4 for significantly exceeding the requirements.  (b) The score for each feature (i) within a category (j) will be combined with the scores of features in the same category as a weighted sum to form the Category Technical Score using the following formula:    where:  *tji* = the technical score for feature “i” in category “j”  *wji* = the weight of feature “i” in category “j”  *k* = the number of scored features in category “j”  and  (c) The Category Technical Scores will be combined in a weighted sum to form the total Technical Bid Score using the following formula:    where:  *Sj* = the Category Technical Score of category “j”  *Wj* = the weight of category “j” as specified in the BDS  *n* = the number of categories  and |

1. Economic Evaluation

The following factors and methods will apply:

**(a)** **Time Schedule**:

The number of weeks, from the effective date specified in Article 3 of the Contract Agreement, to achieve Operational Acceptance must be no more than: ***[****insert**the* ***number weeks,*** *consistent with the Implementation Schedule****]***.

A Bid offering to achieve Operational Acceptance earlier than the maximum number of weeks *[ specify:* ***shall not*** */* ***shall*** *]* be given credit for bid evaluation purposes.

If an adjustment for a proposed accelerated time schedule is specified above it shall be made accordingly: For evaluation purposes a *[ specify:* ***number*** *]* percent reduction in the *[ specify:* ***overall*** */* ***pro rata*** *]*. Bid Price shall be made for each week the proposed achievement of the Operational Acceptance is advanced relative to the Implementation Schedule in the Purchaser’s Requirements up to a limit of *[ specify:* ***number*** *]* weeks of acceleration.

If awarded the Contract, the Bidder’s accelerated Implementation Schedule would be formally incorporated into the Contract and this schedule shall govern the application of the contract clauses pertaining to Performance Security, liquidated damages as well as other relevant contract clauses.

**(b) Recurrent Costs**

Since the operation and maintenance of the system being procured form a major part of the implementation, the resulting recurrent costs will be evaluated according to the principles given hereafter, including the cost of recurrent cost items for the initial period of operation stated below, based on prices furnished by each Bidder in Price Schedule Nos. 3.3 and 3.5.

Recurrent cost items for post- warranty service period if subject to evaluation shall be included in the main contract or a separate contract signed together with the main contract.

Such costs shall be added to the Bid price for evaluation.

Option 1: The recurrent cost factors for calculation of the implementation schedule are:

(i) number of years for implementation

(ii) hardware maintenance

(iii) software licenses and updates

(iv) technical services

(v) telecommunication services, and

(vi) other services (if any).

The Recurrent Costs (R) are reduced to net present value and determined using the following formula:



where

*N* = number of years of evaluated recurrent costs

*x* = an index number 1, 2, 3, ... N.

*Rx* = total Recurrent Costs for year “*x*,” as recorded in the Recurrent Cost Sub-Table.

*I* = discount rate to be used for the Net Present Value calculation, as specified **in the BDS for ITB 35.4.**

**or** Option 2:

*[ specify* ***alternative recurrent cost evaluation scheme*** *or state* ***“none”*** *]*

**(c) Specific additional criteria**

The relevant evaluation method, if any, shall be as follows:

*[specify* ***evaluation method****, otherwise state “****Not Applicable****”]*

1. Technical alternatives

If invited in accordance with ITB 13.4, will be evaluated as follows:*[specify* ***additional criteria*** *or state* ***“none”****]*

1. Combined Evaluation

The Purchaser will evaluate and compare the Bids that have been determined to be substantially responsive, pursuant to ITB 30.

If indicated by the BDS, the Purchaser’s evaluation of responsive Bids will take into account technical factors, in addition to cost factors.

In such a case, an Evaluated Bid Score (B) will be calculated for each responsive Bid using the following formula (for comparison in percentages), which permits a comprehensive assessment of the Bid price and the technical merits of each Bid:

|  |
| --- |
| where  *C* = Evaluated Bid Price  *C low* = the lowest of all Evaluated Bid Prices among responsive Bids  *T* = the total Technical Score awarded to the Bid  *Thigh* = the Technical Score achieved by the Bid that was scored best among all responsive Bids  *X* = weight for the Cost as specified in the BDS  The Bid with the best evaluated Bid Score (B) among responsive Bids shall be the Bid offering the most Value for Money provided the Bidder was prequalified and/or it was found to be qualified to perform the Contract in accordance with ITB 39. |

1. Qualification

**5.1 Update of Information**

The Bidder and any subcontractors shall meet or continue to meet the criteria used at the time of prequalification.

**5.2 Financial Resources**

Using the relevant Form, No FIN 2.3.3 in Section IV, Bidding Forms, the Bidder must demonstrate access to, or availability of, financial resources such as liquid assets, unencumbered real assets, lines of credit, and other financial means, other than any contractual advance payments to meet:

(i) the following cash-flow requirement:

and

(ii) the overall cash flow requirements for this contract and its current supply and services’ commitment.

**5.3 Key Personnel**

The Bidder must demonstrate that it will have suitably qualified key personnel. The Bidder shall complete the relevant Forms in Section IV, Bidding Forms.

**5.4** **Subcontractors/vendors/manufacturers**

Subcontractors/vendors/manufacturers for major items of supply or services identified in the prequalification document must meet or continue to meet the minimum criteria specified therein for each item.

Subcontractors for the following additional major items of supply or services must meet the following minimum criteria, herein listed for that item:

|  |  |  |
| --- | --- | --- |
| Item No. | Description of Item | Minimum Criteria to be met |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| … |  |  |

Failure to comply with this requirement will result in the rejection of the subcontractor.

**5.5 Manufacturer’s authorization**

For all powered (active) hardware and/or software components of the Information System which the Bidder does not itself produce, by submission of documentary evidence in its Bid, the Bidder must establish to the Purchaser’s satisfaction that it is not prohibited to supply those components in the Purchaser’s country under the Contract(s) that may result from this procurement.

(i) In the case of powered (active) hardware and other powered equipment, this must be documented by including Manufacturer’s Authorizations in the Bid (based on the sample found in the Sample Bid Forms in Section IV.);

(ii) In the case of proprietary commercial software (i.e., excluding open source or “freeware” software) that the Bidder does not manufacture itself and for which the Bidder has or will establish an Original Equipment Manufacturer (OEM) relationship with the manufacture, the Bidder must provide Manufacture’s Authorizations;

(iii) In the case of proprietary commercial software (i.e., excluding open source or “freeware” software) that the Bidder does not manufacture itself and for which the Bidder does not or will not establish an OEM relationship with the manufacturer, the Bidder must document to the Purchaser’s satisfaction that the Bidder is not excluded from sourcing these items from the manufacturer’s distribution channels and proposing offering these items for supply in the Beneficiary’s Country.

(iv) In the case of open source software, the Bidder must identify the software item as open source and provide copies of the relevant open source license(s).

The Bidder is responsible for ensuring that the manufacturer or producer complies with the requirements of ITB 4 and ITB 5 and meets the minimum criteria listed above for that item.

**5.6 Local Representative**

In the case of a Bidder not doing business within the Purchaser’s country, the Bidder shall submit documentary evidence in its Bid to establish to the Purchaser’s satisfaction that it is or will be (if awarded the Contract) represented by an agent in that country who is equipped and able to carry out / manage the Bidder’s maintenance, technical support, training, and warranty repair obligations specified in the Purchaser’s Requirements (including any response time, problem-resolution norms or other aspects that may be specified in the Contract).

|  |
| --- |
| Section III - Evaluation and Qualification Criteria (Without Prequalification) |

This Section contains all the criteria that the Purchaser shall use to evaluate Bids and qualify Bidders. No other factors, methods or criteria shall be used. The Bidder shall provide all the information requested in the forms included in Section IV, Bidding Forms.

In addition to the criteria listed in ITB 35.3 (a) to (e), the following factors shall apply:

1. Technical Evaluation **(ITB 35.3 and ITB 35.4)**

If, in addition to the cost factors, the Purchaser has chosen to give weight to important technical factors (i.e., the price weight, X, is less than 1 in the evaluation), the total technical points assigned to each Bid in the Evaluated Bid Formula will be determined by adding and weighting the scores assigned by an evaluation committee to technical features of the Bid in accordance with the BDS and the scoring methodology below:

**Technical proposal scoring methodology**

(a) During the evaluation process, the evaluation committee will assign each desirable/preferred feature a whole number score from 0 to 4, where 0 means that the feature is absent, and 1 to 4 either represent predefined values for desirable features amenable to an objective way of rating (as is the case for, e.g., extra memory, or extra mass storage capacity, etc., if these extras would be conducive for the utility of the system), or if the feature represents a desirable functionality (e.g., of a software package) or a quality improving the prospects for a successful implementation (such as the strengths of the proposed project staff, the methodology, the elaboration of the project plan, etc., in the bid), the scoring will be 1 for the feature being present but showing deficiencies; 2 for meeting the requirements; 3 for marginally exceeding the requirements; and 4 for significantly exceeding the requirements.

(b) The score for each feature (i) within a category (j) will be combined with the scores of features in the same category as a weighted sum to form the Category Technical Score using the following formula:



where:

*tji* = the technical score for feature “i” in category “j”

*wji* = the weight of feature “i” in category “j”

*k* = the number of scored features in category “j”

and 

(c) The Category Technical Scores will be combined in a weighted sum to form the total Technical Bid Score using the following formula:



where:

*Sj* = the Category Technical Score of category “j”

*Wj* = the weight of category “j” as specified in the BDS

*n* = the number of categories

and 

1. Economic Evaluation

The following factors and methods will apply:

**(a)** **Time Schedule**:

The number of weeks, from the effective date specified in Article 3 of the Contract Agreement, to achieve Operational Acceptance must be no more than: ***[****insert**the* ***number weeks,*** *consistent with the Implementation Schedule****]***.

A Bid offering to achieve Operational Acceptance earlier than the maximum number of weeks *[ specify:* ***shall not*** */* ***shall*** *]* be given credit for bid evaluation purposes.

If an adjustment for a proposed accelerated time schedule is specified above it shall be made accordingly: For evaluation purposes a *[ specify:* ***number*** *]* percent reduction in the *[ specify:* ***overall*** */* ***pro rata*** *]* Bid Price shall be made for each week the proposed achievement of the Operational Acceptance is advanced relative to the Implementation Schedule in the Purchaser’s Requirements up to a limit of *[ specify:* ***number*** *]* weeks of acceleration.

If awarded the Contract, the Bidder’s accelerated Implementation Schedule would be formally incorporated into the Contract and this schedule shall govern the application of the contract clauses pertaining to Performance Security, liquidated damages as well as other relevant contract clauses.

**(b) Recurrent Costs**

Since the operation and maintenance of the system being procured form a major part of the implementation, the resulting recurrent costs will be evaluated according to the principles given hereafter, including the cost of recurrent cost items for the initial period of operation stated below, based on prices furnished by each Bidder in Price Schedule Nos. 3.3 and 3.5.

Recurrent cost items for post- warranty service period if subject to evaluation shall be included in the main contract or a separate contract signed together with the main contract.

Such costs shall be added to the Bid price for evaluation.

Option 1: The recurrent cost factors for calculation of the implementation schedule are:

(i) number of years for implementation

(ii) hardware maintenance

(iii) software licenses and updates

(iv) technical services

(v) telecommunication services, and

(vi) other services (if any).

The Recurrent Costs (R) are reduced to net present value and determined using the following formula:



where

*N* = number of years of evaluated recurrent costs

*x* = an index number 1, 2, 3, ... N.

*Rx* = total Recurrent Costs for year “*x*,” as recorded in the Recurrent Cost Sub-Table.

*I* = discount rate to be used for the Net Present Value calculation, as specified **in the BDS for ITB 35.4.**

**or** Option 2:

*[ specify* ***alternative recurrent cost evaluation scheme*** *or state* ***“none”*** *]*

**(c) Specific additional criteria**

The relevant evaluation method, if any, shall be as follows:

*[specify* ***evaluation method****, otherwise state “****Not Applicable****”]*

1. Technical alternatives

If invited in accordance with ITB 13.4, will be evaluated as follows:*[specify* ***additional criteria*** *or state* ***“none”****]*

1. Combined Evaluation

The Purchaser will evaluate and compare the Bids that have been determined to be substantially responsive, pursuant to ITB 30.

If indicated by the BDS, the Purchaser’s evaluation of responsive Bids will take into account technical factors, in addition to cost factors.

In such a case, an Evaluated Bid Score (B) will be calculated for each responsive Bid using the following formula, which permits a comprehensive assessment of the Bid price and the technical merits of each Bid:

|  |
| --- |
| where  *C* = Evaluated Bid Price  *C low* = the lowest of all Evaluated Bid Prices among responsive Bids  *T* = the total Technical Score awarded to the Bid  *Thigh* = the Technical Score achieved by the Bid that was scored best among all responsive Bids  *X* = weight for the Price as specified in the BDS  The Bid with the best evaluated Bid Score (B) among responsive Bids shall be the Bid offering the most Value for Money provided the Bidder was prequalified and/or it was found to be qualified to perform the Contract in accordance with ITB 39. |

1. **Qualification**

| **Factor** | 5.1 Eligibility | | | | | |
| --- | --- | --- | --- | --- | --- | --- |
| Sub-Factor | Criteria | | | | | Documentation Required |
| Requirement | Bidder | | | |
| **Single Entity** | Joint Venture (existing or intended) | | |
| **All members combined** | Each member | **At least one member** |
| 5.1.1 Nationality | Nationality in accordance with ITB 4.4. | Must meet requirement | Must meet requirement | (see below) | Must meet requirement (see below) | Form ELI –5.1.1 and 5.1.2, with attachments |
|  |  |  | The Guidelines stipulate:  Paragraph 1.24 In the case of ICB/MC, association of non-MC Firms with MC Firms may be accepted. However, the lead MC Firm is expected to perform at least fifty (50) per cent of the contract.  Paragraph 1.25 In the case of National Competitive Bidding (NCB), association of domestic Firms with non-domestic Firms is accepted, with the domestic Firm expected to perform at least fifty (50) per cent of the contract. | | |  |
| 5.1.2 Conflict of Interest | No- conflicts of interests as described in ITB 4.2. | Must meet requirement | Must meet requirement | Must meet requirement | N / A | Letter of Bid |
| 5.1.3 Bank Ineligibility | Not having been declared ineligible by the Bank as described in ITB 4.5. | Must meet requirement | Must meet requirement | Must meet requirement | N / A | Letter of Bid |
| 5.1.4 Government owned Entity of the Beneficiary country | Compliance with conditions of ITB 4.6 | Must meet requirement | Must meet requirement | Must meet requirement | N / A | Form ELI –5.1.1 and 5.1.2, with attachments |
| 5.1.4 Ineligibility based on Beneficiary’s country law or Boycott Regulations of the Organization of the Islamic Cooperation, the League of Arab States and the African Union. (Para 1. 11 and 1. 12 of Guidelines for Procurement of Goods, Works and related services Under the Islamic Development Bank Financing, September 2018) | Not having been excluded as a result of the Beneficiary’s country laws or official regulations, or by the Boycott Regulations of the Organization of the Islamic Cooperation, the League of Arab States and the African Union, in accordance with ITB 4.8 and Section V. | Must meet requirement | Existing JV Must meet requirement | Must meet requirement | N / A | Letter of Bid |

| **Factor** | 5.2 Historical Contract Non-Performance | | | | | |
| --- | --- | --- | --- | --- | --- | --- |
| Sub-Factor | Criteria | | | | | **Documentation Required** |
| Requirement | Bidder | | | |
| **Single Entity** | Joint Venture (existing or intended) | | |
| **All members combined** | **Each member** | **At least one member** |

## 

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| History of non-performing contracts | Non-performance of a contract[[17]](#footnote-18) did not occur as a result of Bidder’s default since 1st January *[insert year]*. | Must meet requirement by itself or as member to past or existing JV | N / A | Must meet requirement[[18]](#footnote-19) | N / A | Form CON - 2 |
| Suspension | Not under suspension based on execution of a Bid Securing Declaration pursuant to ITB 4.7 and ITB 20.10 | Must meet requirement | N / A | Must meet requirement | N / A | Letter of Bid |
| Pending Litigation | Bidder’s financial position and prospective long term profitability still sound according to criteria established in 2.3.1 below and assuming that all pending litigation will be resolved against the Bidder. | Must meet requirement by itself or as member to past or existing JV | N / A | Must meet requirement | N / A | Form CON – 2 |
| Litigation History | No consistent history of court/arbitral award decisions against the Bidder[[19]](#footnote-20)since 1st January *[insert year]* | Must meet requirement | Must meet requirement | Must meet requirement | N/A | Form CON – 2 |

| **Factor** | 5.3 Financial Situation | | | | | |
| --- | --- | --- | --- | --- | --- | --- |
| **Sub-Factor** | Criteria | | | | | Documentation Required |
| Requirement | Bidder | | | |
| **Single Entity** | Joint Venture (existing or intended) | | |
| **All members combined** | **Each member** | **At least one member** |
| 5.3.1 Historical Financial Performance | Submission of audited balance sheets or if not required by the law of the Bidder’s country, other financial statements acceptable to the Purchaser, for the last \_\_\_\_ [ ] years to demonstrate the current soundness of the Bidders financial position and its prospective long term profitability. | Must meet requirement | N / A | Must meet requirement | N / A | Form FIN – 5.3.1 with attachments |
| 5.3.2 Average Annual Turnover | Minimum average annual turnover of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, calculated as total certified payments received for contracts in progress or completed, within the last\_\_\_\_\_\_( ) years | Must meet requirement | Must meet requirement | N/A | N/A | Form FIN –5.3.2 |
| 5.3.3 Financial Resources | The Bidder must demonstrate access to, or availability of, financial resources such as liquid assets, unencumbered real assets, lines of credit, and other financial means, other than any contractual advance payments to meet the following cash-flow requirement: | Must meet requirement | Must meet requirement | N/A | N/A | Form FIN –5.3.3 |

| **Factor** | 5.4 Experience | | | | | |
| --- | --- | --- | --- | --- | --- | --- |
| **Sub-Factor** | Criteria | | | | | Documentation Required |
| **Requirement** | Bidder | | | |
| Single Entity | **Joint Venture (existing or intended)** | | |
| **All members combined** | **Each member** | **At least one member** |
| 5.4.1 General Experience | Experience under Information System contracts in the role of prime supplier, management contractor, JV member, or subcontractor for at least the last\_\_\_\_\_\_\_\_ [\_\_\_\_] years prior to the applications submission deadline. | Must meet requirement | N / A | Must meet requirement | N / A | Form EXP-5.4.1 |
| 5.4.2 Specific Experience | Participation as a prime supplier, management contractor, JV[[20]](#footnote-21) member, sub-contractor, in at least \_\_\_\_\_\_\_\_\_ (\_\_\_) contracts within the last \_\_\_\_\_\_\_\_ ( ) years, each with a value of at least \_\_\_\_\_\_\_\_\_\_\_\_ (\_\_\_), that have been successfully and substantially completed and that are similar to the proposed Information System. *[Specify minimum key requirements in terms of physical size, complexity, methods, technology and/or other characteristics from those described in Section VII, Purchaser’s Requirements*  The successfully completed similar contracts shall be documented by a copy of an Operational acceptance certificate (or equivalent documentation satisfactory to the Purchaser) issued by the purchaser(s). | Must meet requirement | Must meet requirements | N / A | Must meet the following requirement *[specify any key requirement to be met by one member]* | Form EXP 5.4.2 |

**5.5 Key Personnel**

The Bidder must demonstrate that it will have suitably qualified key personnel. The Bidder shall complete the relevant Forms in Section IV, Bidding Forms.

**5.6** **Subcontractors/vendors/manufacturers**

Subcontractors/vendors/manufacturers for major items of supply or services identified in the prequalification document must meet or continue to meet the minimum criteria specified therein for each item.

Subcontractors for the following additional major items of supply or services must meet the following minimum criteria, herein listed for that item:

|  |  |  |
| --- | --- | --- |
| Item No. | Description of Item | Minimum Criteria to be met |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| … |  |  |

Failure to comply with this requirement will result in the rejection of the subcontractor.

**5.7 Manufacturer’s authorization**

For all powered (active) hardware and/or software components of the Information System which the Bidder does not itself produce, by submission of documentary evidence in its Bid, the Bidder must establish to the Purchaser’s satisfaction that it is not prohibited to supply those components in the Purchaser’s country under the Contract(s) that may result from this procurement.

(i) In the case of powered (active) hardware and other powered equipment, this must be documented by including Manufacturer’s Authorizations in the Bid (based on the form in Section IV);

(ii) In the case of proprietary commercial software (i.e., excluding open source or “freeware” software) that the Bidder does not manufacture itself and for which the Bidder has or will establish an Original Equipment Manufacturer (OEM) relationship with the manufacture, the Bidder must provide Manufacture’s Authorizations;

(iii) In the case of proprietary commercial software (i.e., excluding open source or “freeware” software) that the Bidder does not manufacture itself and for which the Bidder does not or will not establish an OEM relationship with the manufacture, the Bidder must document to the Purchaser’s satisfaction that the Bidder is not excluded from sourcing these items from the manufacturer’s distribution channels and offering these items for supply in the Beneficiary’s Country.

(iv) In the case of open source software, the Bidder must identify the software item as open source and provide copies of the relevant open source license(s).

The Bidder is responsible for ensuring that the manufacturer or producer complies with the requirements of ITB 4 and ITB 5 and meets the minimum criteria listed above for that item.

**5.8 Local Representation**

In the case of a Bidder not doing business within the Purchaser’s country, the Bidder shall submit documentary evidence in its Bid to establish to the Purchaser’s satisfaction that it is or will be (if awarded the Contract) represented by an agent in that country who is equipped and able to carry out / manage the Bidder’s maintenance, technical support, training, and warranty repair obligations specified in the Purchaser’s Requirements (including any response time, problem-resolution norms or other aspects that may be specified in the Contract).

|  |
| --- |
| Section IV - Bidding Forms |

Table of Forms

[Letter of Bid 73](#_Toc43484951)

[Price Schedule Forms 76](#_Toc43484952)

[Form ELI 5.1.1- Bidder Information Form 84](#_Toc43484953)

[Form ELI 5.1.2- Bidder’s JV Members Information Form 86](#_Toc43484954)

[Form CON – 2- Historical Contract Non-Performance, Pending Litigation and Litigation History 88](#_Toc43484955)

[Form EXP 5.4.1- General Experience 90](#_Toc43484956)

[Form EXP – 5.4.2- Specific Experience 91](#_Toc43484957)

[Form EXP – 5.4.2 (cont.)- Specific Experience (cont.) 92](#_Toc43484958)

[Form CCC- Summary Sheet: Current Contract Commitments / Work in Progress 93](#_Toc43484959)

[Form FIN – 5.3.1- Financial Situation: Historical Financial Performance 94](#_Toc43484960)

[Form FIN – 5.3.2- Average Annual Turnover 96](#_Toc43484961)

[Form FIN 5.3.3- Financial Resources 97](#_Toc43484962)

[Personnel Capabilities- Key Personnel 98](#_Toc43484963)

[Code of Conduct for Supplier’s and Subcontractors’ Personnel Form 101](#_Toc43484964)

[Technical Capabilities 104](#_Toc43484965)

[Manufacturer’s Authorization 105](#_Toc43484966)

[Subcontractor’s Agreement 106](#_Toc43484967)

[Intellectual Property Forms 108](#_Toc43484968)

[Conformance of Information System Materials 111](#_Toc43484969)

[Form of Bid Security (Bank Guarantee) 115](#_Toc43484970)

[Form of Bid Security (Bid Bond) 117](#_Toc43484971)

[Form of Bid-Securing Declaration 119](#_Toc43484972)

Letter of Bid

|  |
| --- |
| *INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE DOCUMENT*  *The Bidder must prepare this Letter of Bid on stationery with its letterhead clearly showing the Bidder’s complete name and business address.*  *Note: All italicized text is to help Bidders in preparing this form.* |

Date of this Bid submission: *[insert* ***date (as day, month and year) of Bid submission****]*

IFB No.: *[insert* ***number of IFB process****]*

Alternative No.: *[insert* ***identification No if this is a Bid for an alternative,*** *otherwise state* ***“not applicable”****]*

We, the undersigned, declare that:

To: *[insert* ***complete name of Purchaser****]*

1. **No reservations:** We have examined and have no reservations to the bidding document, including Addenda issued in accordance with Instructions to Bidders (ITB 8);
2. **Eligibility**: We meet the eligibility requirements and have no conflict of interest in accordance with ITB 4;
3. **Bid-Securing Declaration:** We have not been suspended nor declared ineligible by the Purchaser based on execution of a Bid-Securing Declaration in the Purchaser’s Country in accordance with ITB 4.7;
4. **Conformity:** We offer to provide design, supply and installation services in conformity with the bidding document of the following: [*insert a brief description of the IS Design, Supply and Installation Services*];
5. **Bid Price:** The total price of our Bid, excluding any discounts offered in item (f) below is: *[Insert one of the options below as appropriate]*

*[Option 1, in case of one lot:]* Total price is: *[insert* ***the total price of the Bid in words and figures, indicating the various amounts and the respective currencies****]*;

Or

*[Option 2, in case of multiple lots:]* (a) Total price of each lot *[insert* ***the total price of each lot in words and figures, indicating the various amounts and the respective currencies****]*; and (b) Total price of all lots (sum of all lots) *[insert* ***the total price of all lots in words and figures, indicating the various amounts and the respective currencies****]*;

1. **Discounts:** The discounts offered and the methodology for their application are:

(i) The discounts offered are: [*Specify* ***in detail each discount offered****.*]

(ii) The exact method of calculations to determine the net price after application of discounts is shown below: [*Specify* ***in detail the method that shall be used to apply the discounts***];

1. **Bid Validity:** Our Bid shall be valid until *[insert day, month and year in accordance with ITB 19.1],* and it shall remain binding upon us and may be accepted at any time before the expiration of that period;
2. **Performance Security:** If our Bid is accepted, we commit to obtain a Performance Security in accordance with the bidding document;
3. **One Bid Per Bidder:** We are not submitting any other Bid(s) as an individual Bidder, and we are not participating in any other Bid(s) as a Joint Venture member, and meet the requirements of ITB 4.3, other than alternative Bids submitted in accordance with ITB 13;
4. **Suspension and Debarment**: We, along with any of our subcontractors, suppliers, consultants, manufacturers, or service providers for any part of the contract, are not subject to, and not controlled by any entity or individual that have not been declared ineligible by IsDB,under the Purchaser’s country laws or official regulations or by an act of compliance with a decision of the Organization of the Islamic Cooperation, the League of Arab States and the African Union;
5. **Government-owned enterprise or institution**: [*select the appropriate option and delete the other*: ***We are not a government-owned enterprise or institution*** / ***We are a government-owned enterprise or institution but meet the requirements of ITB 4.6***];
6. **Commissions, gratuities and fees**: We have paid, or will pay the following commissions, gratuities, or fees with respect to the Bidding process or execution of the Contract: *[insert* ***complete name of each Recipient, its full address, the reason for which each commission or gratuity was paid and the amount and currency of each such commission or gratuity****]*

|  |  |  |  |
| --- | --- | --- | --- |
| Name of Recipient | Address | Reason | Amount |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

*[If none has been paid or is to be paid, indicate “****none****.”]*

1. **Binding Contract**: We understand that this Bid, together with your written acceptance thereof included in your Letter of Acceptance, shall constitute a binding contract between us, until a formal contract is prepared and executed;
2. **Not Bound to Accept:** We understand that you are not bound to accept the lowest evaluated cost Bid, the Bid offering the most Value for Money or any other Bid that you may receive; and
3. **Fraud and Corruption:** We hereby certify that we have taken steps to ensure that no person acting for us or on our behalf engages in any type of Fraud and Corruption.

Name of the Bidder: \**[insert* ***complete name of the Bidder****]*

Name of the person duly authorized to sign the Bid on behalf of the Bidder: \*\**[insert* ***complete name of person duly authorized to sign the Bid****]*

Title of the person signing the Bid: *[insert* ***complete title of the person signing the Bid****]*

Signature of the person named above: *[insert* ***signature of person whose name and capacity are shown above****]*

Date signed *[insert* ***number****]* day of *[insert* ***month****]*, *[insert* ***year****]*

**\***: In the case of the Bid submitted by joint venture specify the name of the Joint Venture as Bidder

\*\*: Person signing the Bid shall have the power of attorney given by the Bidder to be attached with the Bid

Price Schedule Forms

## Notes to Bidders on working with the Price Schedules

**General**

1. The Price Schedules are divided into separate Schedules as follows:

3.1 Grand Summary Cost Table

3.2 Supply and Installation Cost Summary Table

3.3 Recurrent Cost Summary Table

3.4 Supply and Installation Cost Sub-Table(s)

3.5 Recurrent Cost Sub-Tables(s)

3.6 Country of Origin Code Table

*[insert:* ***any other Schedules as appropriate*** *]*

2. The Schedules do not generally give a full description of the information technologies to be supplied, installed, and operationally accepted, or the Services to be performed under each item. However, it is assumed that Bidders shall have read the Technical Requirements and other sections of these bidding documents to ascertain the full scope of the requirements associated with each item prior to filling in the rates and prices. The quoted rates and prices shall be deemed to cover the full scope of these Technical Requirements, as well as overhead and profit.

3. If Bidders are unclear or uncertain as to the scope of any item, they shall seek clarification in accordance with the Instructions to Bidders in the bidding documents prior to submitting their bid.

**Pricing**

4. Prices shall be filled in indelible ink, and any alterations necessary due to errors, etc., shall be initialed by the Bidder. As specified in the Bid Data Sheet, prices shall be fixed and firm for the duration of the Contract.

5. Bid prices shall be quoted in the manner indicated and in the currencies specified in ITB 18.1 and ITB 18.2. Prices must correspond to items of the scope and quality defined in the Technical Requirements or elsewhere in these bidding documents.

6. The Bidder must exercise great care in preparing its calculations, since there is no opportunity to correct errors once the deadline for submission of bids has passed. A single error in specifying a unit price can therefore change a Bidder’s overall total bid price substantially, make the bid noncompetitive, or subject the Bidder to possible loss. The Purchaser will correct any arithmetic error in accordance with the provisions of ITB 32.

7. Payments will be made to the Supplier in the currency or currencies indicated under each respective item. As specified in ITB 18.2, no more than three foreign currencies may be used.

3.1  Grand Summary Cost Table

|  |  | *[ insert****: Local Currency****]* ***Price*** | *[**insert****: Foreign Currency A****]* ***Price*** | *[**insert****: Foreign Currency B******]  Price*** | *[ insert****: Foreign Currency C******]  Price*** |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |
| 1. | Supply and Installation Costs (from Supply and Installation Cost Summary Table) |  |  |  |  |
|  |  |  |  |  |  |
| 2. | Recurrent Costs (from Recurrent Cost Summary Table) |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
| 4. | Grand Totals (to Bid Submission Form) |  |  |  |  |

|  |  |  |
| --- | --- | --- |
|  |  |  |
| Name of Bidder: |  |  |
|  |  |  |
| Authorized Signature of Bidder: |  |  |

3.2  Supply and Installation Cost Summary Table

Costs MUST reflect prices and rates quoted in accordance with ITB 17 and 18.

|  |  |  | **Supply & Installation Prices** | | | | |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | **Locally supplied items** | **Items supplied from outside the Purchaser’s Country** | | | |
| **Line Item No.** | **Subsystem / Item** | **Supply and Installation Cost Sub-Table No.** | *[**insert****: Local Currency****]*Price | *[ insert****: Local Currency****]*Price | *[**insert****: Foreign Currency A****]*Price | *[ insert****: Foreign Currency B****]*Price | *[ insert****: Foreign Currency C****]*Price |
|  |  |  |  |  |  |  |  |
| 0 | Project Plan | - - | - - | - - | - - | - - | - - |
| 1 | Subsystem 1 | 1 |  |  |  |  |  |
| SUBTOTALS | | | |  |  |  |  |
| TOTAL (To Grand Summary Table) | | | |  |  |  |  |

**Note:** - - indicates not applicable. “Indicates repetition of table entry above. Refer to the relevant Supply and Installation Cost Sub-Table for the specific components that constitute each Subsystem or line item in this summary table

|  |  |  |
| --- | --- | --- |
|  |  |  |
| Name of Bidder: |  |  |
|  |  |  |
| Authorized Signature of Bidder: |  |  |
|  |  |  |

3.3  Recurrent Cost Summary Table

Costs MUST reflect prices and rates quoted in accordance with ITB 17 and ITB 18.

| **Line Item No.** | **Subsystem / Item** | **Recurrent Cost Sub-Table No.** | *[**insert****: Local Currency****]* ***Price*** | *[**insert****: Foreign Currency A****]* ***Price*** | *[**insert****: Foreign Currency B****]* ***Price*** | *[**insert****: Foreign Currency C******] Price*** |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |
| y | Recurrent Cost Items |  |  |  |  |  |
| y.1 | \_\_\_\_ | y.1 |  |  |  |  |
|  |  |  |  |  |  |  |
|  | Subtotals (to Grand Summary Table) | |  |  |  |  |

**Note:** Refer to the relevant Recurrent Cost Sub-Tables for the specific components that constitute the Subsystem or line item in this summary table.

|  |  |  |
| --- | --- | --- |
|  |  |  |
| Name of Bidder: |  |  |
|  |  |  |
| Authorized Signature of Bidder: |  |  |

3.4  Supply and Installation Cost Sub-Table *[insert: identifying number]*

Line item number: *[specify:* ***relevant line item number from the Supply and Installation Cost Summary Table*** *(e.g., 1.1)]*

Prices, rates, and subtotals MUST be quoted in accordance with ITB 17 and ITB 18.

|  |  |  |  | **Unit Prices / Rates** | | | | | **Total Prices** | | | | |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | **Supplied Locally** | **Supplied from outside the Purchaser’s Country** | | | | **Supplied Locally** | **Supplied from outside the Purchaser’s Country** | | | |
| **Compo­nent  No.** | **Component Description** | **Country of Origin Code** | **Quan­tity** | *[**insert:* ***local currency****]* | *[ insert:* ***local currency****]* | *[**insert:* ***foreign currency A****]* | *[ insert* ***foreign currency B****]* | *[ insert:* ***foreign currency C****]* | *[ insert:* ***local currency****]* | *[ insert:* ***local currency****]* | *[ insert:* ***foreign currency A****]* | *[ insert:* ***foreign currency B****]* | *[**insert:* ***foreign currency C****]* |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| X.1 | \_\_\_\_ | - - | - - | - - | - - | - - | - - | - - |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Subtotals (to *[ insert:* ***line item***] of Supply and Installation Cost Summary Table) | | | | | | | | |  |  |  |  |  |

**Note:** - - indicates not applicable.

|  |  |  |
| --- | --- | --- |
|  |  |  |
| Name of Bidder: |  |  |
|  |  |  |
| Authorized Signature of Bidder: |  |  |

3.5 Recurrent Cost Sub-Table *[insert: identifying number] -- Warranty Period*

Lot number: [if a multi-lot procurement, insert: lot number, otherwise state “single lot procurement”]

Line item number**:** *[specify:* ***relevant line item number from the Recurrent Cost Summary Table******–*** *(e.g., y.1)]*

Currency: *[specify:* ***the currency of the Recurrent Costs in which the costs expressed in this Sub-Table are expressed****]*

[As necessary for operation of the System, specify: the detailed components and quantities in the Sub-Table below for the line item specified above, modifying the sample components and sample table entries as needed. Repeat the Sub-Table as needed to cover each and every line item in the Recurrent Cost Summary Table that requires elaboration. ]

Costs MUST reflect prices and rates quoted in accordance with ITB 17 and ITB 18.

|  |  | Maximum all-inclusive costs (for costs in *[ insert:* ***currency****]*) | | | | | | |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component  No. | Component | Y1 | Y2 | Y3 | Y4 | ... | Yn | Sub-total for *[ insert:* ***currency****]* |
| 1. | Hardware Maintenance | Incl. in Warranty | Incl. in Warranty | Incl. in Warranty |  |  |  |  |
| 2. | Software Licenses & Updates | Incl. in Warranty |  |  |  |  |  |  |
| 2.1 | System and General-Purpose Software | Incl. in Warranty |  |  |  |  |  |  |
| 2.2 | Application, Standard and Custom Software | Incl. in Warranty |  |  |  |  |  |  |
| 3. | Technical Services |  |  |  |  |  |  |  |
| 3.1 | Sr. Systems Analyst |  |  |  |  |  |  |  |
| 3.2 | Sr. Programmer |  |  |  |  |  |  |  |
| 3.3 | Sr. Network Specialist, ….. etc. |  |  |  |  |  |  |  |
| 4. | Telecommunications costs [to be detailed] |  |  |  |  |  |  |  |
| 5. | [Identify other recurrent costs as may apply] |  |  |  |  |  |  |  |
|  | Annual Subtotals: |  |  |  |  |  |  | - - |
| Cumulative Subtotal (to *[ insert:* ***currency***] entry for *[ insert:* ***line item*** *]* in the Recurrent Cost Summary Table) | | | | | | | |  |

|  |  |  |
| --- | --- | --- |
| Name of Bidder: |  |  |
|  |  |  |
| Authorized Signature of Bidder: |  |  |
|  |  |  |

3.6 Country of Origin Code Table

| Country of Origin | Country Code |  | Country of Origin | Country Code |  | Country of Origin | Country Code |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |

Form ELI 5.1.1- Bidder Information Form

*[****Note****: The Bidder shall fill in this Form in accordance with the instructions indicated below. No alterations to its format shall be permitted and no substitutions shall be accepted.]*

Date: *[insert* ***date (as day, month and year) of Bid submission***]

IFB No.: *[insert* ***number of Bidding process****]*

Alternative No.: *[insert* ***identification No if this is a Bid for an alternative]*** *otherwise state* ***“not applicable”***

Page \_\_\_\_\_\_\_\_ of\_ \_\_\_\_\_\_ pages

|  |
| --- |
| 1. Bidder’s Name *[insert* ***Bidder’s legal name****]* |
| 2. In case of JV, legal name of each member : *[insert* ***legal name of each member in JV****]* |
| 3. Bidder’s actual or intended country of registration: *[insert* ***actual or intended country of registration****]* |
| 4. Bidder’s year of registration: *[insert* ***Bidder’s year of registration****]* |
| 5. Bidder’s Address in country of registration: *[insert* ***Bidder’s legal address in country of registration****]* |
| 6. Bidder’s Authorized Representative Information  Name: *[insert* ***Authorized Representative’s name****]*  Address: *[insert* ***Authorized Representative’s Address****]*  Telephone/Fax numbers: *[insert* ***Authorized Representative’s telephone/fax numbers****]*  Email Address: *[insert* ***Authorized Representative’s email address****]* |
| 7. Attached are copies of original documents of *[check the box(es) of the attached original documents]*  🞎 Articles of Incorporation (or equivalent documents of constitution or association), and/or documents of registration of the legal entity named above, in accordance with ITB 4.4.  🞎 In case of JV, letter of intent to form JV or JV agreement, in accordance with ITB 4.1.  🞎 In case of government-owned enterprise or institution, documents establishing legal and financial autonomy and compliance with the principles of commercial law, in accordance with ITB Sub-Clause 4.6  8. Included are the organizational chart and a list of Board of Directors, |

Form ELI 5.1.2- Bidder’s JV Members Information Form

*[The Bidder shall fill in this Form in accordance with the instructions indicated below. The following table shall be filled in for the Bidder and for each member of a Joint Venture].*

Date: *[insert* ***date (as day, month and year) of Bid submission***]

IFB No.: *[insert* ***number of Bidding process****]*

Alternative No.: *[insert* ***identification No if this is a Bid for an alternative,*** *otherwise state* ***“not applicable”****]*

Page \_\_\_\_\_\_\_\_ of\_ \_\_\_\_\_\_ pages

|  |
| --- |
| 1. Bidder’s Name: *[insert* ***Bidder’s legal name****]* |
| 2. Bidder’s JV Member’s name: *[insert* ***JV’s Member legal name****]* |
| 3. Bidder’s JV Member’s country of registration: *[insert* ***JV’s Member country of registration****]* |
| 4. Bidder’s JV Member’s year of registration: *[insert* ***JV’s Member year of registration****]* |
| 5. Bidder’s JV Member’s legal address in country of registration: *[insert* ***JV’s Member legal address in country of registration****]* |
| 6. Bidder’s JV Member’s authorized representative information  Name: *[insert* ***name of JV’s Member authorized representative****]*  Address: *[insert* ***address of JV’s Member authorized representative****]*  Telephone/Fax numbers: *[insert* ***telephone/fax numbers of JV’s Member authorized representative****]*  Email Address: *[insert* ***email address of JV’s Member authorized representative****]* |
| 7. Attached are copies of original documents of *[check the box(es) of the attached original documents]*  🞎 Articles of Incorporation (or equivalent documents of constitution or association), and/or registration documents of the legal entity named above, in accordance with ITB 4.4.  🞎 In case of a state-owned enterprise or institution, documents establishing legal and financial autonomy, operation in accordance with commercial law, and they are not under the supervision of the Purchaser in accordance with ITB 4.6.  8. Included are the organizational chart, and a list of Board of Directors. |

Form CON – 2- Historical Contract Non-Performance, Pending Litigation and Litigation History

In case a prequalification process was conducted this form should be used only if the information submitted at the time of prequalification requires updating

Bidder’s Legal Name: *[insert* ***Bidder’s Legal Name****]*

Date: *[insert* ***date****]*

JV member Legal Name: *[insert* ***JV Member Legal Name****]*

IFB No.: *[insert* ***IFB number****]*

Page \_\_\_\_\_\_\_ of \_\_\_\_\_\_\_ pages

|  |  |  |  |
| --- | --- | --- | --- |
| Non-Performed Contracts in accordance with Section III, Evaluation and Qualification Criteria | | | |
|  Contract non-performance did not occur since 1st January *[insert year]* specified in Section III, Evaluation and Qualification Criteria, Sub-Factor 5.2.1.   Contract(s) not performed since 1st January *[insert year]* specified in Section III, Evaluation and Qualification Criteria, requirement 5.2.1 | | | |
| **Year** | **Non- performed portion of contract** | **Contract Identification** | **Total Contract Amount (current value, currency, exchange rate and US$ equivalent)** |
| *[insert* ***year****]* | *[insert* ***amount and percentage****]* | Contract Identification: *[indicate* ***complete contract name/ number, and any other identification****]*  Name of Employer: *[insert* ***full name****]*  Address of Employer: *[insert* ***street/city/country****]*  Reason(s) for nonperformance: *[indicate* ***main reason(s****)]* | *[insert* ***amount****]* |
| Pending Litigation, in accordance with Section III, Evaluation and Qualification Criteria | | | |
|  No pending litigation in accordance with Section III, Evaluation and Qualification Criteria, Sub-Factor 5.2.3. | | | |
|  Pending litigation in accordance with Section III, Evaluation and Qualification Criteria, Sub-Factor 5.2.3 as indicated below. | | | |

|  |  |  |  |
| --- | --- | --- | --- |
| **Year of dispute** | **Amount in dispute (currency)** | **Contract Identification** | **Total Contract Amount (currency), USD Equivalent (exchange rate)** |
| *[specify* ***year****]* | *[specify* ***amount and currency****]* | Contract Identification: *[insert* ***Contract ID****]*  Name of Employer: *[insert* ***Name of Employer****]*  Address of Employer: *[insert* ***Address of Employer****]*  Matter in dispute: *[describe* ***Matter of dispute****]*  Party who initiated the dispute: *[specify* ***Initiator of dispute****]*  Status of dispute: *[specify* ***Status of dispute****]* | *[specify* ***total contract amount and currency, USD equivalent and exchange rate****]* |
| *[specify* ***year****]* | *[specify* ***amount and currency****]* | Contract Identification: *[insert* ***Contract ID****]*  Name of Employer: *[insert* ***Name of Employer****]*  Address of Employer: *[insert* ***Address of Employer****]*  Matter in dispute: *[describe* ***Matter of dispute****]*  Party who initiated the dispute: *[specify* ***Initiator of dispute****]*  Status of dispute: *[specify* ***Status of dispute****]* | *[specify* ***total contract amount and currency, USD equivalent and exchange rate****]* |
| Litigation History in accordance with Section III, Evaluation and Qualification Criteria | | | |
|  No Litigation History in accordance with Section III, Evaluation and Qualification Criteria, Sub-Factor 5.2.4.   Litigation History in accordance with Section III, Evaluation and Qualification Criteria, Sub-Factor 5.2.4 as indicated below. | | | |
| **Year of award** | **Outcome as percentage of Net Worth** | **Contract Identification** | **Total Contract Amount (currency), USD Equivalent (exchange rate)** |
| *[specify* ***year****]* | *[specify* ***percentage of net worth****]* | Contract Identification: *[insert* ***Contract ID****]*  Name of Employer: *[insert* ***Name of Employer****]*  Address of Employer: *[insert* ***Address of Employer****]* | *[specify* ***total contract amount and currency, USD equivalent and exchange rate****]* |

Form EXP 5.4.1- General Experience

Bidder’s Legal Name: *[insert* ***Bidder’s Legal Name****]*

Date: *[insert* ***Date****]*

JV Member Legal Name: *[insert* ***JV Member Legal Name****]*

IFB No.: *[insert* ***IFB number****]*

Page \_\_\_\_\_\_\_ of \_\_\_\_\_\_\_ pages

| **Starting Month / Year** | **Ending Month / Year** | **Years\*** | **Contract Identification** | **Role of Bidder** |
| --- | --- | --- | --- | --- |
| *[insert* ***month / year****]* | *[insert* ***month / year****]* | *[insert* ***number of years****]* | Contract name: *[insert* ***Name of Contract*** *]*  Brief Description of the Information System performed by the Bidder: *[describe* ***Information System****]*  Name of Purchaser: *[insert* ***Name of Purchaser*** *]*  Address: *[insert* ***Address of Purchaser*** *]* | *[describe* ***role of Bidder under the contract****]* |
| *[insert* ***month / year****]* | *[insert* ***month / year****]* | *[insert* ***number of years****]* | Contract name: *[insert* ***Name of Contract*** *]*  Brief Description of the Information System performed by the Bidder: *[describe* ***Information System****]*  Name of Purchaser: *[insert* ***Name of Purchaser*** *]*  Address: *[insert* ***Address of Purchaser*** *]* | *[describe* ***role of Bidder under the contract****]* |
| *[insert* ***month / year****]* | *[insert* ***month / year****]* | *[insert* ***number of years****]* | Contract name: *[insert* ***Name of Contract*** *]*  Brief Description of the Information System performed by the Bidder: *[describe* ***Information System****]*  Name of Purchaser: *[insert* ***Name of Purchaser*** *]*  Address: *[insert* ***Address of Purchaser*** *]* | *[describe* ***role of Bidder under the contract****]* |
| *[insert* ***month / year****]* | *[insert* ***month / year****]* | *[insert* ***number of years****]* | Contract name: *[insert* ***Name of Contract*** *]*  Brief Description of the Information System performed by the Bidder: *[describe* ***Information System****]*  Name of Purchaser: *[insert* ***Name of Purchaser*** *]*  Address: *[insert* ***Address of Purchaser*** *]* | *[describe* ***role of Bidder under the contract****]* |

\*List calendar year for years with contracts with at least nine (9) months activity per year starting with the earliest year

Form EXP – 5.4.2- Specific Experience

Bidder’s Legal Name: *[insert* ***Bidder’s Legal Name****]*

Date: *[insert* ***Date****]*

JV Member Legal Name: *[insert* ***JV Member Legal Name****]*

IFB No.: *[insert* ***IFB number****]*

Page \_\_\_\_\_\_\_ of \_\_\_\_\_\_\_ pages

| **Similar Contract Number: \_\_\_ of \_\_\_ required.** | **Information** | | |
| --- | --- | --- | --- |
| Contract Identification | *[insert* ***Contract ID****]* | | |
| Award date  Completion date | *[insert* ***Date of******Award***  *[insert* ***Date of******Completion*** | | |
|  |  | | |
| Role in Contract | Prime Supplier | Management Contractor | Subcontractor |
| Total contract amount | *[insert* ***contract amount and currency****]* | | *[insert* ***contract amount in USD and exchange rate****]* |
| If member in a JV or subcontractor, specify participation of total contract amount | *[insert* ***percentage****]*% | *[insert* ***total******contract amount and currency****]* | *[insert* ***total******contract amount in USD and exchange rate****]* |
| Purchaser’s Name: | *[insert* ***Purchaser’s Name****]* | | |
| Address:  Telephone/fax number:  E-mail: | *[insert* ***Purchaser’s Address****]*  *[insert* ***Purchaser’s Telephone / fax number****]*  *[insert* ***Purchaser’s e-mail address****]* | | |

Form EXP – 5.4.2 (cont.)- Specific Experience (cont.)

Bidder’s Legal Name: *[insert* ***Bidder’s Legal Name****]*

Date: *[insert* ***Date****]*

JV Member Legal Name: *[insert* ***JV Member Legal Name****]*

IFB No.: *[insert* ***IFB number****]*

Page \_\_\_\_\_\_\_ of \_\_\_\_\_\_\_ pages

| **Similar Contract No.** *[insert* ***specific number****]* **of** *[****insert total number of contracts****]* **required** | **Information** |
| --- | --- |
| Description of the similarity in accordance with Sub-Factor 5.4.2 of Section III: |  |
| Amount | *[insert* ***contract******amount and currency and USD equivalent and exchange rate****]* |
| Geographical Scope | *[describe* ***geographic scope of the users of the information system****]* |
| Functional Scope | *[describe* ***the functionalities provided by the information system****]* |
| Methods/Technology | *[describe* ***methodologies and technologies used to implement the information system****]* |
| Key Activities | *[describe* ***the key activities of the Bidder under the contract****]* |

Form CCC- Summary Sheet: Current Contract Commitments / Work in Progress

*[Bidders and each partner to an Joint Venture bid should provide information on their current commitments on all contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion, but for which an unqualified, full completion certificate has yet to be issued.]*

Bidder’s Legal Name: *[insert* ***Bidder’s Legal Name****]*

Date: *[insert* ***Date****]*

JV Member Legal Name: *[insert* ***JV Member Legal Name****]*

IFB No.: *[insert* ***IFB number****]*

Page \_\_\_\_\_\_\_ of \_\_\_\_\_\_\_ pages

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of contract | Purchaser, contact address/tel./fax | Value of outstanding Information System (current US$ equivalent) | Estimated completion date | Average monthly invoicing over last six months (US$ equivalent/month) |
| 1. *[insert* ***Name of Contract****]* | *[insert* ***Name of Purchaser, contact address, telephone / fax number****]* | *[insert* ***Total Outstanding Contract Value of the information system in USD equivalent and exchange rate]*** | *[insert* ***Estimated completion date****]* | *[insert* ***Average monthly invoices in USD equivalent and exchange rate]*** |
| 2. *[insert* ***Name of Contract****]* | *[insert* ***Name of Purchaser, contact address, telephone / fax number****]* | *[insert* ***Total Outstanding Contract Value of the information system in USD equivalent and exchange rate]*** | *[insert* ***Estimated completion date****]* | *[insert* ***Average monthly invoices in USD equivalent and exchange rate]*** |
| 3. *[insert* ***Name of Contract****]* | *[insert* ***Name of Purchaser, contact address, telephone / fax number****]* | *[insert* ***Total Outstanding Contract Value of the information system in USD equivalent and exchange rate]*** | *[insert* ***Estimated completion date****]* | *[insert* ***Average monthly invoices in USD equivalent and exchange rate]*** |
| ... |  |  |  |  |

Form FIN – 5.3.1- Financial Situation: Historical Financial Performance

To be completed by the Bidder and, if JV, by each member

Bidder’s Legal Name: *[insert* ***Bidder’s Legal Name****]*

Date: *[insert* ***Date****]*

JV Member Legal Name: *[insert* ***JV Member Legal Name****]*

IFB No.: *[insert* ***IFB number****]*

Page \_\_\_\_\_\_\_ of \_\_\_\_\_\_\_ pages

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Financial information in US$ equivalent** | **Historic information for previous** *[insert* ***number****]* **years**  *(US$ equivalent in 000s)* | | | | | | |
|  | Year 1 | Year 2 | Year 3 | Year … | Year n | Avg. | Avg. Ratio |
| Information from Balance Sheet | | | | | | | |
| Total Assets (TA) |  |  |  |  |  |  |  |
| Total Liabilities (TL) |  |  |  |  |  |  |
| Net Worth (NW) |  |  |  |  |  |  |  |
| Current Assets (CA) |  |  |  |  |  |  |  |
| Current Liabilities (CL) |  |  |  |  |  |  |
| Information from Income Statement | | | | | | | |
| Total Revenue (TR) |  |  |  |  |  |  |  |
| Profits Before Taxes (PBT) |  |  |  |  |  |  |
|  | | | | | | | |

Attached are copies of financial statements (balance sheets, including all related notes, and income statements) for the years required above complying with the following conditions:

1. Must reflect the financial situation of the Bidder or member to a JV, and not sister or parent companies
2. Historic financial statements must be audited by a certified accountant
3. Historic financial statements must be complete, including all notes to the financial statements
4. Historic financial statements must correspond to accounting periods already completed and audited (no statements for partial periods shall be requested or accepted)

Form FIN – 5.3.2- Average Annual Turnover

***[To be completed by the Bidder and, if JV, by each member]***

Bidder’s Legal Name: *[insert* ***Bidder’s Legal Name****]*

Date: *[insert* ***Date****]*

JV Member Legal Name: *[insert* ***JV Member Legal Name****]*

IFB No.: *[insert* ***IFB number****]*

Page \_\_\_\_\_\_\_ of \_\_\_\_\_\_\_ pages

|  |  |  |
| --- | --- | --- |
| **Annual turnover data (applicable activities only)** | | |
| Year | Amount and Currency | US$ equivalent |
| *[insert* ***year****]* | *[insert* ***amount and currency****]* | *[insert* ***amount in USD equivalent and exchange rate****]* |
| *[insert* ***year****]* | *[insert* ***amount and currency****]* | *[insert* ***amount in USD equivalent and exchange rate****]* |
| *[insert* ***year****]* | *[insert* ***amount and currency****]* | *[insert* ***amount in USD equivalent and exchange rate****]* |
| *[insert* ***year****]* | *[insert* ***amount and currency****]* | *[insert* ***amount in USD equivalent and exchange rate****]* |
| *[insert* ***year****]* | *[insert* ***amount and currency****]* | *[insert* ***amount in USD equivalent and exchange rate****]* |
| *[insert* ***year****]* | *[insert* ***amount and currency****]* | *[insert* ***amount in USD equivalent and exchange rate****]* |
| \*Average Annual Turnover | *[insert* ***amount and currency****]* | *[insert* ***amount in USD equivalent and exchange rate****]* |

\*Average annual turnover calculated as total certified payments received for work in progress or completed, divided by the number of years specified in Section III, Evaluation and Qualification Criteria, Sub-Factor 5.3.2.

Form FIN 5.3.3- Financial Resources

*To be completed by the Bidder and, if JV, by each member*

Bidder’s Legal Name: *[insert* ***Bidder’s Legal Name****]*

Date: *[insert* ***Date****]*

JV Member Legal Name: *[insert* ***JV Member Legal Name****]*

IFB No.: *[insert* ***IFB number****]*

Page \_\_\_\_\_\_\_ of \_\_\_\_\_\_\_ pages

Specify proposed sources of financing, such as liquid assets, unencumbered real assets, lines of credit, and other financial means, net of current commitments, available to meet the total cash flow demands of the subject contract or contracts as indicated in Section III, Evaluation and Qualification Criteria

|  |  |
| --- | --- |
| **Source of financing** | **Amount (US$ equivalent)** |
| 1. *[describe* ***type and source of available financing****]* | *[insert* ***amount of available financing in USD equivalent and exchange rate****]* |
| 2. *[describe* ***type and source of available financing****]* | *[insert* ***amount of available financing in USD equivalent and exchange rate****]* |
| 3. *[describe* ***type and source of available financing****]* | *[insert* ***amount of available financing in USD equivalent and exchange rate****]* |
| 4. *[describe* ***type and source of available financing****]* | *[insert* ***amount of available financing in USD equivalent and exchange rate****]* |

Personnel Capabilities- Key Personnel

*To be completed by the Bidder and, if JV, by each member*

Bidder’s Legal Name: *[insert* ***Bidder’s Legal Name****]*

Date: *[insert* ***Date****]*

JV Member Legal Name: *[insert* ***JV Member Legal Name****]*

IFB No.: *[insert* ***IFB number****]*

Page \_\_\_\_\_\_\_ of \_\_\_\_\_\_\_ pages

Bidders should provide the names and details of the suitably qualified Personnel to perform the Contract. The data on their experience should be supplied using the Form PER-2 below for each candidate.

**Key Personnel**

|  |  |  |
| --- | --- | --- |
| 1. | Title of position: *[insert* ***Title of position / role in team****]* | |
|  | Name of candidate:*[insert* ***Name of Candidate****]* | |
|  | Duration of appointment: | [*insert* ***the whole period (start and end dates) for which this position will be engaged***] |
|  | Time commitment: for this position: | [*insert* ***the number of days/week/months/ that has been scheduled for this position***] |
|  | Expected time schedule for this position: | [*insert* ***the expected time schedule for this position (e.g. attach high level Gantt chart***] |
| 2. | Title of position: *[insert* ***Title of position / role in team****]* | |
|  | Name of candidate:*[insert* ***Name of Candidate****]* | |
|  | Duration of appointment: | [*insert* ***the whole period (start and end dates) for which this position will be engaged***] |
|  | Time commitment: for this position: | [*insert* ***the number of days/week/months/ that has been scheduled for this position***] |
|  | Expected time schedule for this position: | [*insert* ***the expected time schedule for this position (e.g. attach high level Gantt chart***] |
| 3. | Title of position: *[insert* ***Title of position / role in team****]* | |
|  | Name of candidate:*[insert* ***Name of Candidate****]* | |
|  | Duration of appointment: | [*insert* ***the whole period (start and end dates) for which this position will be engaged***] |
|  | Time commitment: for this position: | [*insert* ***the number of days/week/months/ that has been scheduled for this position***] |
|  | Expected time schedule for this position: | [*insert* ***the expected time schedule for this position (e.g. attach high level Gantt chart***] |

Candidate Summary

*To be completed by the Bidder and, if JV, by each member*

Bidder’s Legal Name: *[insert* ***Bidder’s Legal Name****]*

Date: *[insert* ***Date****]*

JV Member Legal Name: *[insert* ***JV Member Legal Name****]*

IFB No.: *[insert* ***IFB number****]*

Page \_\_\_\_\_\_\_ of \_\_\_\_\_\_\_ pages

|  |  |  |
| --- | --- | --- |
| Position; *[insert* ***Title of Position****]* | | Prime Alternate |
| Candidate information | Name of candidate *[insert* ***Name of Candidate****]* | Date of birth *[insert* ***Date of Birth****]* |
|  | Professional qualifications *[describe* ***Professional qualifications****]* | |
|  |  | |
| Present employment | Name of Employer *[insert* ***Name of Present Employer****]* | |
|  | Address of Employer *[insert* ***Address of Present Employer****]* | |
|  | Telephone *[insert* ***Telephone*** *of* ***Contact****]* | Contact (manager / personnel officer) *[insert* ***Name****]* |
|  | Fax *[insert* ***fax of Contact****]* | email *[insert* ***email*** *of* ***Contact****]* |
|  | Job title of candidate *[insert* ***Job Title of Candidate****]* | Years with present Employer *[insert* ***Job Number of years****]* |

Summarize professional experience over the last twenty years, in reverse chronological order. Indicate particular technical and managerial experience relevant to the project.

|  |  |  |
| --- | --- | --- |
| From | To | Company/Project/ Position/Relevant technical and management experience |
| *[insert* ***year****]* | *[insert* ***year****]* | *[describe* ***experience relevant to the proposed Contract under the is IFB****]* |
| *[insert* ***year****]* | *[insert* ***year****]* | *[describe* ***experience relevant to the proposed Contract under the is IFB****]* |
| *[insert* ***year****]* | *[insert* ***year****]* | *[describe* ***experience relevant to the proposed Contract under the is IFB****]* |
| *[insert* ***year****]* | *[insert* ***year****]* | *[describe* ***experience relevant to the proposed Contract under the is IFB****]* |

Code of Conduct for Supplier’s and Subcontractors’ Personnel Form

**Note to the Bidder**:

**The minimum content of the Code of Conduct form as set out by the Purchaser shall not be substantially modified**. However, the Bidder may add requirements as appropriate, including to take into account Contract-specific issues/risks.

The Bidder shall initial and submit the Code of Conduct form as part of its bid.

***Note to the Purchaser****:*

***The following minimum requirements shall not be modified****. The Purchaser may add additional requirements to address identified issues, informed by relevant environmental and social assessment.*

***Delete this Box prior to issuance of the bidding documents.***

**CODE OF CONDUCT FOR SUPPLIER’S AND SUBCONTRACTOR’s PERSONNEL**

We are the Supplier, [*enter name of Supplier*]. We have signed a contract with [*enter name of Purchaser*] for [*enter description of the Information System*]. The Information System will be supplied to and installed at [*enter the Project Site/s]*. Our contract requires us to implement measures to address environmental and social risks.

This Code of Conduct identifies the behavior that we require from our personnel and Subcontractors’ personnel employed in the execution of the Contract at the Project Site/s.

Our workplace is an environment where unsafe, offensive, abusive or violent behavior will not be tolerated and where all persons should feel comfortable raising issues or concerns without fear of retaliation.

**REQUIRED CONDUCT**

Suppliers and Subcontractors’ personnel employed in the execution of the Contract at the Project Site/s shall:

1. carry out his/her duties competently and diligently;
2. comply with this Code of Conduct and all applicable laws, regulations and other requirements, including requirements to protect the health, safety and well-being of other Supplier’s and Subcontractor’s personnel and any other person;
3. maintain a safe working environment including by:
   1. ensuring that workplaces, machinery, equipment and processes under each person’s control are safe and without risk to health;
   2. wearing required personal protective equipment;
   3. using appropriate measures relating to chemical, physical and biological substances and agents; and
   4. following applicable emergency operating procedures.
4. report work situations that he/she believes are not safe or healthy and remove himself/herself from a work situation which he/she reasonably believes presents an imminent and serious danger to his/her life or health;
5. treat other people with respect, and not discriminate against specific groups such as women, people with disabilities, migrant workers or children;
6. not engage in any form of sexual harassment including unwelcome sexual advances, requests for sexual favors, and other verbal or physical conduct of a sexual nature with other Supplier’s or Subcontractors’ or Purchaser’s personnel;
7. not engage in Sexual Exploitation, which means any actual or attempted abuse of position of vulnerability, differential power or trust, for sexual purposes, including, but not limited to, profiting monetarily, socially or politically from the sexual exploitation of another;
8. not engage in in Sexual Abuse, which means the actual or threatened physical intrusion of a sexual nature, whether by force or under unequal or coercive conditions;
9. not engage in any form of sexual activity with individuals under the age of 18, except in case of pre-existing marriage;
10. complete relevant training courses that will be provided related to the environmental and social aspects of the Contract, including on health and safety matters, and Sexual Exploitation and Abuse, and Sexual Harassment (SH);
11. report violations of this Code of Conduct; and
12. not retaliate against any person who reports violations of this Code of Conduct, whether to us or the Purchaser, or who makes use of the grievance mechanism for Supplier’s and Subcontractors’ personnel or the project’s Grievance Redress Mechanism.

**RAISING CONCERNS**

If any person observes behavior that he/she believes may represent a violation of this Code of Conduct, or that otherwise concerns him/her, he/she should raise the issue promptly. This can be done in either of the following ways:

1. Contact [*enter name of the Supplier’s Social Expert with relevant experience in handling* *sexual exploitation, sexual abuse and sexual harassment cases, or if such person is not required under the Contract, another individual designated by the Supplier to handle these matters*] in writing at this address [ ] or by telephone at [ ] or in person at [ ]; or
2. Call [ ] to reach the Supplier’s hotline *(if any)* and leave a message.

The person’s identity will be kept confidential, unless reporting of allegations is mandated by the country law. Anonymous complaints or allegations may also be submitted and will be given all due and appropriate consideration. We take seriously all reports of possible misconduct and will investigate and take appropriate action. We will provide warm referrals to service providers that may help support the person who experienced the alleged incident, as appropriate.

There will be no retaliation against any person who raises a concern in good faith about any behavior prohibited by this Code of Conduct. Such retaliation would be a violation of this Code of Conduct.

**CONSEQUENCES OF VIOLATING THE CODE OF CONDUCT**

Any violation of this Code of Conduct by the Supplier’s or Subcontractors’ personnel may result in serious consequences, up to and including termination and possible referral to legal authorities.

FOR Supplier’s or Subcontractors’ PERSONNEL:

I have received a copy of this Code of Conduct written in a language that I comprehend. I understand that if I have any questions about this Code of Conduct, I can contact [*enter name of Supplier’s contact person(s) with relevant experience*] requesting an explanation.

Name of Supplier’s or Subcontractor’s personnel: *[insert* ***name****]*

Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date: (day month year): *[insert* ***date****]*

Countersignature of authorized representative of the Supplier:

Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date: (day month year): *[insert* ***date****]*

Technical Capabilities

*[****Note****: To be completed by the Bidder and, if JV, by each member]*

Bidder’s Legal Name: *[insert* ***Bidder’s Legal Name****]*

Date: *[insert* ***Date****]*

JV Member Legal Name: *[insert* ***JV Member Legal Name****]*

IFB No.: *[insert* ***IFB number****]*

Page \_\_\_\_\_\_\_ of \_\_\_\_\_\_\_ pages

The Bidder shall provide adequate information to demonstrate clearly that it has the technical capability to meet the requirements for the Information System. The Bidder should summarize important certifications, proprietary methodologies, and/or specialized technologies that the Bidder proposes to utilize in the execution of the Contract or Contracts.

Manufacturer’s Authorization

***[Note****: This authorization should be written on the letterhead of the Manufacturer and be signed by a person with the proper authority to sign documents that are binding on the Manufacturer.]*

Invitation for Bids Title and No.: *[Purchaser insert:* ***IFB Title and Number****]*

To: *[Purchaser insert:* ***Purchaser’s Officer to receive the Manufacture’s Authorization****]*

WHEREAS *[ insert:* ***Name of Manufacturer*** *]* who are official producers of *[ insert:* ***items of supply by Manufacturer*** *]* and having production facilities at *[ insert:* ***address of Manufacturer*** *]* do hereby authorize *[ insert:* ***name of Bidder or Joint Venture*** *]* located at *[ insert:* ***address of Bidder or Joint Venture*** *]* (hereinafter, the “Bidder”) to submit a bid and subsequently negotiate and sign a Contract with you for resale of the following Products produced by us:

We hereby confirm that, in case the bidding results in a Contract between you and the Bidder, the above-listed products will come with our full standard warranty.

Name *[insert:* ***Name of Officer****]* in the capacity of *[insert:* ***Title of Officer]***

Signed \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Duly authorized to sign the authorization for and on behalf of: *[ insert:* ***Name of Manufacturer*** *]*

Dated this *[ insert:* ***ordinal****]* day of *[ insert:* ***month****]*, *[ insert:* ***year****]*.

*[add Corporate Seal (where appropriate)]*

Subcontractor’s Agreement

***Note****: This agreement should be written on the letterhead of the Subcontractor and be signed by a person with the proper authority to sign documents that are binding on the Subcontractor.*

Invitation for Bids Title and No.: *[Purchaser insert:* ***IFB Title and Number****]*

To: *[Purchaser insert:* ***Purchaser’s Officer to receive the Subcontractor’s Agreement]***

WHEREAS *[ insert:* ***Name of Subcontractor*** *],* having head offices at *[ insert:* ***address of Subcontractor*** *],* have been informed by *[ insert:* ***name of Bidder or Joint Venture*** *]* located at *[ insert:* ***address of Bidder or Joint Venture*** *]* (hereinafter, the “Bidder”) that it will submit a bid in which *[ insert:* ***Name of Subcontractor*** *]* will provide *[ insert:* ***items of supply or services provided by the Subcontractor*** *].*  We hereby commit to provide the above named items, in the instance that the Bidder is awarded the Contract.

Name *[insert:* ***Name of Officer****]* in the capacity of *[insert:* ***Title of Officer]***

Signed \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Duly authorized to sign the authorization for and on behalf of: *[insert:* ***Name of Subcontractor****]*

Dated this *[ insert:* ***ordinal****]* day of  *[ insert:* ***month****]*, *[ insert:* ***year****]*.

[add Corporate Seal (where appropriate)]

List of Proposed Subcontractors

|  |  |  |  |
| --- | --- | --- | --- |
|  | Item | Proposed Subcontractor | Place of Registration & Qualifications |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

Intellectual Property Forms

## Notes to Bidders on working with the Intellectual Property Forms

In accordance with ITB 11.1(j), Bidders must submit, as part of their bids, lists of all the Software included in the bid assigned to one of the following categories: (a) System, General-Purpose, or Application Software; (b) Standard or Custom Software; (c) Proprietary or Open Source. Bidders must also submit a list of all Custom Materials. These categorizations are needed to support the Intellectual Property in the GCC and SCC. The Bidder must also include the text of the software licenses for the software titles proposed.

Software List

|  | (select one per title) | | | (select one per title) | | (select one per title) | |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Title | System | General-Purpose | Application | Standard | Custom | Proprietary | Open Source |
| [insert Title] |  |  |  |  |  |  |  |
| [insert Title] |  |  |  |  |  |  |  |
| [insert Title] |  |  |  |  |  |  |  |
| [insert Title] |  |  |  |  |  |  |  |
| [insert Title] |  |  |  |  |  |  |  |
| [insert Title] |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |

**Attachments**: Proposed Software Licenses

List of Custom Materials

|  |
| --- |
| Custom Materials |
| *[insert* ***Title and description****]* |
| *[insert* ***Title and description****]* |
| *[insert* ***Title and description****]* |
| *[insert* ***Title and description****]* |
| *[insert* ***Title and description****]* |
|  |

Conformance of Information System Materials

Format of the Technical Bid

In accordance with ITB 16.2, the documentary evidence of conformity of the Information System to the bidding documents includes (but is not restricted to):

(a). The Bidder’s Preliminary Project Plan, including, but not restricted, to the topics specified in the BDS ITB 16.2. The Preliminary Project Plan should also state the Bidder’s assessment of the major responsibilities of the Purchaser and any other involved third parties in System supply and installation, as well as the Bidder’s proposed means for coordinating activities by each of the involved parties to avoid delays or interference.

(b). A written confirmation by the Bidder that, if awarded the Contract, it shall accept responsibility for successful integration and interoperability of all the proposed Information Technologies included in the System, as further specified in the Technical Requirements.

(c). Item-by-Item Commentary on the Technical Requirements demonstrating the substantial responsiveness of the overall design of the System and the individual Information Technologies, Goods, and Services offered to those Technical Requirements.

In demonstrating the responsiveness of its bid, the Bidder must use the Technical Responsiveness Checklist (Format). Failure to do so increases significantly the risk that the Bidder’s Technical Bid will be declared technically non-responsive. Among other things, the checklist should contain explicit cross-references to the relevant pages in supporting materials included the Bidder’s Technical Bid.

**Note**: The Technical Requirements are voiced as requirements of the *Supplier* and/or the *System*. The Bidder’s response must provide clear evidence for the evaluation team to assess the credibility of the response. A response of “yes” or “will do” is unlikely to convey the credibility of the response. The Bidder should indicate *that* – and to the greatest extent practical – *how* the Bidder would comply with the requirements if awarded the contract. Whenever the technical requirements relate to feature(s) of existing products (e.g., hardware or software), the features should be described and the relevant product literature referenced. When the technical requirements relate to professional services (e.g., analysis, configuration, integration, training, etc.) some effort should be expended to describe how they would be rendered – not just a commitment to perform the [cut-and-paste] requirement. Whenever a technical requirement is for the Supplier to provide certifications (e.g., ISO 9001), copies of these certifications must be included in the Technical Bid.

**Note**: The Manufacture’s Authorizations (and any Subcontractor Agreements) are to be included in Attachment 2 (Bidder Qualifications), in accordance with and ITB 15.

**Note**: As a matter of practice, the contract cannot be awarded to a Bidder whose Technical Bid deviates (materially) from the Technical Requirements – *on any Technical Requirement*. Such deviations include omissions (e.g., non-responses) and responses that do not meet or exceed the requirement. Extreme care must be exercised in the preparation and presentation of the responses to all the Technical Requirements.

(d). Supporting materials to underpin the Item-by-item Commentary on the Technical Requirements (e.g., product literature, white-papers, narrative descriptions of technical approaches to be employed, etc.). In the interest of timely bid evaluation and contract award, Bidders are encouraged not to overload the supporting materials with documents that do not directly address the Purchaser’s requirements.

(e). Any separate and enforceable contract(s) for Recurrent Cost items which the BDS ITB 17.2 required Bidders to bid.

**Note**: To facilitate bid evaluation and contract award, Bidders encouraged to provide electronic copies of their Technical Bid – preferably in a format that the evaluation team can extract text from to facilitate the bid clarification process and to facilitate the preparation of the Bid Evaluation Report.

Technical Responsiveness Checklist (Format)

|  |  |
| --- | --- |
| Tech.  Require.  No. \_ | Technical Requirement:  *[ insert:* ***abbreviated description of Requirement****]* |
| Bidder’s technical reasons supporting compliance: | |
| Bidder’s cross references to supporting information in Technical Bid: | |

*[****Note to the Purchaser****: The Technical Responsiveness tables submitted by each Bidder can help structure the Purchaser’s technical evaluation. In particular, the Purchaser can append rows to each of the Bidder’s submitted responsiveness tables to record the Purchaser’s assessment of the compliance, partial compliance, and non-compliance of the Bidder’s response to the specific Technical Requirement – including the Purchaser’s rationale for its conclusion (including, as appropriate, clear indications of the gaps in the Bidder’s response/supporting documentation). These assessments can provide a standardized presentation of the detailed underlying logic of the Purchaser’s final assessment of the responsiveness / non-responsiveness of the Bidder’s technical proposal. Typically, the detailed response/assessment tables would appear as an attachment to the Bid Evaluation Report].*

Form of Bid Security (Bank Guarantee)

*[The bank shall fill in this Bank Guarantee Form in accordance with the instructions indicated.]*

*[Guarantor letterhead or SWIFT identifier code]*

Beneficiary:*[Purchaser to insert its* ***name and address****]*

IFB No.: *[Purchaser to insert reference* ***number for the IFB****]*

Alternative No*.: [Insert identification No if this is a Bid for an alternative]*

**Date:** *[Insert* ***date of issue****]*

**BID GUARANTEE No.:** *[Insert* ***guarantee reference number****]*

We have been informed that *[insert* ***name of the Bidder****, which in the case of a joint venture shall be the name of the joint venture (whether legally constituted or prospective) or the names of all members thereof]* (hereinafter called “the Applicant”) has submitted or will submit the Beneficiary its bid (hereinafter called “the Bid”) for the execution of *[insert* ***Name of Contract****]* under Request for Bids No. [*insert* ***number****]* (“the IFB”).

Furthermore, we understand that, according to the Beneficiary’s, Bids must be supported by a Bid guarantee.

At the request of the Applicant, we as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of *[insert* ***amount in figures*** *([insert* ***amount in words****)]* upon receipt by us of the Beneficiary’s demand supported by the Beneficiary’s statement, whether in the demand itself or a separate signed document accompanying the demand, stating that either the Applicant:

(a) has withdrawn its Bid prior to the Bid validity expiry date set forth in the Applicant’s Letter of Bid, or any extended date provided by the Applicant; or

(b) having been notified of the acceptance of its Bid by the Beneficiary prior to the expiry date of the Bid validity or any extension thereof provided by the Applicant has failed to: (i) execute the Contract Agreement, if required, or (ii) furnish the performance security, in accordance with the Instructions to Bidders (“ITB”) of the Beneficiary’s bidding document.

This guarantee will expire: (a) if the Applicant is the successful Bidder, upon our receipt of copies of the contract agreement signed by the Applicant and the Performance Security issued to the Beneficiary in relation to such Contract Agreement; or (b) if the Applicant is not the successful Bidder, upon the earlier of (i) our receipt of a copy of the Beneficiary’s notification to the Applicant of the results of the Bidding process; or (ii) twenty-eight days after the expiry date of the Bid validity.

Consequently, any demand for payment under this guarantee must be received by us at the office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 758.

**\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**

*[signature(s)]*

Form of Bid Security (Bid Bond)

(Not Applicable)

BOND NO. *[insert* ***number****]*

BY THIS BOND *[insert* ***Name****]* as Principal (hereinafter called “the Principal”), and *[insert* ***Name****],* **authorized to transact business in** *[insert* ***Jurisdiction****],* as Surety (hereinafter called “the Surety”), are held and firmly bound unto *[insert* ***Purchaser******Name****]* as Obligee (hereinafter called “the Purchaser”) in the sum of *[insert* ***amount in figures****]* [[21]](#footnote-22) (*[insert* ***amount in words]***), for the payment of which sum, well and truly to be made, we, the said Principal and Surety, bind ourselves, our successors and assigns, jointly and severally, firmly by these presents.

WHEREAS the Principal has submitted or will submit a written Bid to the Purchaser dated the *[insert* ***ordinal******number*** day of *[insert* ***month****] [****insert year****],* for *[insert* ***name of Contract****]* (hereinafter called the “Bid”).

NOW, THEREFORE, THE CONDITION OF THIS OBLIGATION is such that if the Principal:

1. withdraws its Bid prior to the Bid validity expiry date set forth in the Principal’s Letter of Bid, or any extended date provided by the Principal; or
2. having been notified of the acceptance of its Bid by the Purchaser prior to the expiry date of the Bid validity or any extension thereto provided by the Applicant has failed to; (i) execute the Contract Agreement, or (ii) furnish the Performance Security in accordance with the Instructions to Bidders (“ITB”) of the Purchaser’s bidding document.

then the Surety undertakes to immediately pay to the Purchaser up to the above amount upon receipt of the Purchaser’s first written demand, without the Purchaser having to substantiate its demand, provided that in its demand the Purchaser shall state that the demand arises from the occurrence of any of the above events, specifying which event(s) has occurred.

The Surety hereby agrees that its obligation will remain in full force and effect up to and including the date 28 days after the date of expiry of the Bid validity set forth in the Principal’s Letter of Bid or extended thereto provided by the Principal.

IN TESTIMONY WHEREOF, the Principal and the Surety have caused these presents to be executed in their respective names this *[insert* ***number*** day of *[insert* ***month****] [insert* ***year****]*.

Principal: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ Surety: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  
 Corporate Seal (where appropriate)

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  
*(Signature) (Signature)*

*(Printed name and title) (Printed name and title)*

Form of Bid-Securing Declaration

*[The Bidder shall fill in this Form in accordance with the instructions indicated.]*

Date: *[insert* ***date*** *(as day, month and year)]*

Bid No.: *[insert* ***number of bidding process****]*

Alternative No.: *[insert* ***identification No if this is a Bid for an alternative****]*

To: *[insert* ***complete name of Purchaser****]*

We, the undersigned, declare that:

We understand that, according to your conditions, Bids must be supported by a Bid-Securing Declaration.

We accept that we will automatically be suspended from being eligible for bidding or submitting proposals in any contract with the Purchaser for the period of time of *[insert* ***number of months or years****],* starting on *[insert* ***date****],* if we are in breach of our obligation(s) under the bid conditions, because we:

(a) have withdrawn our Bid prior to the expiry date of the Bid validity specified in the Letter of Bid or any extended date provided by us; or

(b) having been notified of the acceptance of our Bid by the Purchaser prior to the expiry date of the Bid validity in the Letter of Bid or any extended date provided by us, (i) fail to sign the Contract agreement; or (ii) fail or refuse to furnish the Performance Security, if required, in accordance with the ITB.

We understand this Bid-Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of your notification to us of the name of the successful Bidder; or (ii) twenty-eight days after the expiry date of the Bid validity.

Name of the Bidder**\*** *[insert* ***Name of Bidder****]*

Name of the person duly authorized to sign the Bid on behalf of the Bidder**\*\****[insert* ***Name of authorized person****]*

Title of the person signing the Bid*[insert* ***Title of authorized person****]*

Signature of the person named above \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date signed *[insert* ***ordinal******number****]* day of *[insert* ***month****]* , *[insert* ***year****]*

**\***: In the case of the Bid submitted by joint venture specify the name of the Joint Venture as Bidder

\*\*: Person signing the Bid shall have the power of attorney given by the Bidder attached to the Bid

*[Note: In case of a Joint Venture, the Bid-Securing Declaration must be in the name of all members to the Joint Venture that submits the bid.]*

Section V - Eligible Countries

**Eligibility for Procurement of Goods, Works and Non Consulting Services under   
IsDB Project Financing**

1. In accordance with Para 1.11 of the Guidelines for Procurement of Goods, Works and Related Services under Islamic Development Bank Project Financing, April 2019, it is a fundamental policy of IsDB that the Goods, Works and related services provided by the Contractor, and its associates and sub-contractors, shall be in strict compliance with the Boycott Regulations of the Organization of the Islamic Cooperation, the League of Arab States and the African Union. The Beneficiary shall advise prospective Bidders that bids will only be considered from Firms that are not subject to these Boycott Regulations. The Bidder shall provide a letter of oath to that effect.

The eligibility of a Firm will be determined during the evaluation process. In cases where Firms withhold information to evade disqualification on account of the eligibility requirement, the Beneficiary will have the right to cancel the contract at any time and also to penalize such Firm and claim compensation for losses incurred, as a consequence thereof, by the Beneficiary and/or IsDB. IsDB reserves the right not to honor any contract if the supplier or contractor involved is found to be ineligible based on the eligibility requirement stated therein.

For the purpose of eligibility, a Member Country (MC) Firm shall comply with all of the following:

1. it is established or incorporated in a IsDB MC;
2. its principal place of business is located in a IsDB MC; and
3. it is more than 50% beneficially owned by a firm or firms in one or more MC (which firm or firms must also qualify as to nationality) and/or citizens of such MC.

For the purpose of eligibility, a domestic firm of a MC is defined as follows:

1. it is established or incorporated in the MC where the Works are to be carried out and/or where the Goods are to be delivered;
2. its principal place of business is located in the Beneficiary MC; and
3. it is more than 50% beneficially owned by a firm or firms in the Beneficiary MC (which firm or firms must also qualify as to nationality) and/or citizens of such MC.

2. In reference to ITB 4.8 and ITB 5.1, for the information of the Bidders, at the present time firms and information systems from the following countries are excluded from this bidding process:

Under ITB 4.8(a) and ITB 5.1:  *[insert a list of the countries following approval by IsDB to apply the restriction or state “none”].*

Under ITB 4.8(b) and ITB 5.1:  *[insert a list of the countries following approval by IsDB to apply the restriction or state “none”]*

Section VI – IsDB Policy – Corrupt and Fraudulent Practices

Guidelines for Procurement of Goods, Works and related services under Islamic Development Project Financing, April 2019

**Fraud and Corruption:**

1.39 It is IsDB’s policy to require that Beneficiaries as well as Firms, Contractors and their agents (whether declared or not), sub-contractors, sub-consultants, service providers or Suppliers, and any personnel, observe the highest standard of ethics during the selection and execution of IsDB financed contracts[[22]](#footnote-23). In pursuance of this policy, the requirements of *IsDB Group Anti-Corruption Guidelines on Preventing and Combating Fraud and Corruption in IsDB Group-Financed Projects* and sanctions procedures shall be observed at all times. IsDB:

1. defines, for the purposes of this provision, the terms set forth as follows:
2. “corrupt practice” is the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence improperly the actions of another party;
3. “fraudulent practice” is any act or omission, including misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain financial or other benefit or to avoid an obligation;
4. “collusive practices” is an arrangement between two or more parties designed to achieve an improper purpose, including to influence improperly the actions of another party;
5. “coercive practices” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party; and
6. “obstructive practice” is deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede an IsDB investigation into allegations of a corrupt, fraudulent, coercive, or collusive practice; and/or threatening, harassing, or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation; or acts intended to materially impede the exercise of IsDB inspection and audit rights provided for under Paragraph 1.39(e) below.
7. will reject a Bid for award if it determines that the Bidder recommended for award, or any of its personnel, or its agents, or its sub-consultants, sub-contractors, service providers, Suppliers and/or their employees, has, directly or indirectly, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices in competing for the contract in question;
8. will declare misprocurement and cancel the portion of the Project Financing allocated to a contract if it determines at any time that representatives of the Beneficiary or of a recipient of any part of the proceeds of the Project Financing engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices during the procurement or the implementation of the contract in question, without the Beneficiary having taken timely and appropriate action satisfactory to IsDB to address such practices when they occur, including by failing to inform IsDB in a timely manner at the time they knew of the practices;
9. will sanction a Firm or individual, at any time, in accordance with the prevailing IsDB sanctions procedures[[23]](#footnote-24), including by publicly declaring such Firm or individual ineligible, either indefinitely or for a stated period of time:
10. to be awarded a IsDB-financed contract; and
11. to be a nominated sub-contractor, consultant, sub-consultant, Contractor or Supplier of an otherwise eligible Firm being awarded a IsDB-financed contract; and
12. will require that a clause be included in Bidding Documents and in contracts financed by IsDB, requiring Bidders, including their agents (whether declared or not), sub-contractors, sub-consultants, service providers or Suppliers, to permit IsDB to inspect all accounts, records and other documents relating to the submission of Bids and contract performance, and to have them audited by auditors appointed by IsDB.

PART 2 – Purchaser’s Requirements

Section VII - Requirements of the Information System

**(including Technical Requirements, Implementation Schedule, System Inventory Tables, Background and Informational Materials)**

## *Notes on preparing the Requirements of the Information System*

*The Requirements of the Information System comprise four significant and closely related subsections:*

* *Technical Requirements*
* *Implementation Schedule*
* *System Inventory Tables*
* *Background and Informational Materials*

*Each subsection is presented and discussed separately*

**Technical Requirements**

## *Notes on preparing the Technical Requirements*

*The Technical Requirements – in combination with the Implementation Schedule and the supporting System Inventory Tables – state the Supplier’s obligations to design, supply and install the Information System and, as such, should be “voiced” to the Supplier (i.e., “The System MUST …” “The Supplier MUST …”). They form the contractual basis for the Purchaser-Supplier interactions on technical matters (in combination with refinements introduced through the Supplier’s bid, the Project Plan, and any Change Orders).*

*The Technical Requirements also must include all the technical details that Bidders will need to prepare realistic, responsive, and competitive bids (i.e., covering all their obligations under the Contract if so awarded). However, matters addressed to the Bidder’s (i.e., before contract award) generally belong in the Format of the Technical Bid Section 8 of Part 1.*

*Often Technical Requirements are based on either consultant’s project proposals (voiced to the Purchaser’s management) or bids from previous procurements (voiced to the Purchaser). In both instances, care needs to be taken in converting these materials into Technical Requirements (voiced to the Supplier). Otherwise, substantial ambiguity will be introduced into the Technical Requirements from, among other things, “aspirational” text suggesting the benefits (to the Purchaser) which are often not obligations that the Supplier can deliver on or be held to deliver upon. Bid based language will often include “sales pitches”, such as “expandability up to sixteen processors”, whereas the Technical Requirements need to be stated as threshold values to be cleared by the Supplier (e.g., “expandability to at least sixteen processors”).*

*To the greatest extent possible, the Technical Requirements should be expressed in terms of the Purchaser’s business activities, rather than a technological design. This leaves it up to the market to determine what specific Information Technologies can best satisfy these business needs. This is particularly relevant where the Information System will embody complex business logic in the form of application software.*

*Even in the case of a relatively straight-forward Information System, where the business needs can be clearly linked to technological and methodological requirements known in advance of any bidding, the requirements must still be vendor-neutral and admit the widest possible range of technical responses.*

*Accordingly, references to brand names, catalog numbers, or other details that limit the source of any item or component to a specific manufacturer should be avoided. Where such references are unavoidable, the words “or substantially equivalent” should be added to permit Bidders to bid equivalent or superior technologies. (The Purchaser will need to be ready to indicate how this equivalence will be assessed.) Only in the most exceptional circumstances may Bidders be required to offer brand-name items and the equivalency clause be omitted. The IsDB’s consideration for exception requires that:*

*(a) a brand-name component appears to have no equivalent or superior alternative, because: of its unique ability to reliably interoperate with a relatively large base of existing technologies; to conform with the Purchaser’s adopted technological standards; and to offer overwhelming savings in terms of avoided costs for retraining, data conversion, macro / business template redevelopment, etc.;*

*(b) the IsDB has agreed in advance, during project preparation, that such brand-name restrictions are warranted; and*

*(c) such brand-name components are the absolute fewest possible and each component has been explicitly identified in the Bid Data Sheet for ITB 16.3 .*

*Similarly, where national standards or codes of practice are specified, the Purchaser should include a statement that other national or international standards “that are substantially equivalent” will also be acceptable.*

*To help ensure comparable bids and ease Contract execution, the Purchaser’s requirements must be stated as clearly as possible, with minimum room for differing interpretations. Thus, wherever possible, technical requirements should include definitive characteristics and quantifiable measures. If technical characteristics in a specific range, or above or below specific thresholds, are required, then these should be clearly specified. For example, the expandability of a server should be stated as “no less than four processors.” Technical specifications that state only “four processors” create unnecessary uncertainty for Bidders regarding whether or not, for example, a server that could be expanded up to six processor boards would be technically responsive.*

*Quantitative technical specifications must, however, be employed with care. They can dictate technical architectures and, thus, be unnecessarily restrictive. For example, a quantitative requirement for the minimum width of the data path in a processor may be unnecessarily restrictive. Instead, a specification of a required level of standard performance benchmark test is more appropriate, allowing different technical approaches to achieving the Purchaser’s functional and performance objectives. In general, the Purchaser should try to use widely accepted direct measures of performance and functionality whenever possible and carefully review specifications for those that might dictate technical architectures.*

*It is important that the Technical Requirements clearly identify which are mandatory features (for which a bid’s nonconformance might require rejection for non-responsiveness) and which are preferable features that can be included or excluded from a bid at the Bidder’s option. To enhance the clarity of the specifications, Purchasers are advised to use the word “MUST” (in bold capitals) in sentences describing mandatory requirements. A clear requirements numbering scheme is also essential.*

*The following presents a sample outline format for the Technical Requirements Section. This can and should be adapted to meet the Purchaser’s needs for the specific Information System to be procured.*

*Any applicable sustainable procurement/environmental and social sustainability requirements shall be added to the technical requirements.*

*3.0.4 below indicates noise levels and emission standard. Additional requirements as applicable may include, but not limited to, aspects related to the protection of the environment including* *management and safety of hazardous materials, resource efficiency and pollution prevention and management measures*.**Technical Requirements**

## Table of Contents: Technical Requirements

[A. Acronyms Used in The Technical Requirements 130](#_Toc43484901)

[0.1 Acronym Table 130](#_Toc43484902)

[B. Functional, Architectural and Performance Requirements 132](#_Toc43484903)

[1.1 Legal and Regulatory Requirements to be met by the Information System 132](#_Toc43484904)

[1.2 Business Function Requirements to be met by the Information System 132](#_Toc43484905)

[1.3 Architectural Requirements to be met by the Information System 132](#_Toc43484906)

[1.4 Systems Administration and Management Functions Required to be met by the Information System 133](#_Toc43484907)

[1.5 Performance Requirements of the Information System 133](#_Toc43484908)

[C. Service Specifications – Supply & Install Items 134](#_Toc43484909)

[2.1 System Analysis, Design and Customization/Development 134](#_Toc43484910)

[2.2 Software Customization / Development 134](#_Toc43484911)

[2.3 System Integration (to other existing systems) 134](#_Toc43484912)

[2.4 Training and Training Materials 134](#_Toc43484913)

[2.5 Data Conversion and Migration 135](#_Toc43484914)

[2.6 Documentation Requirements 135](#_Toc43484915)

[2.7 Requirements of the Supplier’s Technical Team 135](#_Toc43484916)

[D. Technology Specifications – Supply & Install Items 136](#_Toc43484917)

[3.0 General Technical Requirements 136](#_Toc43484918)

[3.1 Computing Hardware Specifications 137](#_Toc43484919)

[3.2 Network and Communications Specifications 138](#_Toc43484920)

[3.3 Ancillary Hardware Specifications 139](#_Toc43484921)

[3.4 Standard Software Specifications 140](#_Toc43484922)

[3.5 Consumables 140](#_Toc43484923)

[3.6 Other Non-IT Goods 140](#_Toc43484924)

[E. Testing and Quality Assurance Requirements 140](#_Toc43484925)

[4.1 Inspections 140](#_Toc43484926)

[4.2 Pre-commissioning Tests 141](#_Toc43484927)

[4.3 Operational Acceptance Tests 141](#_Toc43484928)

[F. Service Specifications – Recurrent Cost Items 142](#_Toc43484929)

[5.1 Warranty Defect Repair 142](#_Toc43484930)

[5.2 Technical Support 142](#_Toc43484931)

[5.3 Requirements of the Supplier’s Technical Team 142](#_Toc43484932)

A. Acronyms Used in The Technical Requirements

0.1 Acronym Table

**Note**: Compile a table of organizational and technical acronyms used in the Requirements. This can be done, for example, by extending the following table.

|  | Term | Explanation |
| --- | --- | --- |
|  |  |  |
|  | bps | bits per second |
|  | cps | characters per second |
|  | DBMS | Database Management System |
|  | DOS | Disk Operating System |
|  | dpi | dots per inch |
|  | Ethernet | IEEE 802.3 Standard LAN protocol |
|  | GB | gigabyte |
|  | Hz | Hertz (cycles per second) |
|  | IEEE | Institute of Electrical and Electronics Engineers |
|  | ISO | International Standards Organization |
|  | KB | kilobyte |
|  | kVA | Kilovolt ampere |
|  | LAN | Local area network |
|  | lpi | lines per inch |
|  | lpm | lines per minute |
|  | MB | megabyte |
|  | MTBF | Mean time between failures |
|  | NIC | Network interface card |
|  | NOS | Network operating system |
|  | ODBC | Open Database Connectivity |
|  | OLE | Object Linking and Embedding |
|  | OS | Operating system |
|  | PCL | Printer Command Language |
|  | ppm | pages per minute |
|  | PS | PostScript -- Adobe page description language |
|  | RAID | Redundant array of inexpensive disks |
|  | RAM | Random access memory |
|  | RISC | Reduced instruction-set computer |
|  | SCSI | Small Computer System Interface |
|  | SNMP | Simple Network Management Protocol |
|  | SQL | Structured Query Language |
|  | TCP/IP | Transmission Control Protocol / Internet Protocol |
|  | V | Volt |
|  | WLAN | Wireless LAN |

B. Functional, Architectural and Performance Requirements

1.1 Legal and Regulatory Requirements to be met by the Information System

1.1.1 The Information System MUST comply with the following laws and regulations:

1.1.1.1 [as appropriate, summarize: **each relevant legal code and regulations that govern the business processes and procedures that will be automated with the Information System**;]

1.1.1.2 …

**Note**: If appropriate, prepare a subsection with the relevant legal codes and regulations to be included in the Background and Informational Materials and reference these materials.

1.2 Business Function Requirements to be met by the Information System

1.2.1 The Information System MUST support the following business functions

1.2.1.1 [describe, at the appropriate level of detail for the Information System being supplied and installed: **each specific business processes and procedures that will be automated by the Information System**.]

1.2.1.2 …

**Note**: These business process descriptions may be textual as well as presented in a formal system analysis formats (e.g., process model and data model, use-case model, entity-relation diagrams, swim-lane diagrams, etc.)

As appropriate, prepare a subsection for the Background and Informational Materials with samples of existing standardized reports, data entry forms, data formats, data coding schemes, etc. which the Information System will need to implement; reference these materials.

1.3 Architectural Requirements to be met by the Information System

1.3.1 The Information System MUST be supplied and configured to implement the following architecture.

1.3.1.2 Software Architecture: *[specify:* ***features (use diagrams as appropriate)****]*.

1.3.1.2 Hardware Architecture: *[specify:* ***features (use diagrams as appropriate)****]*.

1.4 Systems Administration and Management Functions Required to be met by the Information System

1.4.1 The Information System MUST provide for the following management, administration, and security features at the overall System level in an integrated fashion.

1.4.1.2 Installation, Configuration and Change Management: *[specify:* ***features****]*.

1.4.1.3 Operational Monitoring, Diagnostics, and Troubleshooting: *[specify:* ***features****]*.

1.4.1.4 User Administration and Access Control; User and Usage Monitoring and Audit Trails: *[specify:* ***features****]*

1.4.1.5 System and Information Security and Security Policies: *[specify:* ***features****]*

1.4.1.6 Back-up and Disaster-Recovery: *[specify:* ***features****]*

1.4.1.7 …

1.5 Performance Requirements of the Information System

1.5.1 The Information System MUST reach the following performance levels.

1.5.1.1 [ describe, at the appropriate level of detail for the particular Information System being supplied and installed: **each relevant throughput and/or response times for specific business processes and procedures automated by the System**; also describe: in business process terms, **the relevant conditions under which the System must achieve these performance standards** (e.g., the number of concurrent users, type of transactions, type and quantity of business data that the System must process in achieving these performance standards, etc.)  ]

1.5.1.2 …

**Note**: Whenever feasible, business functions should be stated and used as the basis for performance specifications. Relying solely on technological requirements can inadvertently restrict competition.

C. Service Specifications – Supply & Install Items

2.1 System Analysis, Design and Customization/Development

2.1.1 The Supplier MUST perform the following Analysis and Design activities using a formal system analysis/development methodology with the following key activities and design deliverables.

2.1.1.1 Detailed Analysis: [for example, specify: **System Design Document; System Requirements Specification; Interface Requirements Specification); Software/System Test Descriptions; Software/System Test Plan**, etc.]

2.1.1.2 Physical Design: [for example, specify: **Software Design Description; Interface Design Document; Database Design Document**; etc.]

2.1.1.3 Integrated System: [for example, specify: **User’s Manual; Operations Manual; Source Code; CASE Files;** etc**.]**

2.2 Software Customization / Development

2.1.1 The Supplier MUST perform Software Customization / Development using a formal software development methodology with the following characteristics and/or with the following technologies and/or tools.

2.1.1.1 [for example, describe: **Software Development Method** (e.g., Cascade, Rapid Application Development; **and/or Open Standards** (e.g., Java, XML, etc.); **and/or CASE tools**, etc.]

2.3 System Integration (to other existing systems)

2.3.1 The Supplier MUST perform the following Integration Services [ for example, describe: **existing information systems** (as appropriate, reference the relevant subsection of the Background and Informational Materials Section containing any detailed description of existing systems); and specify: **technical and functional level of integration with the Information System**. ]

2.4 Training and Training Materials

2.4.1 The Supplier MUST provide the following Training Services and Materials.

2.4.1.1 User: [for example, specify: **minimum curricula, modes of training, modes of testing, and training materials for: the introduction to computers, the operation of the relevant equipment incorporated in the System, as well as the operation of the Software applications incorporated in the System;** as appropriate, reference the relevant subsection in the Background and Informational Material Section containing any detailed information regarding the available training facilities; etc.]

2.4.1.2 Technical: [for example, specify: **minimum curricula, modes of training, modes of testing (e.g., certification levels), training materials and training locations for: the key technology and methodology components of the Information System**; etc.]

2.4.1.3 Management: [ for example, specify: **minimum curricula, modes of training, modes of testing, training materials and training locations for: the familiarization with the functionality, technology and methodology components of the Information System, corporate management of information systems**; etc. ]

2.5 Data Conversion and Migration

2.5.1 The Supplier MUST provide services and tools to perform the following Data Conversion and Migration Services: [for example, specify: **volume of data; type, structure, and media of data; timing of conversion; quality assurance and validation methods**; etc.]

2.6 Documentation Requirements

2.6.1 The Supplier MUST prepare and provide the following Documentation.

2.6.1.1 End-User Documents: [ for example, specify: **type(s) of end-user documents; language; content; formats; quality control and revision management; medium; reproduction and distribution methods**; etc. ]

2.6.1.2 Technical Documents: [ for example, specify: **type(s) of technical documents; language; content; formats; quality control and revision management; medium;, reproduction and distribution methods**; etc. ]

2.7 Requirements of the Supplier’s Technical Team

2.7.1 The Supplier MUST maintain a technical team of the following roles and skill levels during the Supply and Installation Activities under the Contract:

2.7.1.1 Project Team Leader: [for example, specify: **education/certifications, years experience in, demonstrated successful experience in,** etc.]

2.7.1.2 *[ specify:* ***Business Area****]* Expert: [ for example, specify: **education/certifications, years’ experience in, demonstrated successful experience in ,**; etc. *]*

2.7.1.3 System Analyst: [for example, specify: **education/certifications, years’ experience in, demonstrated successful experience in,** etc.]

2.7.1.4 Database Expert: [for example, specify: **education/certifications, years’ experience in, demonstrated successful experience in,** etc.]

2.7.1.5 Programming Expert: [for example, specify: **education/certifications, years’ experience in, demonstrated successful experience in,** etc.]

2.7.1.6 System Administration / Security Expert: [for example, specify: **education/certifications, years’ experience in, demonstrated successful experience in,** etc.]

2.7.1.7 Computer Hardware Expert: [for example, specify: **education/certifications, years’ experience in, demonstrated successful experience in,** etc.]

2.7.1.8 Network and Communications Expert: [for example, specify: **education/certifications, years’ experience in, demonstrated successful experience in,** etc.]

2.7.1.9 Training Expert: [for example, specify: **education/certifications, years’ experience in, demonstrated successful experience in,** etc.]

2.7.1.10 Documentation Specialist: [for example, specify: **education/certifications, years’ experience in, demonstrated successful experience in,** etc.]

2.7.1.11 …

D. Technology Specifications – Supply & Install Items

3.0 General Technical Requirements

3.0.1 Language Support: All information technologies must provide support for the [insert: **either national or business language(s) of the end-user(s)**]. Specifically, all display technologies and software must support the ISO [insert: **character set number**] character set and perform sorting according to [insert: **appropriate standard method**].

3.0.2 Electrical Power: All active (powered) equipment must operate on *[specify:* ***voltage range and frequency range****, e.g., 220v +/- 20v, 50Hz +/- 2Hz].* All active equipment must include power plugs standard in [insert: Purchaser’s Country].

3.0.3 Environmental: Unless otherwise specified, all equipment must operate in environments of [ specify, **temperature, humidity, and dust conditions**, e.g., 10-30 degrees centigrade, 20-80 percent relative humidity, and 0-40 grams per cubic meter of dust ].

3.0.4 Safety:

3.0.4.1 Unless otherwise specified, all equipment must operate at noise levels no greater than [insert: **maximum number**, e.g., 55] decibels.

3.0.4.2 All electronic equipment that emits electromagnetic energy must be certified as meeting [insert: **emission standard**, e.g., US FCC class B or END 55022 and END 50082-1], or equivalent, emission standards.

3.1 Computing Hardware Specifications

3.1.1 Processing Unit Type 1: [specify: **name of** **processing unit and technical function** (e.g., Central Database Server)]:

3.1.1.1 Processing unit performance: As configured for the bid, the processing unit MUST, at a minimum,

(a) Achieve [specify:  **standard benchmark test or tests and minimum performance levels**, for example, “SPEC CPU2006 rating”]

(Or, for PCs)

Achieve a minimum performance equal to a score of [specify: **score**] under the benchmark [specify: **benchmark**, for example “Sylmar 2007 Rating”]

(b) Provide input-output performance, as follows [specify: **minimum input-output performance levels** (e.g., data bus transfer rates; standard peripheral interfaces; minimum number of concurrent terminal sessions, etc.)]

3.1.1.2 Processor expandability: [ for example, specify: **minimum acceptable number of processors**; **minimum acceptable levels of performance**; **minimum acceptable degree of expandability for processors** / **performance**, **relative to bid configuration**; **minimum acceptable number of internal Subsystem expansion slots**; etc., ]

3.1.1.3 Processor memory and other storage: [for example, specify:  **main memory; cache memory; disk storage; tape storage; optical drives**; etc.]

Note: If the upgrade requirements over the next few years for processing power, memory, etc., are reasonably well known at the time the bidding documents are to be issued, the Purchaser may wish to incorporate these requirements in the Recurrent Cost Table and possibly include them in the Contract Price. This will subject them to competition and provide a way contractually to control future price increases. This approach reserves for the Purchaser the option of including upgrades in the Contract, even if upgrades are not needed in the end. An SCC needs to be included clarifying how upgrades will be treated in the final Contract.

3.1.1.4 Processing unit fault tolerance: [for example, specify: **error checking; failure detection, prediction, reporting, and management; redundant power supplies and other modules; “hot-swappable modules**”; etc.]

3.1.1.5 Processing unit management features: [for example, specify: **features and supported standards; local and remote management**; etc.]

3.1.1.6 Processing unit input and output devices: [for example, specify: **network interfaces and controllers; display; keyboard; mouse; bar-code, smart-card, and identification-card readers; modems; audio and video interfaces and devices**; etc.]

3.1.1.7 Other processing unit features: [for example, specify: **power-saving features; battery life for portable equipment**; etc.]

3.1.2 Processing Unit Type 2: [specify: **name of** **processing unit and technical function** (e.g., General Purpose Workstation)]:

3.1.2.1 …

3.2 Network and Communications Specifications

3.2.1 Local Area Network:

3.2.1.1 Equipment and software: [for example, specify: as appropriate, for each type of equipment and software: **protocols supported; performance levels; expandability, fault tolerance, administration, management and security features**; etc.]

3.2.1.2 Cabling: [ for example, specify: **cable type(s); topology(ies); cable protectors, channels and other installation standards (e.g., ANSI / EIA / TIA 598); cable labeling schemes, references to premises drawing**s; etc. ]

3.2.2 Wide-Area Network:

3.2.2.1 Equipment and software: [for example, specify: **protocols supported; performance levels; expandability; fault tolerance; administration, management, and security features**; etc.]

3.2.2.2 Telecommunications Services: [ for example, specify: **media; capacity; protocols supported; performance levels; expandability; fault tolerance; administration, management, and security features**; etc. ]

3.2.3 Other Communications Equipment: [for example, specify: **modems; facsimile devices; modem and facsimile servers**, etc.]

3.2.4 Video Conferencing/Congress Equipment:

3.2.5. …

3.3 Ancillary Hardware Specifications

3.3.1 Shared Data Storage Devices: [specify:  **disk; tape; optical storage devices, including capacities, interfaces, hardware-based administration/diagnostics/failover**, etc.]:

3.3.2 Shared Output and Input Devices:

3.3.2.1 General Requirements: Unless otherwise specified, all shared output and input devices must be capable of handling A4 standard sized paper.

3.3.2.2 Printers: [for example, specify: **high-speed, high-quality printer; standard-speed, high-quality printer; high-speed, large-format (A3) printer; color, high-quality printer, video and output devices**; etc.]

3.3.2.3 Scanners: [for example, specify: **scanner resolution; paper- / film-handling features; speed**; etc.]

3.3.3 Power Conditioning Devices:

3.3.3.1 Uninterruptable Power Supplies: [ for example, specify: **output power delivery and duration capacity, power filtering capacity, battery features, interfaces, device management diagnostics and failover features**, etc. ]

3.3.4 Specialized Furnishing/Equipment:

3.3.4.1 Equipment Cabinets/Racks: [for example, specify: **size, capacity, physical access and access control, ventilation and environmental control features**, etc.]

3.3.4.2 Environment Control Equipment: [for example, specify: **air conditioning units; humidity control equipment; etc**.]

3.3.4.3 Physical Access Control Equipment: [for example, specify: **door entry controls; intrusion detection; video surveillance**, etc.]

3.3.4.3 Logical Access Control Equipment: [for example, specify: **secure identity tokens; token readers**, etc.]

3.4 Standard Software Specifications

3.4.1 System Software and System-Management Utilities:

3.4.1.1 Processing unit type 1: [for example, specify: **operating system; back-up, optimization, anti-virus, and other utilities; systems administration, maintenance, and troubleshooting tools**; etc.]

3.4.1.2 Processing unit type 2: [for example, specify: **operating system; back-up, optimization, anti-virus, and other utilities; systems administration, maintenance, and troubleshooting tools**; etc.]

3.4.1.3 Etc...

3.4.2 Networking and Communications Software: [for example, specify: **protocols, media and equipment to be supported; network services, management and administration features; security and failure management features**; etc.]

3.4.3 General-Purpose Software: [for example, specify: **office automation software; programming tools and libraries**; etc.]

3.4.4 Database Software and Development Tools: [for example, specify: **database and database management feature; development tools and environments**; etc.]

3.4.5 Business Application Software: [for example, specify: **specific business functions to be supported in native code; application management feature; customization options and tools**; etc.]

3.5 Consumables

3.5.1 Printer Ink / Toner – Printer Type 1:

3.6 Other Non-IT Goods

3.6.1 Workstation Desks:

3.6.2 Photocopiers:

3.6.3 Specialized Mechanical Systems – Datacenter *[for example, specify:* ***raised floor system, electrical distribution subsystem****, etc.]*

E. Testing and Quality Assurance Requirements

4.1 Inspections

4.1.1 Factory Inspections: [if any, specify:  **the items, criteria, and methods to be employed by the Purchaser, or its agent, during factory inspections of the Information Technologies and other Goods prior to their shipment to the site(s)**.]

4.1.2 Inspections following delivery: [if any, specify:  **the items, criteria, and methods to be employed by the Purchaser, or its agent, upon delivery and unpacking of the Information Technologies and other Goods to the Site(s)**.]

4.2 Pre-commissioning Tests

4.2.0 In addition to the Supplier’s standard check-out and set-up tests, the Supplier (with the assistance of the Purchaser) must perform the following tests on the System and its Subsystems before Installation will be deemed to have occurred and the Purchaser will issue the Installation Certificate(s) (pursuant to GCC Clause 26 and related SCC clauses).

4.2.1 [specify: Subsystem 1 (as defined in the Site Table[s] attached to the Implementation Schedule) specify:  **tests, test conditions, success criteria**, etc.]

4.2.2 [specify: Subsystem 2 (as defined in the Site Table{s}) specify:  **tests, test conditions, success criteria**, etc.]

4.2. N The Entire System: Pre-commissioning Tests for the entire System are: [specify: **tests, test conditions, success criteria**, etc.]

4.3 Operational Acceptance Tests

4.3.0 Pursuant to GCC Clause 27 and related SCC clauses, the Purchaser (with the assistance of the Supplier) will perform the following tests on the System and its Subsystems following Installation to determine whether the System and the Subsystems meet all the requirements mandated for Operational Acceptance.

4.3.1 [specify: Subsystem 1 (as defined in the Implementation Schedule) specify: **tests, test conditions, success criteria**, etc.]

4.3.2 [specify: Subsystem 2 (as defined in the Implementation Schedule) specify: **tests, test conditions, success criteria**, etc.]

4.3. N The Entire System: Pre-commissioning Tests for the entire System are: [specify: **tests, test conditions, success criteria**, etc.]

***Note:*** *The complexity of the Operational Acceptance Testing needed will vary in accordance with the nature and complexity of the System being procured. For simpler Information Systems Operational Acceptance Testing may simply consist of requiring a specified period of trouble-free System or Subsystem operation under normal operating conditions. For more complex Systems, Operational Acceptance testing will require extensive, clearly defined tests under either production or mock-production conditions.*

F. Service Specifications – Recurrent Cost Items

5.1 Warranty Defect Repair

5.1.1 The Supplier MUST provide the following services under the Contract or, as appropriate under separate contracts (as specified in the bidding documents).

5.1.1.1 Warranty Defect Repair Service: [ for example, specify: **coverage period; response time and problem-resolution performance standards; modes of service, such as on-site, on-call, or return to warehouse**; etc. (indicate how these may vary among hardware, software, network technologies, etc.) ]

5.1.1.2 ...

5.2 Technical Support

5.2.1 The Supplier MUST provide the following services under the Contract or, as appropriate under separate contracts (as specified in the bidding documents).

5.2.1.1User support / hot line: [for example, specify: **coverage period; response time and problem resolution performance standards**; etc.]

5.2.1.2 Technical Assistance: [for example, specify: **categories of technical staff required; anticipated tasks and objectives; response-time performance standards**; etc. (indicate how these may vary among hardware, software, network technologies, etc.)]

5.2.1.3 Post-Warranty Maintenance Services: [ for example, specify: **coverage period; response time and problem-resolution performance standards; modes of service, such as on-site, on-call, or return to warehouse**; etc. (indicate how these may vary among hardware, software, network technologies, etc.) ]

5.2.1.4 ….

5.3 Requirements of the Supplier’s Technical Team

5.3.1 The Supplier MUST provide a technical team to cover the Purchaser’s anticipated Post-Operational Acceptance Technical Assistance Activities Requirements (e.g., modification of the Information System to comply with changing legislation and regulations) with the roles and skill levels that are specified below. The minimum expected quantities of inputs by the Supplier’s technical support team are specified in the relevant System Inventory Tables for Recurrent Cost Items.

5.3.1.1 System Analyst: [for example, specify: **education/certifications, years’ experience in, demonstrated successful experience in,** etc.]

5.3.1.2 Database Expert: [for example, specify: **education/certifications, years’ experience in, demonstrated successful experience in,** etc.]

5.3.1.3 Programming Expert: [for example, specify: **education/certifications, years’ experience in, demonstrated successful experience in,** etc.]*.*

5.3.1.4 …

**Note**: The Technical Assistance Team specification may be used to develop bid prices for technical support Recurrent Costs. These may be included in the main Contract or be subject to separate contracts. In either regard, to obtain meaningful and comparable bid prices, the Purchaser will need to specify the roles of the technical support team members in this section and indicate the quantities of the corresponding inputs in the Systems Inventory Tables for Recurrent Cost items.

**Implementation Schedule**

## Notes on preparing the Implementation Schedule

The Implementation Schedule summarize when and where Installation, and Operational Acceptance should take place for all Subsystems and/or major components of the System, and for the overall System itself – as well as any other major Contract milestones.

**Note**: The delivery date is not presented in the Implementation Schedule. Under Incoterms 2010 for CIP, Delivery refers to the date when the Supplier delivers the goods to the first carrier at the port of embarkation, not to the arrival of the goods at the destination site. Delivery (shipment) date therefore varies according to the country of origin of the goods and the Supplier's chosen method of transport.

The target dates need to be realistic and achievable in light of the capacity of both the average Supplier and the Purchaser to carry out their respective contract obligations. Also, the Purchaser must take care to ensure that the dates specified in the Schedule are consistent with any specified elsewhere in the bidding document, especially in the GCC/SCC (e.g., and/or times specified for the submission and acceptance of the Agreed Project Plan).

The work breakdown structure (deliverables) in the Implementation Schedule should be sufficiently detailed to facilitate careful management of the Contract – but not so detailed that it unnecessarily constrains bidders from organizing the proposed work in the most efficient and effective manner.

To facilitate the bidding and the contract management processes, the Implementation Schedule, the System Inventory Tables and Price Schedules should be closely linked. In particular, the Implementation Schedule defines the major deliverable Subsystems. For each Subsystem there should be a corresponding System Inventory Table or Tables. These System Inventory Tables catalog the specific items (inputs) comprising the Subsystem, as well as the quantities of each item required (for the supply and install cost items as well as the recurrent cost items). For each System Inventory Table there should be a corresponding Price Schedule that closely mirrors the System Inventory Table. Careful development of these materials will greatly improve the changes of obtaining complete and comparable bids (and ease the bid evaluation process) as well as improving the likelihood that the Purchaser’s and Supplier’s interactions during contract execution are closely orchestrated (thus easing the burden of contract management and improving the likelihood of successful implementation of the Information System).

The sample tables comprise:

(a) An Implementation Schedule Table;

(b) A Site Table(s); and

(c) A Table of Holidays and other Non-Working Days.

The Purchaser should modify these tables, as required, to suit the particulars of the System (and Subsystems) to be supplied and installed. The sample text in the tables is illustrative only and should be modified or deleted as appropriate.

The timings stated in the Implementation Schedule should be specified in weeks from Contract Effectiveness. This will ease the maintenance of the bidding documents during the preparation and bidding processes.

Where appropriate, the Implementation Schedule should indicate the deliverables against which Liquidated Damages may be applied in the event of implementation delays arising from the actions of the Supplier (as governed by the SCC and GCC clause 28). These milestones should be kept to the essential minimum needed by the Purchaser to ensure contract discipline by the Supplier – but not so many that they unnecessarily strain the Purchaser-Supplier relationship upon which the successful implementation of the Information System will invariably depend.

The Site Table(s) catalog the physical location of the site(s) where the System is to be supplied, installed, and operated. The site(s) may consist of a number of branch offices in remote regions, different departments or offices in the same city, or a combination of these. The Purchaser must specify this information in sufficient detail so that Bidders can accurately estimate costs related to:

(a) Delivery and insurance;

(b) Installation, including cabling and inter-building communications, etc.

(c) Perform support services, such as warranty defect repair, maintenance, and other technical support services; and

(d) Other related Service obligations the successful Bidder will have to perform under the Contract, including related travel and subsistence costs.

This information will also help Bidders identify which site(s) may warrant a site visit during the period they are preparing their bids. If the System presents complex installation challenges, site layout drawings should be included in the Background and Informational Materials Section.

## Table of Contents: Implementation Schedule

[A. Implementation Schedule Table 147](#_Toc454958754)

[B. Site Table(s) 148](#_Toc454958755)

[C. Table of Holidays and Other Non-Working Days 149](#_Toc454958756)

A. Implementation Schedule Table

[Specify **desired installation and acceptance dates for all items in Schedule below, modifying the sample line items and sample table entries as needed.**]

| Line Item No. | Subsystem / Item | Configuration Table No. | Site / Site Code | Delivery (Bidder to specify in the Preliminary Project Plan) | Installation (weeks from Effective Date) | Acceptance (weeks from Effective Date) | Liquidated Damages Milestone |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |
| 0 | Project Plan | - - | - - |  | - - | W\_ | no |
|  |  |  |  |  |  |  |  |
| 1 | Subsystem 1 | 1 | \_\_\_ |  | - - | - - | - - |
| : | etc. |  |  |  |  |  |  |
| x | Operational Acceptance of the System as an integrated whole | - - | all sites |  | - - | W\_\_ | yes |
|  |  |  |  |  |  |  |  |
| y | Recurrent Cost Items – Warranty Period | y | - - |  |  |  |  |

**Note:** Refer to the System Inventory Table(s) for the specific items and components that constitute the Subsystems or item. Refer to the Site Table(s) below for details regarding the site and the site code.

- - indicates not applicable. “Indicates repetition of table entry above.

B. Site Table(s)

[Specify: **the detailed information regarding the site(s) at which the System is to be operated**]

| Site Code | Site | City / Town / Region | Primary Street Address | Drawing Reference No. (if any) |
| --- | --- | --- | --- | --- |
| HQ | Headquarters |  |  |  |
|  |  |  |  |  |
| R1 | Region 1 |  |  |  |
| R1.1 | Region 1 Head Office |  |  |  |
| R1.2 | ABC Branch Office |  |  |  |
| R1.3 | DEF Branch Office |  |  |  |
|  |  |  |  |  |

C. Table of Holidays and Other Non-Working Days

[Specify: **the days for each month for each year that are non-working days, due to Holidays or other business reasons (other than weekends).**]

| Month | 20xy | 20xy+1 | 20xy+2 | .... |  |  | ... | 20zz |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |  |

**System Inventory Tables**

## Notes on preparing the System Inventory Tables

The System Inventory Tables detail:

(a) for each Subsystem (Deliverable) indicated in the Implementation Schedule, the Information Technologies, Materials, and other Goods and Services that comprise the System to be supplied and/or performed by the Supplier;

(b) the quantities of such Information Technologies, Materials, and other Goods and Services;

(c) the sites and the location of each on a specific site (e.g., building, floor, room, department, etc.)

(d) the cross references to the relevant section of the Technical Requirements where that item is described in greater detail

The Purchaser should modify these tables, as required, to suit the particulars of the System (and Subsystems) to be supplied and installed. The sample text provided for various sections of the tables is illustrative only and should be modified or deleted as appropriate.

There are two sample formats given for the System Inventory Tables: one for the Supply and Installation cost items and the second for Recurrent Cost Items needed (if any). The second version of the table permits the Purchaser to obtain price information about items that are needed during the Warranty Period.

## Table of Contents: System Inventory Tables

[System Inventory Table (Supply and Installation Cost Items)  *[ insert: identifying number ]* 159](#_Toc448759416)

[System Inventory Table (Recurrent Cost Items) *[ insert: identifying number ] – Warranty Period* 160](#_Toc448759417)

System Inventory Table (Supply and Installation Cost Items)  *[ insert: identifying number ]*

Line item number: [ specify: relevant line item number from the Implementation Schedule (e.g., 1.1) ]

[ as necessary for the supply and installation of the System, specify: **the detailed components and quantities in the System Inventory Table below for the line item specified above, modifying the sample components and sample table entries as needed.** Repeat the System Inventory Table as needed to cover each and every line item in the Implementation Schedule that requires elaboration. ]

| Component  No. | Component | Relevant Technical Specifications  No. | Additional Site Information (e.g., building, floor, department, etc.) | Quantity |
| --- | --- | --- | --- | --- |
|  |  |  |  |  |
| 1. | Subsystem 1 |  | - - | - - |
| 1.1 | \_\_\_\_\_\_\_\_\_ |  |  | - - |
| : |  |  |  |  |
| 2. | Subsystem 2 |  |  | - - |
| 2.1 | \_\_\_\_\_\_\_\_\_\_\_ |  |  | - - |
| : |  |  |  |  |
|  |  |  |  |  |

**Note:** - - indicates not applicable. “ indicates repetition of table entry above.

System Inventory Table (Recurrent Cost Items) *[ insert: identifying number ] –*

Line item number: [ specify: **relevant line item number from the Implementation Schedule (e.g., y.1)** ]

| Component  No. | Component | Relevant Technical Specifications No. | Y1 | Y2 | Y3 |
| --- | --- | --- | --- | --- | --- |
| 1. | Warranty Defect Repair |  | all items, all sites, included in the Supply and Install Price | all items, all sites, included in the Supply and Install Price | all items, all sites, included in the Supply and Install Price |
| 2. | Software/Firmware Licenses and Updates: |  | all items, all sites, included in the Supply and Install Price | all items, all sites, included in the Supply and Install Price | all items, all sites, included in the Supply and Install Price |
| 3. | Technical Services |  |  |  |  |
| 3.1 | Sr. Systems Analyst |  | 80 days | 40 days | 20 days |
| 3.2 | Sr. Programmer |  | 20 days | 40 days | 60 days |
| 3.3 | Sr. Network Specialist, …. etc. |  | - - | 20 days | 20 days |
|  | … |  |  |  |  |

**Note:** - - indicates not applicable. “ indicates repetition of table entry above.

**Background and Informational Materials**

## Notes on Background and Informational Materials

This section of the bidding document provides a place to gather materials that the Purchaser believes will help Bidders prepare more precisely targeted technical bids and more precise bid prices.

These materials MUST NOT introduce requirements for the Information System. Rather they should assist Bidders to interpret the Technical Requirements and the General and Specific Conditions of Contract. For example, these Background and Informational Materials may describe existing information systems that the Information System to be supplied and installed under the Contract must integrate with. However, the specific requirement that the Supplier must integrate the Information System with other systems needs to be stated in the Technical Requirements. Similarly, these Background and Informational Materials may describe the legal and regulatory norms (including for example statutory report formats) that are relevant to the Information System. The Technical Requirements Section would need to spell out that the Supplier must ensure the Information System complies with the relevant legal and regulatory norms.

## Table of Contents: Background and Informational Materials

A. Background 157

0.1 The Purchaser 157

0.2 The Purchaser’s Business Objectives for the Information System 157

B. Informational Materials 157

0.3 The Legal, Regulatory, and Normative Context for the Information System 157

0.4 Existing Information Systems / Information Technologies Relevant to the Information System 157

0.5 Available Training Facilities to Support the Implementation of the Information System 158

0.6 Site Drawings and Site Survey Information Relevant to the Information System 158

**Background and Informational Materials**

***Note****: The following is only a sample outline. Entries should be modified, extended, and/or deleted, as appropriate for the particular System to be supplied and installed. DO NOT introduce requirements for the System in this section.*

A. Background

0.1 The Purchaser

0.1.1 [ provide: an overview of the Agency’s legal basis, organizational role, and core objectives ]

0.1.2 [ provide: an overview of the stakeholders to the Information System

0.1.3 [ provide: an overview of the Purchaser’s project management and decision-making arrangements applicable to the System and performance of the Contract ]

0.2 The Purchaser’s Business Objectives for the Information System

0.2.1 [ provide: an overview of the current business objectives, procedures, and processes and how they will be affected by the System ]

0.2.2 [ provide: an overview of the changes in objectives, procedures, and processes to be made possible by the System ]

0.2.3 [ provide: a brief description of the expected benefits of the System ]

B. Informational Materials

0.3 The Legal, Regulatory, and Normative Context for the Information System

0.3.1 [ provide: an overview of the laws, regulations and other formal norm which will shape the Information System. ]

0.3.2 [ provide: samples of existing standardized reports, data entry forms, data formats, data coding schemes, etc. which the Information System will need to implement.  ]

0.4 Existing Information Systems / Information Technologies Relevant to the Information System

0.4.1 [ provide: an overview of the existing information systems and information technologies which will establish the technological context for the implementation of the Information System. ]

0.4.2 [ provide: an overview of the ongoing or planned information systems initiatives that will shape context for the implementation of the Information System. ]

0.5 Available Training Facilities to Support the Implementation of the Information System

0.5.1 [ provide: an overview of the Purchaser’s existing training facilities that would be available to support the implementation of the Information System. ]

0.6 Site Drawings and Site Survey Information Relevant to the Information System

0.6.1 [ provide: information of the sites at which the Information System would be implemented. ]

PART 3 – Conditions of Contract and Contract Forms

Section VIII - General Conditions of Contract

## Table of Clauses

[A. Contract and Interpretation 163](#_Toc43484780)

[1. Definitions 163](#_Toc43484781)

[2. Contract Documents 171](#_Toc43484782)

[3. Interpretation 171](#_Toc43484783)

[4. Notices 173](#_Toc43484784)

[5. Governing Law 174](#_Toc43484785)

[6. Fraud and Corruption 175](#_Toc43484786)

[B. Subject Matter of Contract 175](#_Toc43484787)

[7. Scope of the System 175](#_Toc43484788)

[8. Time for Commencement and Operational Acceptance 176](#_Toc43484789)

[9. Supplier’s Responsibilities 176](#_Toc43484790)

[10. Purchaser’s Responsibilities 182](#_Toc43484791)

[C. Payment 184](#_Toc43484792)

[11. Contract Price 184](#_Toc43484793)

[12. Terms of Payment 184](#_Toc43484794)

[13. Securities 185](#_Toc43484795)

[14. Taxes and Duties 186](#_Toc43484796)

[D. Intellectual Property 187](#_Toc43484797)

[15. Copyright 187](#_Toc43484798)

[16. Software License Agreements 188](#_Toc43484799)

[17. Confidential Information 190](#_Toc43484800)

[E. Supply, Installation, Testing, Commissioning, and Acceptance of the System 191](#_Toc43484801)

[18. Representatives 191](#_Toc43484802)

[19. Project Plan 194](#_Toc43484803)

[20. Subcontracting 196](#_Toc43484804)

[21. Design and Engineering 197](#_Toc43484805)

[22. Procurement, Delivery, and Transport 199](#_Toc43484806)

[23. Product Upgrades 202](#_Toc43484807)

[24. Implementation, Installation, and Other Services 203](#_Toc43484808)

[25. Inspections and Tests 203](#_Toc43484809)

[26. Installation of the System 204](#_Toc43484810)

[27. Commissioning and Operational Acceptance 205](#_Toc43484811)

[F. Guarantees and Liabilities 209](#_Toc43484812)

[28. Operational Acceptance Time Guarantee 209](#_Toc43484813)

[29. Defect Liability 210](#_Toc43484814)

[30. Functional Guarantees 213](#_Toc43484815)

[31. Intellectual Property Rights Warranty 213](#_Toc43484816)

[32. Intellectual Property Rights Indemnity 214](#_Toc43484817)

[33. Limitation of Liability 216](#_Toc43484818)

[G. Risk Distribution 217](#_Toc43484819)

[34. Transfer of Ownership 217](#_Toc43484820)

[35. Care of the System 217](#_Toc43484821)

[36. Loss of or Damage to Property; Accident or Injury to Workers; Indemnification 219](#_Toc43484822)

[37. Insurances 220](#_Toc43484823)

[38. Force Majeure 222](#_Toc43484824)

[H. Change in Contract Elements 224](#_Toc43484825)

[39. Changes to the System 224](#_Toc43484826)

[40. Extension of Time for Achieving Operational Acceptance 229](#_Toc43484827)

[41. Termination 229](#_Toc43484828)

[42. Assignment 236](#_Toc43484829)

[I. Settlement of Disputes 237](#_Toc43484830)

[43. Settlement of Disputes 237](#_Toc43484831)

**General Conditions of Contract**

A. Contract and Interpretation

|  |  |  |
| --- | --- | --- |
| 1. Definitions | | 1.1 In this Contract, the following terms shall have the meaning as indicated below. |
|  | | (a) contract elements  (i) “Contract” means the Contract Agreement entered into between the Purchaser and the Supplier, together with the Contract Documents referred to therein. The Contract Agreement and the Contract Documents shall constitute the Contract, and the term “the Contract” shall in all such documents be construed accordingly.  (ii) “Contract Documents” means the documents specified in Article 1.1 (Contract Documents) of the Contract Agreement (including any amendments to these Documents).  (iii) “Contract Agreement” means the agreement entered into between the Purchaser and the Supplier using the form of Contract Agreement contained in the Sample Contractual Forms Section of the bidding documents and any modifications to this form agreed to by the Purchaser and the Supplier. The date of the Contract Agreement shall be recorded in the signed form.  (iv) “GCC” means the General Conditions of Contract.  (v) “SCC” means the Special Conditions of Contract.  (vi) “Technical Requirements” means the Technical Requirements in Section VII of the bidding documents.  (vii) “Implementation Schedule” means the Implementation Schedule in Section VII of the bidding documents.  (viii) “Contract Price” means the price or prices defined in Article 2 (Contract Price and Terms of Payment) of the Contract Agreement.  (ix) “Procurement Guidelines” refers to the edition **specified in the SCC** of the Guidelines for Procurement of Goods, Works and related services under Islamic Development Project Financing.  (x) “bidding documents” refers to the collection of documents issued by the Purchaser to instruct and inform potential suppliers of the processes for bidding, selection of the winning bid, and Contract formation, as well as the contractual conditions governing the relationship between the Purchaser and the Supplier. The General and Special Conditions of Contract, the Technical Requirements, and all other documents included in the bidding documents reflect the Procurement Guidelines that the Purchaser is obligated to follow during procurement and administration of this Contract.  (xi) Sexual Exploitation and Abuse” “(SEA)” means the following:  Sexual Exploitation is defined as any actual or attempted abuse of position of vulnerability, differential power or trust, for sexual purposes, including, but not limited to, profiting monetarily, socially or politically from the sexual exploitation of another.  Sexual Abuse is defined as the actual or threatened physical intrusion of a sexual nature, whether by force or under unequal or coercive conditions.  (xii)“Sexual Harassment” “(SH)” is defined as unwelcome sexual advances, requests for sexual favors, and other verbal or physical conduct of a sexual nature by the Supplier’s or its Subcontractors’ personnel with other Supplier’s, Subcontractors’ or Purchaser’s personnel. |
|  | | (b) entities  (i) “Purchaser” means the entity purchasing the Information System, as **specified in the SCC.**  (ii) “Project Manager” means the person **named as such in the SCC** or otherwise appointed by the Purchaser in the manner provided in GCC Clause 18.1 (Project Manager) to perform the duties delegated by the Purchaser.  (iii) “Supplier” means the firm or Joint Venture whose bid to perform the Contract has been accepted by the Purchaser and is named as such in the Contract Agreement.  (iv) “Supplier’s Representative” means any person nominated by the Supplier and named as such in the Contract Agreement or otherwise approved by the Purchaser in the manner provided in GCC Clause 18.2 (Supplier’s Representative) to perform the duties delegated by the Supplier.  (v) “Subcontractor” means any firm to whom any of the obligations of the Supplier, including preparation of any design or supply of any Information Technologies or other Goods or Services, is subcontracted directly or indirectly by the Supplier.  (vi) “Adjudicator” means the person named in Appendix 2 of the Contract Agreement, appointed by agreement between the Purchaser and the Supplier to make a decision on or to settle any dispute between the Purchaser and the Supplier referred to him or her by the parties, pursuant to GCC Clause 43.1 (Adjudication).  (vii) “The Bank” or “IsDB” means the Islamic Development Bank”. |
|  | | (c) scope  (i) “Information System,” also called “the System,” means all the Information Technologies, Materials, and other Goods to be supplied, installed, integrated, and made operational (exclusive of the Supplier’s Equipment), together with the Services to be carried out by the Supplier under the Contract.  (ii) “Subsystem” means any subset of the System identified as such in the Contract that may be supplied, installed, tested, and commissioned individually before Commissioning of the entire System.  (iii) “Information Technologies” means all information processing and communications-related hardware, Software, supplies, and consumable items that the Supplier is required to supply and install under the Contract.  (iv) “Goods” means all equipment, machinery, furnishings, Materials, and other tangible items that the Supplier is required to supply or supply and install under the Contract, including, without limitation, the Information Technologies and Materials, but excluding the Supplier’s Equipment.  (v) “Services” means all technical, logistical, management, and any other Services to be provided by the Supplier under the Contract to supply, install, customize, integrate, and make operational the System. Such Services may include, but are not restricted to, activity management and quality assurance, design, development, customization, documentation, transportation, insurance, inspection, expediting, site preparation, installation, integration, training, data migration, Pre-commissioning, Commissioning, maintenance, and technical support.  (vi) “The Project Plan” means the document to be developed by the Supplier and approved by the Purchaser, pursuant to GCC Clause 19, based on the requirements of the Contract and the Preliminary Project Plan included in the Supplier’s bid. The “Agreed Project Plan” is the version of the Project Plan approved by the Purchaser, in accordance with GCC Clause 19.2. Should the Project Plan conflict with the Contract in any way, the relevant provisions of the Contract, including any amendments, shall prevail.  (vii) “Software” means that part of the System which are instructions that cause information processing Subsystems to perform in a specific manner or execute specific operations.  (viii) “System Software” means Software that provides the operating and management instructions for the underlying hardware and other components, and is identified as such in Appendix 4 of the Contract Agreement and such other Software as the parties may agree in writing to be Systems Software. Such System Software includes, but is not restricted to, micro-code embedded in hardware (i.e., “firmware”), operating systems, communications, system and network management, and utility software.  (ix) “General-Purpose Software” means Software that supports general-purpose office and software development activities and is identified as such in Appendix 4 of the Contract Agreement and such other Software as the parties may agree in writing to be General- Purpose Software. Such General-Purpose Software may include, but is not restricted to, word processing, spreadsheet, generic database management, and application development software.  (x) “Application Software” means Software formulated to perform specific business or technical functions and interface with the business or technical users of the System and is identified as such in Appendix 4 of the Contract Agreement and such other Software as the parties may agree in writing to be Application Software.  (xi) “Standard Software” means Software identified as such in Appendix 4 of the Contract Agreement and such other Software as the parties may agree in writing to be Standard Software.  (xii) “Custom Software” means Software identified as such in Appendix 4 of the Contract Agreement and such other Software as the parties may agree in writing to be Custom Software.  (xiii) “Source Code” means the database structures, dictionaries, definitions, program source files, and any other symbolic representations necessary for the compilation, execution, and subsequent maintenance of the Software (typically, but not exclusively, required for Custom Software).  (xiv) “Materials” means all documentation in printed or printable form and all instructional and informational aides in any form (including audio, video, and text) and on any medium, provided to the Purchaser under the Contract.  (xv) “Standard Materials” means all Materials not specified as Custom Materials.  (xvi) “Custom Materials” means Materials developed by the Supplier at the Purchaser’s expense under the Contract and identified as such in Appendix 5 of the Contract Agreement and such other Materials as the parties may agree in writing to be Custom Materials. Custom Materials includes Materials created from Standard Materials.  (xvii) “Intellectual Property Rights” means any and all copyright, moral rights, trademark, patent, and other intellectual and proprietary rights, title and interests worldwide, whether vested, contingent, or future, including without limitation all economic rights and all exclusive rights to reproduce, fix, adapt, modify, translate, create derivative works from, extract or re-utilize data from, manufacture, introduce into circulation, publish, distribute, sell, license, sublicense, transfer, rent, lease, transmit or provide access electronically, broadcast, display, enter into computer memory, or otherwise use any portion or copy, in whole or in part, in any form, directly or indirectly, or to authorize or assign others to do so.  (xviii) “Supplier’s Equipment” means all equipment, tools, apparatus, or things of every kind required in or for installation, completion and maintenance of the System that are to be provided by the Supplier, but excluding the Information Technologies, or other items forming part of the System. |
|  | | (d) activities  (i) “Delivery” means the transfer of the Goods from the Supplier to the Purchaser in accordance with the current edition Incoterms specified in the Contract.  (ii) “Installation” means that the System or a Subsystem as specified in the Contract is ready for Commissioning as provided in GCC Clause 26 (Installation).  (iii) “Pre-commissioning” means the testing, checking, and any other required activity that may be specified in the Technical Requirements that are to be carried out by the Supplier in preparation for Commissioning of the System as provided in GCC Clause 26 (Installation).  (iv) “Commissioning” means operation of the System or any Subsystem by the Supplier following Installation, which operation is to be carried out by the Supplier as provided in GCC Clause 27.1 (Commissioning), for the purpose of carrying out Operational Acceptance Test(s).  (v) “Operational Acceptance Tests” means the tests specified in the Technical Requirements and Agreed Project Plan to be carried out to ascertain whether the System, or a specified Subsystem, is able to attain the functional and performance requirements specified in the Technical Requirements and Agreed Project Plan, in accordance with the provisions of GCC Clause 27.2 (Operational Acceptance Test).  (vi) “Operational Acceptance” means the acceptance by the Purchaser of the System (or any Subsystem(s) where the Contract provides for acceptance of the System in parts), in accordance with GCC Clause 27.3 (Operational Acceptance). |
|  | | (e) place and time  (i) “Purchaser’s Country” is the **country named in the SCC.**  (ii) “Supplier’s Country” is the country in which the Supplier is legally organized, as named in the Contract Agreement.  (iii) **Unless otherwise specified in the SCC** “Project Site(s)” means the place(s) in the Site Table in the Technical Requirements Section for the supply and installation of the System.  (iv) “Eligible Country” means the countries and territories eligible for participation in procurements financed by the IsDB as defined in the Procurement Guidelines.  (v) “Day” means calendar day of the Gregorian Calendar.  (vi) “Week” means seven (7) consecutive Days, beginning the day of the week as is customary in the Purchaser’s Country.  (vii) “Month” means calendar month of the Gregorian Calendar.  (viii) “Year” means twelve (12) consecutive Months.  (ix) “Effective Date” means the date of fulfillment of all conditions specified in Article 3 (Effective Date for Determining Time for Achieving Operational Acceptance) of the Contract Agreement, for the purpose of determining the Delivery, Installation, and Operational Acceptance dates for the System or Subsystem(s).  (x) “Contract Period” is the time period during which this Contract governs the relations and obligations of the Purchaser and Supplier in relation to the System, as **unless otherwise specified in the SCC,** the Contract shall continue in force until, unless the Contract is terminated earlier in accordance with the terms set out in the Contract**.**  (xi) “Defect Liability Period” (also referred to as the “Warranty Period”) means the period of validity of the warranties given by the Supplier commencing at date of the Operational Acceptance Certificate of the System or Subsystem(s), during which the Supplier is responsible for defects with respect to the System (or the relevant Subsystem[s]) as provided in GCC Clause 29 (Defect Liability).  (xii) “The Coverage Period” means the Days of the Week and the hours of those Days during which maintenance, operational, and/or technical support services (if any) must be available.  (xiii) The Post-Warranty Services Period” means the number of years **defined in the SCC** (if any), following the expiration of the Warranty Period during which the Supplier may be obligated to provide Software licenses, maintenance, and/or technical support services for the System, either under this Contract or under separate contract(s). |
| 2. Contract Documents | | 2.1 Subject to Article 1.2 (Order of Precedence) of the Contract Agreement, all documents forming part of the Contract (and all parts of these documents) are intended to be correlative, complementary, and mutually explanatory. The Contract shall be read as a whole. |
| 3. Interpretation | | 3.1 Governing Language |
|  | | 3.1.1 **Unless otherwise specified in the SCC**, all Contract Documents and related correspondence exchanged between Purchaser and Supplier shall be written in the language of these bidding documents (English)**,** and the Contract shall be construed and interpreted in accordance with that language.  3.1.2 If any of the Contract Documents or related correspondence are prepared in a language other than the governing language under GCC Clause 3.1.1 above, the translation of such documents into the governing language shall prevail in matters of interpretation. The originating party, with respect to such documents shall bear the costs and risks of such translation.  3.2 Singular and Plural  The singular shall include the plural and the plural the singular, except where the context otherwise requires.  3.3 Headings  The headings and marginal notes in the GCC are included for ease of reference and shall neither constitute a part of the Contract nor affect its interpretation.  3.4 Persons  Words importing persons or parties shall include firms, corporations, and government entities.  3.5 Incoterms  Unless inconsistent with any provision of the Contract, the meaning of any trade term and the rights and obligations of parties thereunder shall be as prescribed by the Incoterms  Incoterms means international rules for interpreting trade terms published by the International Chamber of Commerce (latest edition), 38 Cours Albert 1er, 75008 Paris, France.  3.6 Entire Agreement  The Contract constitutes the entire agreement between the Purchaser and Supplier with respect to the subject matter of Contract and supersedes all communications, negotiations, and agreements (whether written or oral) of parties with respect to the subject matter of the Contract made prior to the date of Contract.  3.7 Amendment  No amendment or other variation of the Contract shall be effective unless it is in writing, is dated, expressly refers to the Contract, and is signed by a duly authorized representative of each party to the Contract.  3.8 Independent Supplier  The Supplier shall be an independent contractor performing the Contract. The Contract does not create any agency, partnership, joint venture, or other joint relationship between the parties to the Contract.  Subject to the provisions of the Contract, the Supplier shall be solely responsible for the manner in which the Contract is performed. All employees, representatives, or Subcontractors engaged by the Supplier in connection with the performance of the Contract shall be under the complete control of the Supplier and shall not be deemed to be employees of the Purchaser, and nothing contained in the Contract or in any subcontract awarded by the Supplier shall be construed to create any contractual relationship between any such employees, representatives, or Subcontractors and the Purchaser.  3.9 Joint Venture  If the Supplier is a Joint Venture of two or more firms, all such firms shall be jointly and severally bound to the Purchaser for the fulfillment of the provisions of the Contract and shall designate one of such firms to act as a leader with authority to bind the Joint Venture. The composition or constitution of the Joint Venture shall not be altered without the prior consent of the Purchaser.  3.10 Nonwaiver  3.10.1 Subject to GCC Clause 3.10.2 below, no relaxation, forbearance, delay, or indulgence by either party in enforcing any of the terms and conditions of the Contract or the granting of time by either party to the other shall prejudice, affect, or restrict the rights of that party under the Contract, nor shall any waiver by either party of any breach of Contract operate as waiver of any subsequent or continuing breach of Contract.  3.10.2 Any waiver of a party’s rights, powers, or remedies under the Contract must be in writing, must be dated and signed by an authorized representative of the party granting such waiver, and must specify the right and the extent to which it is being waived.  3.11 Severability  If any provision or condition of the Contract is prohibited or rendered invalid or unenforceable, such prohibition, invalidity, or unenforceability shall not affect the validity or enforceability of any other provisions and conditions of the Contract.  3.12 Country of Origin  “Origin” means the place where the Information Technologies, Materials, and other Goods for the System were produced or from which the Services are supplied. Goods are produced when, through manufacturing, processing, Software development, or substantial and major assembly or integration of components, a commercially recognized product results that is substantially different in basic characteristics or in purpose or utility from its components. The Origin of Goods and Services is distinct from the nationality of the Supplier and may be different. |
| 4. Notices | | 4.1 Unless otherwise stated in the Contract, all notices to be given under the Contract shall be in writing and shall be sent, pursuant to GCC Clause 4.3 below, by personal delivery, airmail post, special courier, facsimile, electronic mail, or Electronic Data Interchange (EDI), in accordance with the following provisions. |
|  | | 4.1.1 Any notice sent by facsimile, electronic mail, or EDI shall be confirmed within two (2) days after dispatch by notice sent by airmail post or special courier, except as otherwise specified in the Contract.  4.1.2 Any notice sent by airmail post or special courier shall be deemed (in the absence of evidence of earlier receipt) to have been delivered ten (10) days after dispatch. In proving the fact of dispatch, it shall be sufficient to show that the envelope containing such notice was properly addressed, stamped, and conveyed to the postal authorities or courier service for transmission by airmail or special courier.  4.1.3 Any notice delivered personally or sent by facsimile, electronic mail, or EDI shall be deemed to have been delivered on the date of its dispatch.  4.1.4 Either party may change its postal, facsimile, electronic mail, or EDI addresses for receipt of such notices by ten (10) days’ notice to the other party in writing.  4.2 Notices shall be deemed to include any approvals, consents, instructions, orders, certificates, information and other communication to be given under the Contract.  4.3 Pursuant to GCC Clause 18, notices from/to the Purchaser are normally given by, or addressed to, the Project Manager, while notices from/to the Supplier are normally given by, or addressed to, the Supplier's Representative, or in its absence its deputy if any. If there is no appointed Project Manager or Supplier's Representative (or deputy), or if their related authority is limited by the SCC for GCC Clauses 18.1 or 18.2.2, or for any other reason, the Purchaser or Supplier may give and receive notices at their fallback addresses. The address of the Project Manager and the fallback address of the Purchaser are as **specified in the SCC** or as subsequently established/amended. The address of the Supplier's Representative and the fallback address of the Supplier are as specified in Appendix 1 of the Contract Agreement or as subsequently established/amended. |
| 5. Governing Law | | 5.1 The Contract shall be governed by and interpreted in accordance with the laws of the country **specified in the SCC**.  5.2 Throughout the execution of the Contract and when importing from a country, the Supplier shall comply with the import of goods and services prohibitions in the Purchaser’s Country when  (a) as a matter of law or official regulations, the Beneficiary’s country prohibits commercial relations with that country; or  (b) by the Boycott Regulations of the Organization of the Islamic Cooperation, the League of Arab States and the African Union, the Beneficiary’s Country prohibits any import of goods from that country or any payments to any country, person, or entity in that country. |
| 6. Fraud and Corruption | | 6.1 The IsDB requires compliance with its policy in regard to corrupt and fraudulent practices, as set forth in the Appendix to the GCC.  6.2 The Purchaser requires the Suppliers to disclose any commissions or fees that may have been paid or are to be paid to agents or any other party with respect to the bidding process or execution of the Contract. The information disclosed must include at least the name and address of the agent or other party, the amount and currency, and the purpose of the commission, gratuity or fee. | | |

B. Subject Matter of Contract

|  |  |
| --- | --- |
| 7. Scope of the System | 7.1 Unless otherwise expressly **limited in the SCC** or Technical Requirements, the Supplier’s obligations cover the provision of all Information Technologies, Materials and other Goods as well as the performance of all Services required for the design, development, and implementation (including procurement, quality assurance, assembly, associated site preparation, Delivery, Pre-commissioning, Installation, Testing, and Commissioning) of the System, in accordance with the plans, procedures, specifications, drawings, codes, and any other documents specified in the Contract and the Agreed Project Plan. |
|  | 7.2 The Supplier shall, unless specifically excluded in the Contract, perform all such work and / or supply all such items and Materials not specifically mentioned in the Contract but that can be reasonably inferred from the Contract as being required for attaining Operational Acceptance of the System as if such work and / or items and Materials were expressly mentioned in the Contract.  7.3 The Supplier’s obligations (if any) to provide Goods and Services as implied by the Recurrent Cost tables of the Supplier’s bid, such as consumables, spare parts, and technical services (e.g., maintenance, technical assistance, and operational support), are as **specified in the SCC,** including the relevant terms, characteristics, and timings. |
| 8. Time for Commencement and Operational Acceptance | 8.1 The Supplier shall commence work on the System within the period **specified in the SCC,** and without prejudice to GCC Clause 28.2, the Supplier shall thereafter proceed with the System in accordance with the time schedule specified in the Implementation Schedule and any refinements made in the Agreed Project Plan. |
|  | 8.2 The Supplier shall achieve Operational Acceptance of the System (or Subsystem(s) where a separate time for Operational Acceptance of such Subsystem(s) is specified in the Contract) in accordance with the time schedule specified in the Implementation Schedule and any refinements made in the Agreed Project Plan, or within such extended time to which the Supplier shall be entitled under GCC Clause 40 (Extension of Time for Achieving Operational Acceptance). |
| 9. Supplier’s Responsibilities | 9.1 The Supplier shall conduct all activities with due care and diligence, in accordance with the Contract and with the skill and care expected of a competent provider of information technologies, information systems, support, maintenance, training, and other related services, or in accordance with best industry practices. In particular, the Supplier shall provide and employ only technical personnel who are skilled and experienced in their respective callings and supervisory staff who are competent to adequately supervise the work at hand. The Supplier shall ensure that its Subcontractors carryout the work on the Information System in accordance with the Contract, including complying with relevant environmental and social requirements and the obligations set out in GCC Clause 9.9. |
|  | 9.2 The Supplier confirms that it has entered into this Contract on the basis of a proper examination of the data provided by the Purchaser in relation to the System and on the basis of information that the Supplier could have obtained from a visual inspection of the site (if applicable) and of other data readily available to the Supplier relating to the System as at the date twenty-eight (28) days prior to bid submission. The Supplier acknowledges that any failure to acquaint itself with all such data and information shall not relieve its responsibility for properly estimating the difficulty or cost of successfully performing the Contract.  9.3 The Supplier shall be responsible for timely provision of all resources, information, and decision making under its control that are necessary to reach a mutually Agreed Project Plan (pursuant to GCC Clause 19.2) within the time schedule specified in the Implementation Schedule. Failure to provide such resources, information, and decision-making may constitute grounds for termination pursuant to GCC Clause 41.2. |
|  | 9.4 The Supplier shall acquire in its name all permits, approvals, and/or licenses from all local, state, or national government authorities or public service undertakings in the Purchaser’s Country that are necessary for the performance of the Contract, including, without limitation, visas for the Supplier’s and Subcontractor’s personnel and entry permits for all imported Supplier’s Equipment. The Supplier shall acquire all other permits, approvals, and/or licenses that are not the responsibility of the Purchaser under GCC Clause 10.4 and that are necessary for the performance of the Contract.  9.5 The Supplier shall comply with all laws in force in the Purchaser’s Country. The laws will include all national, provincial, municipal, or other laws that affect the performance of the Contract and are binding upon the Supplier. The Supplier shall indemnify and hold harmless the Purchaser from and against any and all liabilities, damages, claims, fines, penalties, and expenses of whatever nature arising or resulting from the violation of such laws by the Supplier or its personnel, including the Subcontractors and their personnel, but without prejudice to GCC Clause 10.1. The Supplier shall not indemnify the Purchaser to the extent that such liability, damage, claims, fines, penalties, and expenses were caused or contributed to by a fault of the Purchaser. |
|  | 9.6 Any Information Technologies or other Goods and Services that will be incorporated in or be required for the System and other supplies shall have their Origin, as defined in GCC Clause 3.12, in a country that shall be an Eligible Country, as defined in GCC Clause 1.1 (e) (iv).  9.7 Pursuant to paragraph 2.2 e. of the Appendix to the General Conditions of Contract, the Supplier shall permit and shall cause its agents (where declared or not), subcontractors, subconsultants, service providers, suppliers, and personnel, to permit, the Bank and/or persons appointed by the Bank to inspect the site and/or the accounts, records and other documents relating to the procurement process, selection and/or contract execution, and to have such accounts, records and other documents audited by auditors appointed by the Bank. The Supplier’s and its Subcontractors’ and subconsultants’ attention is drawn to GCC Clause 6.1 (Fraud and Corruption) which provides, inter alia, that acts intended to materially impede the exercise of the Bank’s inspection and audit rights constitute a prohibited practice subject to contract termination (as well as to a determination of ineligibility pursuant to the Bank’s prevailing sanctions procedures).  9.8 The Supplier shall conform to the sustainable procurement contractual provisions, if and as **specified in the SCC.**  9.9 **Code of Conduct**  The Supplier shall have a Code of Conduct for its personnel and Subcontractors’ personnel employed for the execution of the Contract.  The Supplier shall take all necessary measures to ensure that each such personnel is made aware of the Code of Conduct including specific behaviors that are prohibited, and understands the consequences of engaging in such prohibited behaviors.  These measures include providing instructions and documentation that can be understood by such personnel, and seeking to obtain that person’s signature acknowledging receipt of such instructions and/or documentation, as appropriate.  The Supplier shall also ensure that the Code of Conduct is visibly displayed in the Project Site/s as well as, as applicable, in areas outside the locations accessible to the local community and any project affected people. The posted Code of Conduct shall be provided in languages comprehensible to the Supplier’s and its Subcontractor’s personnel, Purchaser’s personnel and the local community.  9.10 The Supplier shall, in all dealings with its labor and the labor of its Subcontractors currently employed on or connected with the Contract, pay due regard to all recognized festivals, official holidays, religious or other customs, and all local laws and regulations pertaining to the employment of labor.  9.11 The Supplier, including its Subcontractors, shall comply with all applicable safety obligations. The Supplier shall at all times take all reasonable precautions to maintain the health and safety of its and Subcontractors’ personnel employed for the execution of Contract at the Project Site/s.  9.12 Training of Supplier’s Personnel  The Supplier shall provide appropriate training to relevant Supplier’s and Subcontractors’ personnel on any applicable environmental and social aspect of the Contract, including appropriate sensitization on prohibition of SEA, health and safety.  As stated in the Purchaser’s Requirements or as instructed by the Project Manager, the Supplier shall also allow appropriate opportunities for the relevant personnel to be trained on any applicable environmental and social aspects of the Contract by the Purchaser’s personnel and/or other personnel assigned by the Purchaser.  9.13 Stakeholder engagements  The Supplier shall provide relevant contract- related information, as the Purchaser and/or Project Manager may reasonably request to conduct contract stakeholder engagement. “Stakeholder” refers to individuals or groups who:   * + 1. are affected or likely to be affected by the Contract; and     2. may have an interest in the Contract.   The Supplier may also directly participate in contract stakeholder engagements, as the Purchaser and/or Project Manager may reasonably request.  9.14 Forced Labor  The Supplier, including its Subcontractors, shall not employ or engage forced labour. Forced labour consists of any work or service, not voluntarily performed, that is exacted from an individual under threat of force or penalty, and includes any kind of involuntary or compulsory labour, such as indentured labour, bonded labour or similar labour-contracting arrangements.  No persons shall be employed or engaged who have been subject to trafficking. Trafficking in persons is defined as the recruitment, transportation, transfer, harbouring or receipt of persons by means of the threat or use of force or other forms of coercion, abduction, fraud, deception, abuse of power, or of a position of vulnerability, or of the giving or receiving of payments or benefits to achieve the consent of a person having control over another person, for the purposes of exploitation.  9.15 Child Labor  The Supplier, including its Subcontractors, shall not employ or engage a child under the age of 14 unless the national law specifies a higher age (the minimum age).  The Supplier, including its Subcontractors, shall not employ or engage a child between the minimum age and the age of 18 in a manner that is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development.  The Supplier, including its Subcontractors, shall only employ or engage children between the minimum age and the age of 18 after an appropriate risk assessment has been conducted by the Supplier with the Project Manager’s consent. The Supplier shall be subject to regular monitoring by the Project Manager that includes monitoring of health, working conditions and hours of work.  Work considered hazardous for children is work that, by its nature or the circumstances in which it is carried out, is likely to jeopardize the health, safety, or morals of children. Such work activities prohibited for children include work:   1. with exposure to physical, psychological or sexual abuse; 2. underground, underwater, working at heights or in confined spaces; 3. with dangerous machinery, equipment or tools, or involving handling or transport of heavy loads; 4. in unhealthy environments exposing children to hazardous substances, agents, or processes, or to temperatures, noise or vibration damaging to health; or 5. under difficult conditions such as work for long hours, during the night or in confinement on the premises of the employer.   9.16 Non-Discrimination and Equal Opportunity  The Supplier shall not make decisions relating to the employment or treatment of personnel for the execution of the Contract on the basis of personal characteristics unrelated to inherent job requirements. The Supplier shall base the employment of personnel for the execution of the Contract on the principle of equal opportunity and fair treatment, and shall not discriminate with respect to any aspects of the employment relationship, including recruitment and hiring, compensation (including wages and benefits), working conditions and terms of employment, access to training, job assignment, promotion, termination of employment or retirement, and disciplinary practices.  Special measures of protection or assistance to remedy past discrimination or selection for a particular job based on the inherent requirements of the job shall not be deemed discrimination. The Supplier shall provide protection and assistance as necessary to ensure non-discrimination and equal opportunity, including for specific groups such as women, people with disabilities, migrant workers and children (of working age in accordance with GCC Clause 9.15).  9.17 Personnel Grievance Mechanism  The Supplier shall have a grievance mechanism for personnel employed in the execution of the Contract to raise workplace concerns. The grievance mechanism shall be proportionate to the nature, scale, risks and impacts of the Contract. The grievance mechanism may utilize existing grievance mechanisms, provided that they are properly designed and implemented, address concerns promptly, and are readily accessible to such personnel.  9.18 Security of the Project Site  **If stated in the SCC**, the Supplier shall be responsible for the security at the Project Site/s including providing and maintaining at its own expense all lighting, fencing, and watching when and where necessary for the proper execution and the protection of the locations, or for the safety of the owners and occupiers of adjacent property and for the safety of the public.  In making security arrangements, the Supplier shall be guided by applicable laws and any other requirements that may be stated in the Purchaser’s Requirements.  The Supplier shall (i) conduct appropriate background checks on any personnel retained to provide security; (ii) train the security personnel adequately (or determine that they are properly trained) in the use of force (and where applicable, firearms), and appropriate conduct towards the Supplier’s and its Subcontractors’ personnel, Purchaser’s personnel and affected communities; and (iii) require the security personnel to act within the applicable Laws and any requirements set out in the Purchaser’s Requirements.  The Supplier shall not permit any use of force by security personnel in providing security except when used for preventive and defensive purposes in proportion to the nature and extent of the threat.  9.19 Recruitment of Persons  The Supplier shall not recruit, or attempt to recruit, either on limited time or `permanent basis or through any other contractual agreement, staff and labor from amongst the Purchaser’s Personnel. |
|  | 9.20 **Unless otherwise specified in the SCC** the Supplier shall have no other Supplier responsibilities. |
| 10. Purchaser’s Responsibilities | 10.1 The Purchaser shall ensure the accuracy of all information and/or data to be supplied by the Purchaser to the Supplier, except when otherwise expressly stated in the Contract. |
|  | 10.2 The Purchaser shall be responsible for timely provision of all resources, information, and decision making under its control that are necessary to reach an Agreed Project Plan (pursuant to GCC Clause 19.2) within the time schedule specified in the Implementation Schedule. Failure to provide such resources, information, and decision making may constitute grounds for Termination pursuant to GCC Clause 41.3.1 (b).  10.3 The Purchaser shall be responsible for acquiring and providing legal and physical possession of the site and access to it, and for providing possession of and access to all other areas reasonably required for the proper execution of the Contract.  10.4 If requested by the Supplier, the Purchaser shall use its best endeavors to assist the Supplier in obtaining in a timely and expeditious manner all permits, approvals, and/or licenses necessary for the execution of the Contract from all local, state, or national government authorities or public service undertakings that such authorities or undertakings require the Supplier or Subcontractors or the personnel of the Supplier or Subcontractors, as the case may be, to obtain.  10.5 In such cases where the responsibilities of specifying and acquiring or upgrading telecommunications and/or electric power services falls to the Supplier, as specified in the Technical Requirements, SCC, Agreed Project Plan, or other parts of the Contract, the Purchaser shall use its best endeavors to assist the Supplier in obtaining such services in a timely and expeditious manner.  10.6 The Purchaser shall be responsible for timely provision of all resources, access, and information necessary for the Installation and Operational Acceptance of the System (including, but not limited to, any required telecommunications or electric power services), as identified in the Agreed Project Plan, except where provision of such items is explicitly identified in the Contract as being the responsibility of the Supplier. Delay by the Purchaser may result in an appropriate extension of the Time for Operational Acceptance, at the Supplier’s discretion.  10.7 Unless otherwise specified in the Contract or agreed upon by the Purchaser and the Supplier, the Purchaser shall provide sufficient, properly qualified operating and technical personnel, as required by the Supplier to properly carry out Delivery, Pre-commissioning, Installation, Commissioning, and Operational Acceptance, at or before the time specified in the Implementation Schedule and the Agreed Project Plan.  10.8 The Purchaser will designate appropriate staff for the training courses to be given by the Supplier and shall make all appropriate logistical arrangements for such training as specified in the Technical Requirements, SCC, the Agreed Project Plan, or other parts of the Contract.  10.9 The Purchaser assumes primary responsibility for the Operational Acceptance Test(s) for the System, in accordance with GCC Clause 27.2, and shall be responsible for the continued operation of the System after Operational Acceptance. However, this shall not limit in any way the Supplier’s responsibilities after the date of Operational Acceptance otherwise specified in the Contract.  10.10 The Purchaser is responsible for performing and safely storing timely and regular backups of its data and Software in accordance with accepted data management principles, except where such responsibility is clearly assigned to the Supplier elsewhere in the Contract.  10.11 All costs and expenses involved in the performance of the obligations under this GCC Clause 10 shall be the responsibility of the Purchaser, save those to be incurred by the Supplier with respect to the performance of the Operational Acceptance Test(s), in accordance with GCC Clause 27.2.  10.12 **Unless otherwise specified in the SCC** the Purchaser shall have no other responsibilities. |

C. Payment

|  |  |
| --- | --- |
| 11. Contract Price | 11.1 The Contract Price shall be as specified in Article 2 (Contract Price and Terms of Payment) of the Contract Agreement. |
|  | 11.2 Unless an adjustment clause is **provided for in the SCC,** the Contract Price shall be a firm lump sum not subject to any alteration, except in the event of a Change in the System pursuant to GCC Clause 39 or to other clauses in the Contract; |
|  | 11.3 The Supplier shall be deemed to have satisfied itself as to the correctness and sufficiency of the Contract Price, which shall, except as otherwise provided for in the Contract, cover all its obligations under the Contract. |
| 12. Terms of Payment | 12.1 The Supplier’s request for payment shall be made to the Purchaser in writing, accompanied by an invoice describing, as appropriate, the System or Subsystem(s), Delivered, Pre-commissioned, Installed, and Operationally Accepted, and by documents submitted pursuant to GCC Clause 22.5 and upon fulfillment of other obligations stipulated in the Contract.  The Contract Price shall be paid as **specified in the SCC.** |
|  | 12.2 No payment made by the Purchaser herein shall be deemed to constitute acceptance by the Purchaser of the System or any Subsystem(s).  12.3 Payments shall be made promptly by the Purchaser, but in no case later than forty five (45) days after submission of a valid invoice by the Supplier. In the event that the Purchaser fails to make any payment by its respective due date or within the period set forth in the Contract.  12.4 Payments shall be made in the currency(ies) specified in the Contract Agreement, pursuant to GCC Clause 11. For Goods and Services supplied locally, payments shall be made **as specified in the SCC.**  12.5 **Unless otherwise specified in the SCC,** payment of the foreign currency portion of the Contract Price for Goods supplied from outside the Purchaser’s Country shall be made to the Supplier through an irrevocable letter of credit opened by an authorized bank in the Supplier’s Country and will be payable on presentation of the appropriate documents. It is agreed that the letter of credit will be subject to Article 10 of the latest revision of *Uniform Customs and Practice for Documentary Credits*, published by the International Chamber of Commerce, Paris. |
| 13. Securities | 13.1 Issuance of Securities  The Supplier shall provide the securities specified below in favor of the Purchaser at the times and in the amount, manner, and form specified below. |
|  | 13.2 Advance Payment Security  13.2.1 The Supplier shall provide within twenty-eight (28) days of the notification of Contract award an Advance Payment Security in the amount and currency of the Advance Payment specified in SCC for GCC Clause 12.1 above and valid until the System is Operationally Accepted.  13.2.2 The security shall be in the form provided in the bidding documents or in another form acceptable to the Purchaser. The amount of the security shall be reduced in proportion to the value of the System executed by and paid to the Supplier from time to time and shall automatically become null and void when the full amount of the advance payment has been recovered by the Purchaser. **Unless otherwise specified in the SCC,** the reduction in value and expiration of the Advance Payment Security are calculated as follows:  P\*a/(100-a), where “P” is the sum of all payments effected so far to the Supplier (excluding the Advance Payment), and “a” is the Advance Payment expressed as a percentage of the Contract Price pursuant to the SCC for GCC Clause 12.1.  The security shall be returned to the Supplier immediately after its expiration. |
|  | 13.3 Performance Security  13.3.1 The Supplier shall, within twenty-eight (28) days of the notification of Contract award, provide a security for the due performance of the Contract in the amount and currency **specified in the SCC.**  13.3.2 The security shall be a bank guarantee in the form provided in the Sample Contractual Forms Section of the bidding documents, or it shall be in another form acceptable to the Purchaser.  13.3.3 The security shall automatically become null and void once all the obligations of the Supplier under the Contract have been fulfilled, including, but not limited to, any obligations during the Warranty Period and any extensions to the period. The security shall be returned to the Supplier no later than twenty-eight (28) days after its expiration.  13.3.4 Upon Operational Acceptance of the entire System, the security shall be reduced to the amount **specified in the SCC,** on the date of the Operational Acceptance, so that the reduced security would only cover the remaining warranty obligations of the Supplier. |
| 14. Taxes and Duties | 14.1 For Goods or Services supplied from outside the Purchaser’s country, the Supplier shall be entirely responsible for all taxes, stamp duties, license fees, and other such levies imposed outside the Purchaser’s country. Any duties, such as importation or customs duties, and taxes and other levies, payable in the Purchaser’s country for the supply of Goods and Services from outside the Purchaser’s country are the responsibility of the Purchaser unless these duties or taxes have been made part of the Contract Price in Article 2 of the Contract Agreement and the Price Schedule it refers to, in which case the duties and taxes will be the Supplier’s responsibility. |
|  | 14.2 For Goods or Services supplied locally, the Supplier shall be entirely responsible for all taxes, duties, license fees, etc., incurred until delivery of the contracted Goods or Services to the Purchaser. The only exception are taxes or duties, such as value-added or sales tax or stamp duty as apply to, or are clearly identifiable, on the invoices and provided they apply in the Purchaser’s country, and only if these taxes, levies and/or duties are also excluded from the Contract Price in Article 2 of the Contract Agreement and the Price Schedule it refers to.  14.3 If any tax exemptions, reductions, allowances, or privileges may be available to the Supplier in the Purchaser’s Country, the Purchaser shall use its best efforts to enable the Supplier to benefit from any such tax savings to the maximum allowable extent.  14.4 For the purpose of the Contract, it is agreed that the Contract Price specified in Article 2 (Contract Price and Terms of Payment) of the Contract Agreement is based on the taxes, duties, levies, and charges prevailing at the date twenty-eight (28) days prior to the date of bid submission in the Purchaser’s Country (also called “Tax” in this GCC Clause 14.4). If any Tax rates are increased or decreased, a new Tax is introduced, an existing Tax is abolished, or any change in interpretation or application of any Tax occurs in the course of the performance of the Contract, which was or will be assessed on the Supplier, its Subcontractors, or their employees in connection with performance of the Contract, an equitable adjustment to the Contract Price shall be made to fully take into account any such change by addition to or reduction from the Contract Price, as the case may be. |

D. Intellectual Property

|  |  |
| --- | --- |
| 15. Copyright | 15.1 The Intellectual Property Rights in all Standard Software and Standard Materials shall remain vested in the owner of such rights. |
|  | 15.2 The Purchaser agrees to restrict use, copying, or duplication of the Standard Software and Standard Materials in accordance with GCC Clause 16, except that additional copies of Standard Materials may be made by the Purchaser for use within the scope of the project of which the System is a part, in the event that the Supplier does not deliver copies within thirty (30) days from receipt of a request for such Standard Materials.  15.3 The Purchaser’s contractual rights to use the Standard Software or elements of the Standard Software may not be assigned, licensed, or otherwise transferred voluntarily except in accordance with the relevant license agreement or **unless otherwise specified in the SCC** to a legally constituted successor organization (e.g., a reorganization of a public entity formally authorized by the government or through a merger or acquisition of a private entity)**.**  15.4 **Unless otherwise specified in the SCC,** the Intellectual Property Rights in all Custom Software and Custom Materials specified in Appendices 4 and 5 of the Contract Agreement (if any) shall, at the date of this Contract or on creation of the rights (if later than the date of this Contract), vest in the Purchaser. The Supplier shall do and execute or arrange for the doing and executing of each necessary act, document, and thing (as legally sufficient) that the Purchaser may consider necessary or desirable to perfect the right, title, and interest of the Purchaser in and to those rights. In respect of such Custom Software and Custom Materials, the Supplier shall ensure that the holder of a moral right in such an item does not assert it, and the Supplier shall, if requested to do so by the Purchaser and where permitted by applicable law, ensure that the holder of such a moral right waives it. |
|  | 15.5 **Unless otherwise specified in the SCC**, escrow arrangements shall NOT be required. |
| 16. Software License Agreements | 16.1 Except to the extent that the Intellectual Property Rights in the Software vest in the Purchaser, the Supplier hereby grants to the Purchaser license to access and use the Software, including all inventions, designs, and marks embodied in the Software. |
|  | Such license to access and use the Software shall:  (a) be:  (i) nonexclusive;  (ii) fully paid up and irrevocable (except that it shall terminate if the Contract terminates under GCC Clauses 41.1 or 41.3);  (iii) **unless otherwise specified in the SCC** valid throughout the territory of the Purchaser’s Country;  (iv) **unless otherwise specified in the SCC** subject to NO additional restrictions.  (b) permit the Software to be:  (i) used or copied for use on or with the computer(s) for which it was acquired (if specified in the Technical Requirements and/or the Supplier’s bid), plus a backup computer(s) of the same or similar capacity, if the primary is(are) inoperative, and during a reasonable transitional period when use is being transferred between primary and backup;  (ii) used or copied for use on or transferred to a replacement computer(s), (and use on the original and replacement computer(s) may be simultaneous during a reasonable transitional period) provided that, if the Technical Requirements and/or the Supplier’s bid specifies a class of computer to which the license is restricted, the replacement computer(s) is(are) within that class;  (iii) if the nature of the System is such as to permit such access, accessed from other computers connected to the primary and/or backup computer(s) by means of a local or wide-area network or similar arrangement, and used on or copied for use on those other computers to the extent necessary to that access;  (iv) reproduced for safekeeping or backup purposes;  (v) customized, adapted, or combined with other computer software for use by the Purchaser, provided that derivative software incorporating any substantial part of the delivered, restricted Software shall be subject to same restrictions as are set forth in this Contract;  (vi) **unless otherwise specified in the SCC,** disclosed to, and reproduced for use by, support service suppliers and their subcontractors, to the extent reasonably necessary to the performance of their support service contracts, subject to the same restrictions as are set forth in this Contract; and  (vii) **unless otherwise specified in the SCC** disclosed to, and reproduced for use by, NO other parties. |
|  | 16.2 The Supplier has the right to audit the Standard Software to verify compliance with the above license agreements. **Unless otherwise specified in the SCC**, the Purchaser will make available to the Supplier, within seven (7) days of a written request, accurate and up-to-date records of the number and location of copies, the number of authorized users, or any other relevant data required to demonstrate use of the Standard Software as per the license agreement. If and only if, expressly agreed in writing between the Purchaser and the Supplier, Purchaser will allow, under a pre-specified agreed procedure, the execution of embedded software functions under Supplier’s control, and unencumbered transmission of resulting information on software usage. |
| 17. Confidential Information | 17.1 **Unless otherwise specified in the SCC,** the "Receiving Party" (either the Purchaser or the Supplier) shall keep confidential and shall not, without the written consent of the other party to this Contract (“the Disclosing Party”), divulge to any third party any documents, data, or other information of a confidential nature (“Confidential Information”) connected with this Contract, and furnished directly or indirectly by the Disclosing Party prior to or during performance, or following termination, of this Contract. |
|  | 17.2 For the purposes of GCC Clause 17.1, the Supplier is also deemed to be the Receiving Party of Confidential Information generated by the Supplier itself in the course of the performance of its obligations under the Contract and relating to the businesses, finances, suppliers, employees, or other contacts of the Purchaser or the Purchaser’s use of the System.  17.3 Notwithstanding GCC Clauses 17.1 and 17.2:  (a) the Supplier may furnish to its Subcontractor Confidential Information of the Purchaser to the extent reasonably required for the Subcontractor to perform its work under the Contract; and  (b) the Purchaser may furnish Confidential Information of the Supplier: (i) to its support service suppliers and their subcontractors to the extent reasonably required for them to perform their work under their support service contracts; and (ii) to its affiliates and subsidiaries,  in which event the Receiving Party shall ensure that the person to whom it furnishes Confidential Information of the Disclosing Party is aware of and abides by the Receiving Party’s obligations under this GCC Clause 17 as if that person were party to the Contract in place of the Receiving Party. |
|  | 17.4 The Purchaser shall not, without the Supplier’s prior written consent, use any Confidential Information received from the Supplier for any purpose other than the operation, maintenance and further development of the System. Similarly, the Supplier shall not, without the Purchaser’s prior written consent, use any Confidential Information received from the Purchaser for any purpose other than those that are required for the performance of the Contract.  17.5 The obligation of a party under GCC Clauses 17.1 through 17.4 above, however, shall not apply to that information which:  (a) now or hereafter enters the public domain through no fault of the Receiving Party;  (b) can be proven to have been possessed by the Receiving Party at the time of disclosure and that was not previously obtained, directly or indirectly, from the Disclosing Party;  (c) otherwise lawfully becomes available to the Receiving Party from a third party that has no obligation of confidentiality;  (d) is being provided to the Bank.  17.6 The above provisions of this GCC Clause 17 shall not in any way modify any undertaking of confidentiality given by either of the parties to this Contract prior to the date of the Contract in respect of the System or any part thereof.  17.7 **Unless otherwise specified in the SCC**, the provisions of this GCC Clause 17 shall survive the termination, for whatever reason, of the Contract for three (3) years. |

E. Supply, Installation, Testing,  
Commissioning, and Acceptance of the System

|  |  |
| --- | --- |
| 18. Representatives | 18.1 Project Manager  If the Project Manager is not named in the Contract, then within fourteen (14) days of the Effective Date, the Purchaser shall appoint and notify the Supplier in writing of the name of the Project Manager. The Purchaser may from time to time appoint some other person as the Project Manager in place of the person previously so appointed and shall give a notice of the name of such other person to the Supplier without delay. No such appointment shall be made at such a time or in such a manner as to impede the progress of work on the System. Such appointment shall take effect only upon receipt of such notice by the Supplier. **Unless otherwise specified in the SCC** (if any), the Project Manager shall have the authority to represent the Purchaser on all day-to-day matters relating to the System or arising from the Contract, and shall normally be the person giving or receiving notices on behalf of the Purchaser pursuant to GCC Clause 4. |
|  | 18.2 Supplier’s Representative  18.2.1 If the Supplier’s Representative is not named in the Contract, then within fourteen (14) days of the Effective Date, the Supplier shall appoint the Supplier’s Representative and shall request the Purchaser in writing to approve the person so appointed. The request must be accompanied by a detailed curriculum vitae for the nominee, as well as a description of any other System or non-System responsibilities the nominee would retain while performing the duties of the Supplier’s Representative. If the Purchaser does not object to the appointment within fourteen (14) days, the Supplier’s Representative shall be deemed to have been approved. If the Purchaser objects to the appointment within fourteen (14) days giving the reason therefor, then the Supplier shall appoint a replacement within fourteen (14) days of such objection in accordance with this GCC Clause 18.2.1.  18.2.2 **Unless otherwise specified in the SCC** (if any), the Supplier’s Representative shall have the authority to represent the Supplier on all day-to-day matters relating to the System or arising from the Contract, and shall normally be the person giving or receiving notices on behalf of the Supplier pursuant to GCC Clause 4.  18.2.3 The Supplier shall not revoke the appointment of the Supplier’s Representative without the Purchaser’s prior written consent, which shall not be unreasonably withheld. If the Purchaser consents to such an action, the Supplier shall appoint another person of equal or superior qualifications as the Supplier’s Representative, pursuant to the procedure set out in GCC Clause 18.2.1.  18.2.4 The Supplier’s Representative and staff are obliged to work closely with the Purchaser’s Project Manager and staff, act within their own authority, and abide by directives issued by the Purchaser that are consistent with the terms of the Contract. The Supplier’s Representative is responsible for managing the activities of its personnel and any subcontracted personnel.  18.2.5 The Supplier’s Representative may, subject to the approval of the Purchaser (which shall not be unreasonably withheld), at any time delegate to any person any of the powers, functions, and authorities vested in him or her. Any such delegation may be revoked at any time. Any such delegation or revocation shall be subject to a prior notice signed by the Supplier’s Representative and shall specify the powers, functions, and authorities thereby delegated or revoked. No such delegation or revocation shall take effect unless and until the notice of it has been delivered.  18.2.6 Any act or exercise by any person of powers, functions and authorities so delegated to him or her in accordance with GCC Clause 18.2.5 shall be deemed to be an act or exercise by the Supplier’s Representative.  18.3 Removal of Supplier’s and Subcontractors’ Personnel  18.3.1 The Project Manager may require the Supplier to remove (or cause to be removed) the Supplier’s Representative or any other person employed by the Supplier in the execution of the Contract, who:   1. persists in any misconduct or lack of care; 2. carries out duties incompetently or negligently; 3. fails to comply with any provision of the Contract; 4. persists in any conduct which is prejudicial to safety, health, or the protection of the environment; 5. based on reasonable evidence, is determined to have engaged in Fraud and Corruption during the execution of the Contract; 6. has been recruited from the Purchaser’s Personnel; 7. engages in any other behaviour which breaches the Code of Conduct, as applicable;   If appropriate, the Supplier shall then promptly appoint (or cause to be appointed) a suitable replacement with equivalent skills and experience.  Notwithstanding any requirement from the Project Manager to remove or cause to remove any person, the Supplier shall take immediate action as appropriate in response to any violation of (a) through (g) above. Such immediate action shall include removing (or causing to be removed) from work on the System, any person Employed by the Supplier in the execution of the Contract who engages in (a), (b), (c), (d), (e) or (g) above or has been recruited as stated in (f) above.  18.3.2 If any representative or person employed by the Supplier is removed in accordance with GCC Clause 18.3.1, the Supplier shall, where required, promptly appoint a suitable replacement with equivalent skills and experience. |
| 19. Project Plan | 19.1 In close cooperation with the Purchaser and based on the Preliminary Project Plan included in the Supplier’s bid, the Supplier shall develop a Project Plan encompassing the activities specified in the Contract. The contents of the Project Plan shall be as **specified in the SCC** and/or Technical Requirements. |
|  | 19.2 **Unless otherwise specified in the SCC**, within thirty (30) days from the Effective Date of the Contract, the Supplier shall present a Project Plan to the Purchaser. The Purchaser shall, within fourteen (14)days of receipt of the Project Plan, notify the Supplier of any respects in which it considers that the Project Plan does not adequately ensure that the proposed program of work, proposed methods, and/or proposed Information Technologies will satisfy the Technical Requirements and/or the SCC (in this Clause 19.2 called “non-conformities” below). The Supplier shall, within five (5) days of receipt of such notification, correct the Project Plan and resubmit to the Purchaser. The Purchaser shall, within five (5) days of resubmission of the Project Plan, notify the Supplier of any remaining non-conformities. This procedure shall be repeated as necessary until the Project Plan is free from non-conformities. When the Project Plan is free from non-conformities, the Purchaser shall provide confirmation in writing to the Supplier. This approved Project Plan (“the Agreed Project Plan”) shall be contractually binding on the Purchaser and the Supplier.  19.3 If required, the impact on the Implementation Schedule of modifications agreed during finalization of the Agreed Project Plan shall be incorporated in the Contract by amendment, in accordance with GCC Clauses 39 and 40.  19.4 The Supplier shall undertake to supply, install, test, and commission the System in accordance with the Agreed Project Plan and the Contract.  19.5 **Unless otherwise specified in the SCC**, the Supplier shall submit to the Purchaser Monthly Progress Reports summarizing:  (i) results accomplished during the prior period;  (ii) cumulative deviations to date from schedule of progress milestones as specified in the Agreed Project Plan;  (iii) corrective actions to be taken to return to planned schedule of progress; proposed revisions to planned schedule;  (iv) other issues and outstanding problems; proposed actions to be taken;  (v) resources that the Supplier expects to be provided by the Purchaser and/or actions to be taken by the Purchaser in the next reporting period;  (vi) status of compliance to environmental and social requirements, as applicable;  (vii) other issues or potential problems the Supplier foresees that could impact on project progress and/or effectiveness.  19.6 The Supplier shall submit to the Purchaser other (periodic) reports as specified in the SCC.  19.7 Immediate Reporting requirement  The Supplier shall inform the Project Manager immediately of any allegation, incident or accident in Project Site/s, which has or is likely to have a significant adverse effect on the environment, the affected communities, the public, Purchaser’s personnel, Supplier’s or Subcontractors’ personnel. This includes, but is not limited to, any incident or accident causing fatality or serious injury; significant adverse effects or damage to private property; or any allegation of SEA and/or SH. In case of SEA and/or SH, while maintaining confidentiality as appropriate, the type of allegation (sexual exploitation, sexual abuse or sexual harassment), gender and age of the person who experienced the alleged incident should be included in the information. The Supplier shall provide full details of such incidents or accidents to the Project Manager within the timeframe agreed with the Purchaser.  The Purchaser shall require its Subcontractors to immediately notify it of any incidents or accidents referred to in this Sub- Clause. |
| 20. Subcontracting | 20.1 Appendix 3 (List of Approved Subcontractors) to the Contract Agreement specifies critical items of supply or services and a list of Subcontractors for each item that are considered acceptable by the Purchaser. If no Subcontractors are listed for an item, the Supplier shall prepare a list of Subcontractors it considers qualified and wishes to be added to the list for such items. The Supplier may from time to time propose additions to or deletions from any such list. The Supplier shall submit any such list or any modification to the list to the Purchaser for its approval in sufficient time so as not to impede the progress of work on the System. The Purchaser shall not withhold such approval unreasonably. Such approval by the Purchaser of a Subcontractor(s) shall not relieve the Supplier from any of its obligations, duties, or responsibilities under the Contract. |
|  | 20.2 The Supplier may, at its discretion, select and employ Subcontractors for such critical items from those Subcontractors listed pursuant to GCC Clause 20.1. If the Supplier wishes to employ a Subcontractor not so listed, or subcontract an item not so listed, it must seek the Purchaser’s prior approval under GCC Clause 20.3.  20.3 For items for which pre-approved Subcontractor lists have not been specified in Appendix 3 to the Contract Agreement, the Supplier may employ such Subcontractors as it may select, provided: (i) the Supplier notifies the Purchaser in writing at least twenty-eight (28) days prior to the proposed mobilization date for such Subcontractor; and (ii) by the end of this period either the Purchaser has granted its approval in writing or fails to respond. The Supplier shall not engage any Subcontractor to which the Purchaser has objected in writing prior to the end of the notice period. The absence of a written objection by the Purchaser during the above specified period shall constitute formal acceptance of the proposed Subcontractor. Except to the extent that it permits the deemed approval of the Purchaser of Subcontractors not listed in the Contract Agreement, nothing in this Clause, however, shall limit the rights and obligations of either the Purchaser or Supplier as they are specified in GCC Clauses 20.1 and 20.2, or in Appendix 3 of the Contract Agreement. |
| 21. Design and Engineering | 21.1 Technical Specifications and Drawings  21.1.1 The Supplier shall execute the basic and detailed design and the implementation activities necessary for successful installation of the System in compliance with the provisions of the Contract or, where not so specified, in accordance with good industry practice. |
|  | The Supplier shall be responsible for any discrepancies, errors or omissions in the specifications, drawings, and other technical documents that it has prepared, whether such specifications, drawings, and other documents have been approved by the Project Manager or not, provided that such discrepancies, errors, or omissions are not because of inaccurate information furnished in writing to the Supplier by or on behalf of the Purchaser.  21.1.2 The Supplier shall be entitled to disclaim responsibility for any design, data, drawing, specification, or other document, or any modification of such design, drawings, specification, or other documents provided or designated by or on behalf of the Purchaser, by giving a notice of such disclaimer to the Project Manager.  21.2 Codes and Standards  Wherever references are made in the Contract to codes and standards in accordance with which the Contract shall be executed, the edition or the revised version of such codes and standards current at the date twenty-eight (28) days prior to date of bid submission shall apply. During Contract execution, any changes in such codes and standards shall be applied after approval by the Purchaser and shall be treated in accordance with GCC Clause 39.3.  21.3 Approval/Review of Controlling Technical Documents by the Project Manager  21.3.1 **Unless otherwise specified in the SCC**, there will NO Controlling Technical Documents required. However, **if the SCC specifies** Controlling Technical Documents, the Supplier shall prepare and furnish such documents for the Project Manager’s approval or review.  Any part of the System covered by or related to the documents to be approved by the Project Manager shall be executed only after the Project Manager’s approval of these documents.  GCC Clauses 21.3.2 through 21.3.7 shall apply to those documents requiring the Project Manager’s approval, but not to those furnished to the Project Manager for its review only.  21.3.2 Within fourteen (14) days after receipt by the Project Manager of any document requiring the Project Manager’s approval in accordance with GCC Clause 21.3.1, the Project Manager shall either return one copy of the document to the Supplier with its approval endorsed on the document or shall notify the Supplier in writing of its disapproval of the document and the reasons for disapproval and the modifications that the Project Manager proposes. If the Project Manager fails to take such action within the fourteen (14) days, then the document shall be deemed to have been approved by the Project Manager.  21.3.3 The Project Manager shall not disapprove any document except on the grounds that the document does not comply with some specified provision of the Contract or that it is contrary to good industry practice.  21.3.4 If the Project Manager disapproves the document, the Supplier shall modify the document and resubmit it for the Project Manager’s approval in accordance with GCC Clause 21.3.2. If the Project Manager approves the document subject to modification(s), the Supplier shall make the required modification(s), and the document shall then be deemed to have been approved, subject to GCC Clause 21.3.5. The procedure set out in GCC Clauses 21.3.2 through 21.3.4 shall be repeated, as appropriate, until the Project Manager approves such documents.  21.3.5 If any dispute occurs between the Purchaser and the Supplier in connection with or arising out of the disapproval by the Project Manager of any document and/or any modification(s) to a document that cannot be settled between the parties within a reasonable period, then, in case the Contract Agreement includes and names an Adjudicator, such dispute may be referred to the Adjudicator for determination in accordance with GCC Clause 43.1 (Adjudication). If such dispute is referred to an Adjudicator, the Project Manager shall give instructions as to whether and if so, how, performance of the Contract is to proceed. The Supplier shall proceed with the Contract in accordance with the Project Manager’s instructions, provided that if the Adjudicator upholds the Supplier’s view on the dispute and if the Purchaser has not given notice under GCC Clause 43.1.2, then the Supplier shall be reimbursed by the Purchaser for any additional costs incurred by reason of such instructions and shall be relieved of such responsibility or liability in connection with the dispute and the execution of the instructions as the Adjudicator shall decide, and the Time for Achieving Operational Acceptance shall be extended accordingly.  21.3.6 The Project Manager’s approval, with or without modification of the document furnished by the Supplier, shall not relieve the Supplier of any responsibility or liability imposed upon it by any provisions of the Contract except to the extent that any subsequent failure results from modifications required by the Project Manager or inaccurate information furnished in writing to the Supplier by or on behalf of the Purchaser.  21.3.7 The Supplier shall not depart from any approved document unless the Supplier has first submitted to the Project Manager an amended document and obtained the Project Manager’s approval of the document, pursuant to the provisions of this GCC Clause 21.3. If the Project Manager requests any change in any already approved document and/or in any document based on such an approved document, the provisions of GCC Clause 39 (Changes to the System) shall apply to such request. |
| 22. Procurement, Delivery, and Transport | 22.1 Subject to related Purchaser's responsibilities pursuant to GCC Clauses 10 and 14, the Supplier shall manufacture or procure and transport all the Information Technologies, Materials, and other Goods in an expeditious and orderly manner to the Project Site. |
|  | 22.2 Delivery of the Information Technologies, Materials, and other Goods shall be made by the Supplier in accordance with the Technical Requirements.  22.3 Early or partial deliveries require the explicit written consent of the Purchaser, which consent shall not be unreasonably withheld.  22.4 Transportation  22.4.1 The Supplier shall provide such packing of the Goods as is required to prevent their damage or deterioration during shipment. The packing, marking, and documentation within and outside the packages shall comply strictly with the Purchaser’s instructions to the Supplier.   * + 1. The Supplier will bear responsibility for and cost of transport to the Project Sites in accordance with the terms and conditions used in the specification of prices in the Price Schedules, including the terms and conditions of the associated Incoterms.     2. **Unless otherwise specified in the SCC,** the Supplier shall be free to use transportation through carriers registered in any eligible country and to obtain insurance from any eligible source country.   22.5 **Unless otherwise specified in the SCC,** the Supplier will provide the Purchaser with shipping and other documents, as specified below:  22.5.1 For Goods supplied from outside the Purchaser’s Country:  Upon shipment, the Supplier shall notify the Purchaser and the insurance company contracted by the Supplier to provide cargo insurance by cable, facsimile, electronic mail, or EDI with the full details of the shipment. The Supplier shall promptly send the following documents to the Purchaser by mail or courier, as appropriate, with a copy to the cargo insurance company:  (a) two copies of the Supplier’s invoice showing the description of the Goods, quantity, unit price, and total amount;  (b) usual transportation documents;  (c) insurance certificate;  (d) certificate(s) of origin; and  (e) estimated time and point of arrival in the Purchaser’s Country and at the site.  22.5.2 For Goods supplied locally (i.e., from within the Purchaser’s country):  Upon shipment, the Supplier shall notify the Purchaser by cable, facsimile, electronic mail, or EDI with the full details of the shipment. The Supplier shall promptly send the following documents to the Purchaser by mail or courier, as appropriate:  (a) two copies of the Supplier’s invoice showing the Goods’ description, quantity, unit price, and total amount;  (b) delivery note, railway receipt, or truck receipt;  (c) certificate of insurance;  (d) certificate(s) of origin; and  (e) estimated time of arrival at the site.  22.6 Customs Clearance  (a) The Purchaser will bear responsibility for, and cost of, customs clearance into the Purchaser's country in accordance the particular Incoterm(s) used for Goods supplied from outside the Purchaser’s country in the Price Schedules referred to by Article 2 of the Contract Agreement.  (b) At the request of the Purchaser, the Supplier will make available a representative or agent during the process of customs clearance in the Purchaser's country for goods supplied from outside the Purchaser's country. In the event of delays in customs clearance that are not the fault of the Supplier:  (i) the Supplier shall be entitled to an extension in the Time for Achieving Operational Acceptance, pursuant to GCC Clause 40;  (ii) the Contract Price shall be adjusted to compensate the Supplier for any additional storage charges that the Supplier may incur as a result of the delay. |
| 23. Product Upgrades | 23.1 At any point during performance of the Contract, should technological advances be introduced by the Supplier to the benefit of its clients for Information Technologies originally offered by the Supplier in its bid and still to be delivered, the Supplier shall be obligated to offer to the Purchaser the latest versions of the available Information Technologies having equal or better performance or functionality at the same or lesser unit prices, pursuant to GCC Clause 39 (Changes to the System). |
|  | 23.2 At any point during performance of the Contract, for Information Technologies still to be delivered, the Supplier will also pass on to the Purchaser any cost reductions and additional and/or improved support and facilities that it offers to other clients of the Supplier in the Purchaser’s Country, pursuant to GCC Clause 39 (Changes to the System).  23.3 During performance of the Contract, the Supplier shall offer to the Purchaser all new versions, releases, and updates of Standard Software, as well as related documentation and technical support services, within thirty (30) days of their availability from the Supplier to other clients of the Supplier in the Purchaser’s Country, and no later than twelve (12) months after they are released in the country of origin. In no case will the prices for these Software exceed those quoted by the Supplier in the Recurrent Costs tables in its bid.  23.4 **Unless otherwise specified in the SCC,** during the Warranty Period, the Supplier will provide at no additional cost to the Purchaser all new versions, releases, and updates for all Standard Software that are used in the System, within thirty (30) days of their availability from the Supplier to other clients of the Supplier in the Purchaser’s country, and no later than twelve (12) months after they are released in the country of origin of the Software.  23.5 The Purchaser shall introduce all new versions, releases or updates of the Software within eighteen (18) months of receipt of a production-ready copy of the new version, release, or update, provided that the new version, release, or update does not adversely affect System operation or performance or require extensive reworking of the System. In cases where the new version, release, or update adversely affects System operation or performance, or requires extensive reworking of the System, the Supplier shall continue to support and maintain the version or release previously in operation for as long as necessary to allow introduction of the new version, release, or update. In no case shall the Supplier stop supporting or maintaining a version or release of the Software less than twenty four (24) months after the Purchaser receives a production-ready copy of a subsequent version, release, or update. The Purchaser shall use all reasonable endeavors to implement any new version, release, or update as soon as practicable, subject to the twenty-four-month-long stop date. |
| 24. Implementation, Installation, and Other Services | 24.1 The Supplier shall provide all Services specified in the Contract and Agreed Project Plan in accordance with the highest standards of professional competence and integrity. |
|  | 24.2 Prices charged by the Supplier for Services, if not included in the Contract, shall be agreed upon in advance by the parties (including, but not restricted to, any prices submitted by the Supplier in the Recurrent Cost Schedules of its Bid) and shall not exceed the prevailing rates charged by the Supplier to other purchasers in the Purchaser’s Country for similar services. |
| 25. Inspections and Tests | 25.1 The Purchaser or its representative shall have the right to inspect and/or test any components of the System, as specified in the Technical Requirements, to confirm their good working order and/or conformity to the Contract at the point of delivery and/or at the Project Site. |
|  | 25.2 The Purchaser or its representative shall be entitled to attend any such inspections and/or tests of the components, provided that the Purchaser shall bear all costs and expenses incurred in connection with such attendance, including but not limited to all inspection agent fees, travel, and related expenses.  25.3 Should the inspected or tested components fail to conform to the Contract, the Purchaser may reject the component(s), and the Supplier shall either replace the rejected component(s), or make alterations as necessary so that it meets the Contract requirements free of cost to the Purchaser.  25.4 The Project Manager may require the Supplier to carry out any inspection and/or test not specified in the Contract, provided that the Supplier’s reasonable costs and expenses incurred in the carrying out of such inspection and/or test shall be added to the Contract Price. Further, if such inspection and/or test impedes the progress of work on the System and/or the Supplier’s performance of its other obligations under the Contract, due allowance will be made in respect of the Time for Achieving Operational Acceptance and the other obligations so affected.  25.5 If any dispute shall arise between the parties in connection with or caused by an inspection and/or with regard to any component to be incorporated in the System that cannot be settled amicably between the parties within a reasonable period of time, either party may invoke the process pursuant to GCC Clause 43 (Settlement of Disputes), starting with referral of the matter to the Adjudicator in case an Adjudicator is included and named in the Contract Agreement. |
| 26. Installation of the System | 26.1 As soon as the System, or any Subsystem, has, in the opinion of the Supplier, been delivered, Pre-commissioned, and made ready for Commissioning and Operational Acceptance Testing in accordance with the Technical Requirements, the SCC and the Agreed Project Plan, the Supplier shall so notify the Purchaser in writing. |
|  | 26.2 The Project Manager shall, within fourteen (14) days after receipt of the Supplier’s notice under GCC Clause 26.1, either issue an Installation Certificate in the form specified in the Sample Contractual Forms Section in the bidding documents, stating that the System, or major component or Subsystem (if Acceptance by major component or Subsystem is specified pursuant to the SCC for GCC Clause 27.2.1), has achieved Installation by the date of the Supplier’s notice under GCC Clause 26.1, or notify the Supplier in writing of any defects and/or deficiencies, including, but not limited to, defects or deficiencies in the interoperability or integration of the various components and/or Subsystems making up the System. The Supplier shall use all reasonable endeavors to promptly remedy any defect and/or deficiencies that the Project Manager has notified the Supplier of. The Supplier shall then promptly carry out retesting of the System or Subsystem and, when in the Supplier’s opinion the System or Subsystem is ready for Commissioning and Operational Acceptance Testing, notify the Purchaser in writing, in accordance with GCC Clause 26.1. The procedure set out in this GCC Clause 26.2 shall be repeated, as necessary, until an Installation Certificate is issued.  26.3 If the Project Manager fails to issue the Installation Certificate and fails to inform the Supplier of any defects and/or deficiencies within fourteen (14) days after receipt of the Supplier’s notice under GCC Clause 26.1, or if the Purchaser puts the System or a Subsystem into production operation, then the System (or Subsystem) shall be deemed to have achieved successful Installation as of the date of the Supplier’s notice or repeated notice, or when the Purchaser put the System into production operation, as the case may be. |
| 27. Commissioning and Operational Acceptance | 27.1 Commissioning  27.1.1 Commissioning of the System (or Subsystem if specified pursuant to the SCC for GCC Clause 27.2.1) shall be commenced by the Supplier:  (a) immediately after the Installation Certificate is issued by the Project Manager, pursuant to GCC Clause 26.2; or  (b) as otherwise specified in the Technical Requirement or the Agreed Project Plan; or  (c) immediately after Installation is deemed to have occurred, under GCC Clause 26.3. |
|  | 27.1.2 The Purchaser shall supply the operating and technical personnel and all materials and information reasonably required to enable the Supplier to carry out its obligations with respect to Commissioning.  Production use of the System or Subsystem(s) shall not commence prior to the start of formal Operational Acceptance Testing.  27.2 Operational Acceptance Tests  27.2.1 The Operational Acceptance Tests (and repeats of such tests) shall be the primary responsibility of the Purchaser (in accordance with GCC Clause 10.9), but shall be conducted with the full cooperation of the Supplier during Commissioning of the System (or major components or Subsystem[s]), to ascertain whether the System (or major component or Subsystem[s]) conforms to the Technical Requirements and meets the standard of performance quoted in the Supplier’s bid, including, but not restricted to, the functional and technical performance requirements. **Unless otherwise specified in the SCC**, the Operational Acceptance Tests during Commissioning will be conducted as specified in the Technical Requirements and/or the Agreed Project Plan.  At the Purchaser’s discretion, Operational Acceptance Tests may also be performed on replacement Goods, upgrades and new version releases, and Goods that are added or field-modified after Operational Acceptance of the System.  27.2.2 If for reasons attributable to the Purchaser, the Operational Acceptance Test of the System (or Subsystem[s] or major components, pursuant to the SCC for GCC Clause 27.2.1) cannot be successfully completed within ninety (90) days from the date of Installation or any other period agreed upon in writing by the Purchaser and the Supplier, the Supplier shall be deemed to have fulfilled its obligations with respect to the technical and functional aspects of the Technical Specifications, SCC and/or the Agreed Project Plan, and GCC Clause 28.2 and 28.3 shall not apply.  27.3 Operational Acceptance  27.3.1 Subject to GCC Clause 27.4 (Partial Acceptance) below, Operational Acceptance shall occur in respect of the System, when  (a) the Operational Acceptance Tests, as specified in the Technical Requirements, and/or SCC and/or the Agreed Project Plan have been successfully completed; or  (b) the Operational Acceptance Tests have not been successfully completed or have not been carried out for reasons that are attributable to the Purchaser within the period from the date of Installation or any other agreed-upon period as specified in GCC Clause 27.2.2 above; or  (c) the Purchaser has put the System into production or use for sixty (60) consecutive days. If the System is put into production or use in this manner, the Supplier shall notify the Purchaser and document such use.  27.3.2 At any time after any of the events set out in GCC Clause 27.3.1 have occurred, the Supplier may give a notice to the Project Manager requesting the issue of an Operational Acceptance Certificate.  27.3.3 After consultation with the Purchaser, and within fourteen (14) days after receipt of the Supplier’s notice, the Project Manager shall:  (a) issue an Operational Acceptance Certificate; or  (b) notify the Supplier in writing of any defect or deficiencies or other reason for the failure of the Operational Acceptance Tests; or  (c) issue the Operational Acceptance Certificate, if the situation covered by GCC Clause 27.3.1 (b) arises.  27.3.4 The Supplier shall use all reasonable endeavors to promptly remedy any defect and/or deficiencies and/or other reasons for the failure of the Operational Acceptance Test that the Project Manager has notified the Supplier of. Once such remedies have been made by the Supplier, the Supplier shall notify the Purchaser, and the Purchaser, with the full cooperation of the Supplier, shall use all reasonable endeavors to promptly carry out retesting of the System or Subsystem. Upon the successful conclusion of the Operational Acceptance Tests, the Supplier shall notify the Purchaser of its request for Operational Acceptance Certification, in accordance with GCC Clause 27.3.3. The Purchaser shall then issue to the Supplier the Operational Acceptance Certification in accordance with GCC Clause 27.3.3 (a), or shall notify the Supplier of further defects, deficiencies, or other reasons for the failure of the Operational Acceptance Test. The procedure set out in this GCC Clause 27.3.4 shall be repeated, as necessary, until an Operational Acceptance Certificate is issued.  27.3.5 If the System or Subsystem fails to pass the Operational Acceptance Test(s) in accordance with GCC Clause 27.2, then either:  (a) the Purchaser may consider terminating the Contract, pursuant to GCC Clause 41.2.2;  or  (b) if the failure to achieve Operational Acceptance within the specified time period is a result of the failure of the Purchaser to fulfill its obligations under the Contract, then the Supplier shall be deemed to have fulfilled its obligations with respect to the relevant technical and functional aspects of the Contract, and GCC Clauses 30.3 and 30.4 shall not apply.  27.3.6 If within fourteen (14) days after receipt of the Supplier’s notice the Project Manager fails to issue the Operational Acceptance Certificate or fails to inform the Supplier in writing of the justifiable reasons why the Project Manager has not issued the Operational Acceptance Certificate, the System or Subsystem shall be deemed to have been accepted as of the date of the Supplier’s said notice.  27.4 Partial Acceptance  27.4.1 If so specified in the SCC for GCC Clause 27.2.1, Installation and Commissioning shall be carried out individually for each identified major component or Subsystem(s) of the System. In this event, the provisions in the Contract relating to Installation and Commissioning, including the Operational Acceptance Test, shall apply to each such major component or Subsystem individually, and Operational Acceptance Certificate(s) shall be issued accordingly for each such major component or Subsystem of the System, subject to the limitations contained in GCC Clause 27.4.2.  27.4.2 The issuance of Operational Acceptance Certificates for individual major components or Subsystems pursuant to GCC Clause 27.4.1 shall not relieve the Supplier of its obligation to obtain an Operational Acceptance Certificate for the System as an integrated whole (if so specified in the SCC for GCC Clauses 12.1 and 27.2.1) once all major components and Subsystems have been supplied, installed, tested, and commissioned.  27.4.3 In the case of minor components for the System that by their nature do not require Commissioning or an Operational Acceptance Test (e.g., minor fittings, furnishings or site works, etc.), the Project Manager shall issue an Operational Acceptance Certificate within fourteen (14) days after the fittings and/or furnishings have been delivered and/or installed or the site works have been completed. The Supplier shall, however, use all reasonable endeavors to promptly remedy any defects or deficiencies in such minor components detected by the Purchaser or Supplier. |

F. Guarantees and Liabilities

|  |  |
| --- | --- |
| 28. Operational Acceptance Time Guarantee | 28.1 The Supplier guarantees that it shall complete the supply, Installation, Commissioning, and achieve Operational Acceptance of the System (or Subsystems, pursuant to the SCC for GCC Clause 27.2.1) within the time periods specified in the Implementation Schedule and/or the Agreed Project Plan pursuant to GCC Clause 8.2, or within such extended time to which the Supplier shall be entitled under GCC Clause 40 (Extension of Time for Achieving Operational Acceptance). |
|  | 28.2 **Unless otherwise specified in the SCC**, if the Supplier fails to supply, install, commission, and achieve Operational Acceptance of the System (or Subsystems pursuant to the SCC for GCC Clause 27.2.1) within the time for achieving Operational Acceptance specified in the Implementation Schedule or the Agreed Project Plan, or any extension of the time for achieving Operational Acceptance previously granted under GCC Clause 40 (Extension of Time for Achieving Operational Acceptance), the Supplier shall pay to the Purchaser liquidated damages at the rate of one half of one percent per week as a percentage of the Contract Price (exclusive of Recurrent Costs if any), or the relevant part of the Contract Price if a Subsystem has not achieved Operational Acceptance. The aggregate amount of such liquidated damages shall in no event exceed the amount of ten (10) percent of the Contract Price (exclusive of Recurrent Costs if any). Once the Maximum is reached, the Purchaser may consider termination of the Contract, pursuant to GCC Clause 41.2.2.  28.3 **Unless otherwise specified in the SCC,** liquidated damages payable under GCC Clause 28.2 shall apply only to the failure to achieve Operational Acceptance of the System (and Subsystems) as specified in the Implementation Schedule and/or Agreed Project Plan. This Clause 28.3 shall not limit, however, any other rights or remedies the Purchaser may have under the Contract for other delays.  28.4 If liquidated damages are claimed by the Purchaser for the System (or Subsystem), the Supplier shall have no further liability whatsoever to the Purchaser in respect to the Operational Acceptance time guarantee for the System (or Subsystem). However, the payment of liquidated damages shall not in any way relieve the Supplier from any of its obligations to complete the System or from any other of its obligations and liabilities under the Contract. |
| 29. Defect Liability | 29.1 The Supplier warrants that the System, including all Information Technologies, Materials, and other Goods supplied and Services provided, shall be free from defects in the design, engineering, Materials, and workmanship that prevent the System and/or any of its components from fulfilling the Technical Requirements or that limit in a material fashion the performance, reliability, or extensibility of the System and/or Subsystems. **Unless otherwise specified in the SCC**, there will be NO exceptions and/or limitations to this warranty with respect to Software (or categories of Software). Commercial warranty provisions of products supplied under the Contract shall apply to the extent that they do not conflict with the provisions of this Contract. |
|  | 29.2 The Supplier also warrants that the Information Technologies, Materials, and other Goods supplied under the Contract are new, unused, and incorporate all recent improvements in design that materially affect the System’s or Subsystem’s ability to fulfill the Technical Requirements.  29.3 **Unless otherwise specified in the SCC,** the Supplier warrants that: (i) all Goods components to be incorporated into the System form part of the Supplier’s and/or Subcontractor’s current product lines, and (ii) they have been previously released to the market.  29.4 **Unless otherwise specified in the SCC**, the Warranty Period shall commence from the date of Operational Acceptance of the System (or of any major component or Subsystem for which separate Operational Acceptance is provided for in the Contract) and shall extend for thirty-six (36) months.  29.5 If during the Warranty Period any defect as described in GCC Clause 29.1 should be found in the design, engineering, Materials, and workmanship of the Information Technologies and other Goods supplied or of the Services provided by the Supplier, the Supplier shall promptly, in consultation and agreement with the Purchaser regarding appropriate remedying of the defects, and at its sole cost, repair, replace, or otherwise make good (as the Supplier shall, at its discretion, determine) such defect as well as any damage to the System caused by such defect. Any defective Information Technologies or other Goods that have been replaced by the Supplier shall remain the property of the Supplier.  29.6 The Supplier shall not be responsible for the repair, replacement, or making good of any defect, or of any damage to the System arising out of or resulting from any of the following causes:  (a) improper operation or maintenance of the System by the Purchaser;  (b) normal wear and tear;  (c) use of the System with items not supplied by the Supplier, unless otherwise identified in the Technical Requirements, or approved by the Supplier; or  (d) modifications made to the System by the Purchaser, or a third party, not approved by the Supplier.  29.7 The Supplier’s obligations under this GCC Clause 29 shall not apply to:  (a) any materials that are normally consumed in operation or have a normal life shorter than the Warranty Period; or  (b) any designs, specifications, or other data designed, supplied, or specified by or on behalf of the Purchaser or any matters for which the Supplier has disclaimed responsibility, in accordance with GCC Clause 21.1.2.  29.8 The Purchaser shall give the Supplier a notice promptly following the discovery of such defect, stating the nature of any such defect together with all available evidence. The Purchaser shall afford all reasonable opportunity for the Supplier to inspect any such defect. The Purchaser shall afford the Supplier all necessary access to the System and the site to enable the Supplier to perform its obligations under this GCC Clause 29.  29.9 The Supplier may, with the consent of the Purchaser, remove from the site any Information Technologies and other Goods that are defective, if the nature of the defect, and/or any damage to the System caused by the defect, is such that repairs cannot be expeditiously carried out at the site. If the repair, replacement, or making good is of such a character that it may affect the efficiency of the System, the Purchaser may give the Supplier notice requiring that tests of the defective part be made by the Supplier immediately upon completion of such remedial work, whereupon the Supplier shall carry out such tests.  If such part fails the tests, the Supplier shall carry out further repair, replacement, or making good (as the case may be) until that part of the System passes such tests. The tests shall be agreed upon by the Purchaser and the Supplier.  29.10 **Unless otherwise specified in the SCC**, the response times and repair/replacement times for Warranty Defect Repair are specified in the Technical Requirements. Nevertheless, if the Supplier fails to commence the work necessary to remedy such defect or any damage to the System caused by such defect within two weeks the Purchaser may, following notice to the Supplier, proceed to do such work or contract a third party (or parties) to do such work, and the reasonable costs incurred by the Purchaser in connection with such work shall be paid to the Purchaser by the Supplier or may be deducted by the Purchaser from any monies due the Supplier or claimed under the Performance Security.  29.11 If the System or Subsystem cannot be used by reason of such defect and/or making good of such defect, the Warranty Period for the System shall be extended by a period equal to the period during which the System or Subsystem could not be used by the Purchaser because of such defect and/or making good of such defect.  29.12 Items substituted for defective parts of the System during the Warranty Period shall be covered by the Defect Liability Warranty for the remainder of the Warranty Period applicable for the part replaced or three (3) months, whichever is greater. For reasons of information security, the Purchaser may choose to retain physical possession of any replaced defective information storage devices.  29.13 At the request of the Purchaser and without prejudice to any other rights and remedies that the Purchaser may have against the Supplier under the Contract, the Supplier will offer all possible assistance to the Purchaser to seek warranty services or remedial action from any subcontracted third-party producers or licensor of Goods included in the System, including without limitation assignment or transfer in favor of the Purchaser of the benefit of any warranties given by such producers or licensors to the Supplier. |
| 30. Functional Guarantees | 30.1 The Supplier guarantees that, once the Operational Acceptance Certificate(s) has been issued, the System represents a complete, integrated solution to the Purchaser’s requirements set forth in the Technical Requirements and it conforms to all other aspects of the Contract. The Supplier acknowledges that GCC Clause 27 regarding Commissioning and Operational Acceptance governs how technical conformance of the System to the Contract requirements will be determined. |
|  | 30.2 If, for reasons attributable to the Supplier, the System does not conform to the Technical Requirements or does not conform to all other aspects of the Contract, the Supplier shall at its cost and expense make such changes, modifications, and/or additions to the System as may be necessary to conform to the Technical Requirements and meet all functional and performance standards. The Supplier shall notify the Purchaser upon completion of the necessary changes, modifications, and/or additions and shall request the Purchaser to repeat the Operational Acceptance Tests until the System achieves Operational Acceptance.  30.3 If the System (or Subsystem[s]) fails to achieve Operational Acceptance, the Purchaser may consider termination of the Contract, pursuant to GCC Clause 41.2.2, and forfeiture of the Supplier’s Performance Security in accordance with GCC Clause 13.3 in compensation for the extra costs and delays likely to result from this failure. |
| 31. Intellectual Property Rights Warranty | 31.1 The Supplier hereby represents and warrants that:  (a) the System as supplied, installed, tested, and accepted;  (b) use of the System in accordance with the Contract; and  (c) copying of the Software and Materials provided to the Purchaser in accordance with the Contract  do not and will not infringe any Intellectual Property Rights held by any third party and that it has all necessary rights or at its sole expense shall have secured in writing all transfers of rights and other consents necessary to make the assignments, licenses, and other transfers of Intellectual Property Rights and the warranties set forth in the Contract, and for the Purchaser to own or exercise all Intellectual Property Rights as provided in the Contract. Without limitation, the Supplier shall secure all necessary written agreements, consents, and transfers of rights from its employees and other persons or entities whose services are used for development of the System. |
| 32. Intellectual Property Rights Indemnity | 32.1 The Supplier shall indemnify and hold harmless the Purchaser and its employees and officers from and against any and all losses, liabilities, and costs (including losses, liabilities, and costs incurred in defending a claim alleging such a liability), that the Purchaser or its employees or officers may suffer as a result of any infringement or alleged infringement of any Intellectual Property Rights by reason of:  (a) installation of the System by the Supplier or the use of the System, including the Materials, in the country where the site is located;  (b) copying of the Software and Materials provided the Supplier in accordance with the Agreement; and |
|  | (c) sale of the products produced by the System in any country, except to the extent that such losses, liabilities, and costs arise as a result of the Purchaser’s breach of GCC Clause 32.2. |
|  | 32.2 Such indemnity shall not cover any use of the System, including the Materials, other than for the purpose indicated by or to be reasonably inferred from the Contract, any infringement resulting from the use of the System, or any products of the System produced thereby in association or combination with any other goods or services not supplied by the Supplier, where the infringement arises because of such association or combination and not because of use of the System in its own right.  32.3 Such indemnities shall also not apply if any claim of infringement:  (a) is asserted by a parent, subsidiary, or affiliate of the Purchaser’s organization;  (b) is a direct result of a design mandated by the Purchaser’s Technical Requirements and the possibility of such infringement was duly noted in the Supplier’s Bid; or  (c) results from the alteration of the System, including the Materials, by the Purchaser or any persons other than the Supplier or a person authorized by the Supplier. |
|  | 32.4 If any proceedings are brought or any claim is made against the Purchaser arising out of the matters referred to in GCC Clause 32.1, the Purchaser shall promptly give the Supplier notice of such proceedings or claims, and the Supplier shall, at its own expense and in the Purchaser’s name repeals and resist the claim and conduct the proceedings or and any negotiations for the settlement of any such proceedings or claim.  If the Supplier fails to notify the Purchaser within twenty-eight (28) days after receipt of such notice that it intends to conduct any such proceedings or claim, then the Purchaser shall be free to conduct the same on its own behalf. Unless the Supplier has so failed to notify the Purchaser within the twenty-eight (28) days, the Purchaser shall make no admission that may be prejudicial to the defense of any such proceedings or claim. The Purchaser shall, at the Supplier’s request, afford all available assistance to the Supplier in conducting such proceedings or claim and shall be reimbursed by the Supplier for all reasonable expenses incurred in so doing. |
|  | 32.5 The Purchaser shall indemnify and hold harmless the Supplier and its employees, officers, and Subcontractors from and against any and all losses, liabilities, and costs (including losses, liabilities, and costs incurred in defending a claim alleging such a liability) that the Supplier or its employees, officers, or Subcontractors may suffer as a result of any infringement or alleged infringement of any Intellectual Property Rights arising out of or in connection with any design, data, drawing, specification, or other documents or materials provided to the Supplier in connection with this Contract by the Purchaser or provided by any other person at the request of the Purchaser, except to the extent that such losses, liabilities, and costs arise as a result of the Supplier’s breach of GCC Clause 32.8. |
|  | 32.6 Such indemnity shall not cover  (a) any use of the design, data, drawing, specification, or other documents or materials, other than for the purpose indicated by or to be reasonably inferred from the Contract;  (b) any infringement resulting from the use of the design, data, drawing, specification, or other documents or materials, or any products produced thereby, in association or combination with any other Goods or Services not provided by the Purchaser or any other person contracted by the Purchaser, where the infringement arises because of such association or combination and not because of the use of the design, data, drawing, specification, or other documents or materials in its own right.  32.7 Such indemnities shall also not apply:  (a) if any claim of infringement is asserted by a parent, subsidiary, or affiliate of the Supplier’s organization;  (b) to the extent that any claim of infringement is caused by the alteration, by the Supplier, or any persons contracted by the Supplier, of the design, data, drawing, specification, or other documents or materials provided to the Supplier by the Purchaser or any persons contracted by the Purchaser.  32.8 If any proceedings are brought or any claim is made against the Supplier arising out of the matters referred to in GCC Clause 32.5, the Supplier shall promptly give the Purchaser notice of such proceedings or claims, and the Purchaser may at its own expense and in the Supplier’s name conduct such proceedings or claim and any negotiations for the settlement of any such proceedings or claim. If the Purchaser fails to notify the Supplier within twenty-eight (28) days after receipt of such notice that it intends to conduct any such proceedings or claim, then the Supplier shall be free to conduct the same on its own behalf. Unless the Purchaser has so failed to notify the Supplier within the twenty-eight (28) days, the Supplier shall make no admission that may be prejudicial to the defense of any such proceedings or claim. The Supplier shall, at the Purchaser’s request, afford all available assistance to the Purchaser in conducting such proceedings or claim and shall be reimbursed by the Purchaser for all reasonable expenses incurred in so doing. |
| 33. Limitation of Liability | 33.1 Provided the following does not exclude or limit any liabilities of either party in ways not permitted by applicable law: |
|  | (a) the Supplier shall not be liable to the Purchaser, whether in contract, tort, or otherwise, for any indirect or consequential loss or damage, loss of use, loss of production, or loss of profits or interest costs, provided that this exclusion shall not apply to any obligation of the Supplier to pay liquidated damages to the Purchaser; and  (b) the aggregate liability of the Supplier to the Purchaser, whether under the Contract, in tort or otherwise, shall not exceed the total Contract Price, provided that this limitation shall not apply to any obligation of the Supplier to indemnify the Purchaser with respect to intellectual property rights infringement. |

G. Risk Distribution

|  |  |
| --- | --- |
| 34. Transfer of Ownership | 34.1 With the exception of Software and Materials, the ownership of the Information Technologies and other Goods shall be transferred to the Purchaser at the time of Delivery or otherwise under terms that may be agreed upon and specified in the Contract Agreement. |
|  | 34.2 Ownership and the terms of usage of the Software and Materials supplied under the Contract shall be governed by GCC Clause 15 (Copyright) Clause 16 (Software License Agreements), and any elaboration in the Technical Requirements.  34.3 Ownership of the Supplier’s Equipment used by the Supplier and its Subcontractors in connection with the Contract shall remain with the Supplier or its Subcontractors. |
| 35. Care of the System | 35.1 The Purchaser shall become responsible for the care and custody of the System or Subsystems upon their Delivery. The Purchaser shall make good at its own cost any loss or damage that may occur to the System or Subsystems from any cause from the date of Delivery until the date of Operational Acceptance of the System or Subsystems, pursuant to GCC Clause 27 (Commissioning and Operational Acceptance), excepting such loss or damage arising from acts or omissions of the Supplier, its employees, or subcontractors.  35.2 If any loss or damage occurs to the System or any part of the System by reason of:  (a) (insofar as they relate to the country where the Project Site is located) nuclear reaction, nuclear radiation, radioactive contamination, a pressure wave caused by aircraft or other aerial objects, or any other occurrences that an experienced Supplier could not reasonably foresee, or if reasonably foreseeable could not reasonably make provision for or insure against, insofar as such risks are not normally insurable on the insurance market and are mentioned in the general exclusions of the policy of insurance taken out under GCC Clause 37;  (b) any use not in accordance with the Contract, by the Purchaser or any third party;  (c) any use of or reliance upon any design, data, or specification provided or designated by or on behalf of the Purchaser, or any such matter for which the Supplier has disclaimed responsibility in accordance with GCC Clause 21.1.2,  the Purchaser shall pay to the Supplier all sums payable in respect of the System or Subsystems that have achieved Operational Acceptance, notwithstanding that the same be lost, destroyed, or damaged. If the Purchaser requests the Supplier in writing to make good any loss or damage to the System thereby occasioned, the Supplier shall make good the same at the cost of the Purchaser in accordance with GCC Clause 39. If the Purchaser does not request the Supplier in writing to make good any loss or damage to the System thereby occasioned, the Purchaser shall either request a change in accordance with GCC Clause 39, excluding the performance of that part of the System thereby lost, destroyed, or damaged, or, where the loss or damage affects a substantial part of the System, the Purchaser shall terminate the Contract pursuant to GCC Clause 41.1.  35.3 The Purchaser shall be liable for any loss of or damage to any Supplier’s Equipment which the Purchaser has authorized to locate within the Purchaser's premises for use in fulfillment of Supplier's obligations under the Contract, except where such loss or damage arises from acts or omissions of the Supplier, its employees, or subcontractors. |
| 36. Loss of or Damage to Property; Accident or Injury to Workers; Indemnification | 36.1 The Supplier and each and every Subcontractor shall abide by the job safety, insurance, customs, and immigration measures prevalent and laws in force in the Purchaser’s Country.  36.2 Subject to GCC Clause 36.3, the Supplier shall indemnify and hold harmless the Purchaser and its employees and officers from and against any and all losses, liabilities and costs (including losses, liabilities, and costs incurred in defending a claim alleging such a liability) that the Purchaser or its employees or officers may suffer as a result of the death or injury of any person or loss of or damage to any property (other than the System, whether accepted or not) arising in connection with the supply, installation, testing, and Commissioning of the System and by reason of the negligence of the Supplier or its Subcontractors, or their employees, officers or agents, except any injury, death, or property damage caused by the negligence of the Purchaser, its contractors, employees, officers, or agents. |
|  | 36.3 If any proceedings are brought or any claim is made against the Purchaser that might subject the Supplier to liability under GCC Clause 36.2, the Purchaser shall promptly give the Supplier notice of such proceedings or claims, and the Supplier shall at its own expense and in the Purchaser’s name conduct such proceedings or claim and any negotiations for the settlement of any such proceedings or claim. If the Supplier fails to notify the Purchaser within twenty-eight (28) days after receipt of such notice that it intends to conduct any such proceedings or claim, then the Purchaser shall be free to conduct the same on its own behalf. Unless the Supplier has so failed to notify the Purchaser within the twenty-eight (28) day period, the Purchaser shall make no admission that may be prejudicial to the defense of any such proceedings or claim. The Purchaser shall, at the Supplier’s request, afford all available assistance to the Supplier in conducting such proceedings or claim and shall be reimbursed by the Supplier for all reasonable expenses incurred in so doing.  36.4 The Purchaser shall indemnify and hold harmless the Supplier and its employees, officers, and Subcontractors from any and all losses, liabilities, and costs (including losses, liabilities, and costs incurred in defending a claim alleging such a liability) that the Supplier or its employees, officers, or Subcontractors may suffer as a result of the death or personal injury of any person or loss of or damage to property of the Purchaser, other than the System not yet achieving Operational Acceptance, that is caused by fire, explosion, or any other perils, in excess of the amount recoverable from insurances procured under GCC Clause 37 (Insurances), provided that such fire, explosion, or other perils were not caused by any act or failure of the Supplier. |
|  | 36.5 If any proceedings are brought or any claim is made against the Supplier that might subject the Purchaser to liability under GCC Clause 36.4, the Supplier shall promptly give the Purchaser notice of such proceedings or claims, and the Purchaser may at its own expense and in the Supplier’s name conduct such proceedings or claim and any negotiations for the settlement of any such proceedings or claim. If the Purchaser fails to notify the Supplier within twenty-eight (28) days after receipt of such notice that it intends to conduct any such proceedings or claim, then the Supplier shall be free to conduct the same on its own behalf. Unless the Purchaser has so failed to notify the Supplier within the twenty-eight (28) days, the Supplier shall make no admission that may be prejudicial to the defense of any such proceedings or claim. The Supplier shall, at the Purchaser’s request, afford all available assistance to the Purchaser in conducting such proceedings or claim and shall be reimbursed by the Purchaser for all reasonable expenses incurred in so doing. |
|  | 36.6 The party entitled to the benefit of an indemnity under this GCC Clause 36 shall take all reasonable measures to mitigate any loss or damage that has occurred. If the party fails to take such measures, the other party’s liabilities shall be correspondingly reduced. |
| 37. Insurances | 37.1 The Supplier shall at its expense take out and maintain in effect, or cause to be taken out and maintained in effect, during the performance of the Contract, the insurance set forth below. The identity of the insurers and the form of the policies shall be subject to the approval of the Purchaser, who should not unreasonably withhold such approval. |
|  | (a) Cargo Insurance During Transport  as applicable, 110 percent of the price of the Information Technologies and other Goods in a freely convertible currency, covering the Goods from physical loss or damage during shipment through receipt at the Project Site.  (b) Installation “All Risks” Insurance  as applicable, 110 percent of the price of the Information Technologies and other Goods covering the Goods at the site from all risks of physical loss or damage (excluding only perils commonly excluded under “all risks” insurance policies of this type by reputable insurers) occurring prior to Operational Acceptance of the System.  (c) Third-Party Liability Insurance  On terms as **specified in the SCC,** covering bodily injury or death suffered by third parties (including the Purchaser’s personnel) and loss of or damage to property (including the Purchaser’s property and any Subsystems that have been accepted by the Purchaser) occurring in connection with the supply and installation of the Information System.  (d) Automobile Liability Insurance  In accordance with the statutory requirements prevailing in the Purchaser’s Country, covering use of all vehicles used by the Supplier or its Subcontractors (whether or not owned by them) in connection with the execution of the Contract.  (e) Other Insurance (if any), as **specified in the SCC.**  37.2 The Purchaser shall be named as co-insured under all insurance policies taken out by the Supplier pursuant to GCC Clause 37.1, except for the Third-Party Liability, and the Supplier’s Subcontractors shall be named as co-insured under all insurance policies taken out by the Supplier pursuant to GCC Clause 37.1 except for Cargo Insurance During Transport. All insurer’s rights of subrogation against such co-insured for losses or claims arising out of the performance of the Contract shall be waived under such policies.  37.3 The Supplier shall deliver to the Purchaser certificates of insurance (or copies of the insurance policies) as evidence that the required policies are in full force and effect.  37.4 The Supplier shall ensure that, where applicable, its Subcontractor(s) shall take out and maintain in effect adequate insurance policies for their personnel and vehicles and for work executed by them under the Contract, unless such Subcontractors are covered by the policies taken out by the Supplier.  37.5 If the Supplier fails to take out and/or maintain in effect the insurance referred to in GCC Clause 37.1, the Purchaser may take out and maintain in effect any such insurance and may from time to time deduct from any amount due the Supplier under the Contract any premium that the Purchaser shall have paid to the insurer or may otherwise recover such amount as a debt due from the Supplier.  37.6 Unless otherwise provided in the Contract, the Supplier shall prepare and conduct all and any claims made under the policies affected by it pursuant to this GCC Clause 37, and all monies payable by any insurers shall be paid to the Supplier. The Purchaser shall give to the Supplier all such reasonable assistance as may be required by the Supplier in connection with any claim under the relevant insurance policies. With respect to insurance claims in which the Purchaser’s interest is involved, the Supplier shall not give any release or make any compromise with the insurer without the prior written consent of the Purchaser. With respect to insurance claims in which the Supplier’s interest is involved, the Purchaser shall not give any release or make any compromise with the insurer without the prior written consent of the Supplier. |
| 38. Force Majeure | 38.1 “Force Majeure” shall mean any event beyond the reasonable control of the Purchaser or of the Supplier, as the case may be, and which is unavoidable notwithstanding the reasonable care of the party affected and shall include, without limitation, the following: |
|  | (a) war, hostilities, or warlike operations (whether a state of war be declared or not), invasion, act of foreign enemy, and civil war;  (b) rebellion, revolution, insurrection, mutiny, usurpation of civil or military government, conspiracy, riot, civil commotion, and terrorist acts;  (c) confiscation, nationalization, mobilization, commandeering or requisition by or under the order of any government or de jure or de facto authority or ruler, or any other act or failure to act of any local state or national government authority;  (d) strike, sabotage, lockout, embargo, import restriction, port congestion, lack of usual means of public transportation and communication, industrial dispute, shipwreck, shortage or restriction of power supply, epidemics, quarantine, and plague;  (e) earthquake, landslide, volcanic activity, fire, flood or inundation, tidal wave, typhoon or cyclone, hurricane, storm, lightning, or other inclement weather condition, nuclear and pressure waves, or other natural or physical disaster;  (f) failure, by the Supplier, to obtain the necessary export permit(s) from the governments of the Country(s) of Origin of the Information Technologies or other Goods, or Supplier’s Equipment provided that the Supplier has made all reasonable efforts to obtain the required export permit(s), including the exercise of due diligence in determining the eligibility of the System and all of its components for receipt of the necessary export permits.  38.2 If either party is prevented, hindered, or delayed from or in performing any of its obligations under the Contract by an event of Force Majeure, then it shall notify the other in writing of the occurrence of such event and the circumstances of the event of Force Majeure within fourteen (14) days after the occurrence of such event.  38.3 The party who has given such notice shall be excused from the performance or punctual performance of its obligations under the Contract for so long as the relevant event of Force Majeure continues and to the extent that such party’s performance is prevented, hindered, or delayed. The Time for Achieving Operational Acceptance shall be extended in accordance with GCC Clause 40 (Extension of Time for Achieving Operational Acceptance).  38.4 The party or parties affected by the event of Force Majeure shall use reasonable efforts to mitigate the effect of the event of Force Majeure upon its or their performance of the Contract and to fulfill its or their obligations under the Contract, but without prejudice to either party’s right to terminate the Contract under GCC Clause 38.6.  38.5 No delay or nonperformance by either party to this Contract caused by the occurrence of any event of Force Majeure shall:  (a) constitute a default or breach of the Contract;  (b) (subject to GCC Clauses 35.2, 38.3, and 38.4) give rise to any claim for damages or additional cost or expense occasioned by the delay or nonperformance,  if, and to the extent that, such delay or nonperformance is caused by the occurrence of an event of Force Majeure.  38.6 If the performance of the Contract is substantially prevented, hindered, or delayed for a single period of more than sixty (60) days or an aggregate period of more than one hundred and twenty (120) days on account of one or more events of Force Majeure during the time period covered by the Contract, the parties will attempt to develop a mutually satisfactory solution, failing which, either party may terminate the Contract by giving a notice to the other.  38.7 In the event of termination pursuant to GCC Clause 38.6, the rights and obligations of the Purchaser and the Supplier shall be as specified in GCC Clauses 41.1.2 and 41.1.3.  38.8 Notwithstanding GCC Clause 38.5, Force Majeure shall not apply to any obligation of the Purchaser to make payments to the Supplier under this Contract. |

H. Change in Contract Elements

|  |  |
| --- | --- |
| 39. Changes to the System | 39.1 Introducing a Change  39.1.1 Subject to GCC Clauses 39.2.5 and 39.2.7, the Purchaser shall have the right to propose, and subsequently require, the Project Manager to order the Supplier from time to time during the performance of the Contract to make any change, modification, addition, or deletion to, in, or from the System (interchangeably called “Change”), provided that such Change falls within the general scope of the System, does not constitute unrelated work, and is technically practicable, taking into account both the state of advancement of the System and the technical compatibility of the Change envisaged with the nature of the System as originally specified in the Contract. |
|  | A Change may involve, but is not restricted to, the substitution of updated Information Technologies and related Services in accordance with GCC Clause 23 (Product Upgrades). |
|  | 39.1.2 The Supplier may from time to time during its performance of the Contract propose to the Purchaser (with a copy to the Project Manager) any Change that the Supplier considers necessary or desirable to improve the quality or efficiency of the System. The Purchaser may at its discretion approve or reject any Change proposed by the Supplier.  39.1.3 Notwithstanding GCC Clauses 39.1.1 and 39.1.2, no change made necessary because of any default of the Supplier in the performance of its obligations under the Contract shall be deemed to be a Change, and such change shall not result in any adjustment of the Contract Price or the Time for Achieving Operational Acceptance.  39.1.4 The procedure on how to proceed with and execute Changes is specified in GCC Clauses 39.2 and 39.3, and further details and sample forms are provided in the Sample Contractual Forms Section in the bidding documents.  39.1.5 Moreover, the Purchaser and Supplier will agree, during development of the Project Plan, to a date prior to the scheduled date for Operational Acceptance, after which the Technical Requirements for the System shall be “frozen.” Any Change initiated after this time will be dealt with after Operational Acceptance.  39.2 Changes Originating from Purchaser  39.2.1 If the Purchaser proposes a Change pursuant to GCC Clauses 39.1.1, it shall send to the Supplier a “Request for Change Proposal,” requiring the Supplier to prepare and furnish to the Project Manager as soon as reasonably practicable a “Change Proposal,” which shall include the following:  (a) brief description of the Change;  (b) impact on the Time for Achieving Operational Acceptance;  (c) detailed estimated cost of the Change;  (d) effect on Functional Guarantees (if any);  (e) effect on any other provisions of the Contract.  39.2.2 Prior to preparing and submitting the “Change Proposal,” the Supplier shall submit to the Project Manager a “Change Estimate Proposal,” which shall be an estimate of the cost of preparing the Change Proposal, plus a first approximation of the suggested approach and cost for implementing the changes. Upon receipt of the Supplier’s Change Estimate Proposal, the Purchaser shall do one of the following:  (a) accept the Supplier’s estimate with instructions to the Supplier to proceed with the preparation of the Change Proposal;  (b) advise the Supplier of any part of its Change Estimate Proposal that is unacceptable and request the Supplier to review its estimate;  (c) advise the Supplier that the Purchaser does not intend to proceed with the Change.  39.2.3 Upon receipt of the Purchaser’s instruction to proceed under GCC Clause 39.2.2 (a), the Supplier shall, with proper expedition, proceed with the preparation of the Change Proposal, in accordance with GCC Clause 39.2.1. The Supplier, at its discretion, may specify a validity period for the Change Proposal, after which if the Purchaser and Supplier has not reached agreement in accordance with GCC Clause 39.2.6, then GCC Clause 39.2.7 shall apply.  39.2.4 The pricing of any Change shall, as far as practicable, be calculated in accordance with the rates and prices included in the Contract. If the nature of the Change is such that the Contract rates and prices are inequitable, the parties to the Contract shall agree on other specific rates to be used for valuing the Change.  39.2.5 If before or during the preparation of the Change Proposal it becomes apparent that the aggregate impact of compliance with the Request for Change Proposal and with all other Change Orders that have already become binding upon the Supplier under this GCC Clause 39 would be to increase or decrease the Contract Price as originally set forth in Article 2 (Contract Price) of the Contract Agreement by more than fifteen (15) percent, the Supplier may give a written notice of objection to this Request for Change Proposal prior to furnishing the Change Proposal. If the Purchaser accepts the Supplier’s objection, the Purchaser shall withdraw the proposed Change and shall notify the Supplier in writing of its acceptance.  The Supplier’s failure to so object to a Request for Change Proposal shall neither affect its right to object to any subsequent requested Changes or Change Orders, nor affect its right to take into account, when making such subsequent objection, the percentage increase or decrease in the Contract Price that any Change not objected to by the Supplier represents.  39.2.6 Upon receipt of the Change Proposal, the Purchaser and the Supplier shall mutually agree upon all matters contained in the Change Proposal. Within fourteen (14) days after such agreement, the Purchaser shall, if it intends to proceed with the Change, issue the Supplier a Change Order. If the Purchaser is unable to reach a decision within fourteen (14) days, it shall notify the Supplier with details of when the Supplier can expect a decision. If the Purchaser decides not to proceed with the Change for whatever reason, it shall, within the said period of fourteen (14) days, notify the Supplier accordingly. Under such circumstances, the Supplier shall be entitled to reimbursement of all costs reasonably incurred by it in the preparation of the Change Proposal, provided that these do not exceed the amount given by the Supplier in its Change Estimate Proposal submitted in accordance with GCC Clause 39.2.2.  39.2.7 If the Purchaser and the Supplier cannot reach agreement on the price for the Change, an equitable adjustment to the Time for Achieving Operational Acceptance, or any other matters identified in the Change Proposal, the Change will not be implemented. However, this provision does not limit the rights of either party under GCC Clause 6 (Settlement of Disputes).  39.3 Changes Originating from Supplier  If the Supplier proposes a Change pursuant to GCC Clause 39.1.2, the Supplier shall submit to the Project Manager a written “Application for Change Proposal,” giving reasons for the proposed Change and including the information specified in GCC Clause 39.2.1. Upon receipt of the Application for Change Proposal, the parties shall follow the procedures outlined in GCC Clauses 39.2.6 and 39.2.7. However, should the Purchaser choose not to proceed or the Purchaser and the Supplier cannot come to agreement on the change during any validity period that the Supplier may specify in its Application for Change Proposal, the Supplier shall not be entitled to recover the costs of preparing the Application for Change Proposal, unless subject to an agreement between the Purchaser and the Supplier to the contrary.  39.4 Value engineering. The Supplier may prepare, at its own cost, a value engineering proposal at any time during the performance of the Contract. The value engineering proposal shall, at a minimum, include the following;  (a) the proposed change(s), and a description of the difference to the existing Contract requirements;  (b) a full cost/benefit analysis of the proposed change(s) including a description and estimate of costs (including life cycle costs) the Purchaser may incur in implementing the value engineering proposal; and  (c) a description of any effect(s) of the change on performance/functionality.  The Purchaser may accept the value engineering proposal if the proposal demonstrates benefits that:  (a) accelerates the delivery period; or  (b) reduces the Contract Price or the life cycle costs to the Purchaser; or  (c) improves the quality, efficiency, safety or sustainability of the systems; or  (d) yields any other benefits to the Purchaser,  without compromising the necessary functions of the systems.  If the value engineering proposal is approved by the Purchaser and results in:  (a) a reduction of the Contract Price; the amount to be paid to the Supplier shall be the percentage specified in the SCC of the reduction in the Contract Price; or  (b) an increase in the Contract Price; but results in a reduction in life cycle costs due to any benefit described in (a) to (d) above,  the amount to be paid to the Supplier shall be the full increase in the Contract Price. |
| 40. Extension of Time for Achieving Operational Acceptance | 40.1 The time(s) for achieving Operational Acceptance specified in the Schedule of Implementation shall be extended if the Supplier is delayed or impeded in the performance of any of its obligations under the Contract by reason of any of the following: |
|  | (a) any Change in the System as provided in GCC Clause 39 (Change in the Information System);  (b) any occurrence of Force Majeure as provided in GCC Clause 38 (Force Majeure);  (c) default of the Purchaser; or  (d) any other matter specifically mentioned in the Contract;  by such period as shall be fair and reasonable in all the circumstances and as shall fairly reflect the delay or impediment sustained by the Supplier.  40.2 Except where otherwise specifically provided in the Contract, the Supplier shall submit to the Project Manager a notice of a claim for an extension of the time for achieving Operational Acceptance, together with particulars of the event or circumstance justifying such extension as soon as reasonably practicable after the commencement of such event or circumstance. As soon as reasonably practicable after receipt of such notice and supporting particulars of the claim, the Purchaser and the Supplier shall agree upon the period of such extension. In the event that the Supplier does not accept the Purchaser’s estimate of a fair and reasonable time extension, the Supplier shall be entitled to refer the matter to the provisions for the Settlement of Disputes pursuant to GCC Clause 43.  40.3 The Supplier shall at all times use its reasonable efforts to minimize any delay in the performance of its obligations under the Contract. |
| 41. Termination | 41.1 Termination for Purchaser’s Convenience |
|  | 41.1.1 The Purchaser may at any time terminate the Contract for any reason by giving the Supplier a notice of termination that refers to this GCC Clause 41.1.  41.1.2 Upon receipt of the notice of termination under GCC Clause 41.1.1, the Supplier shall either as soon as reasonably practical or upon the date specified in the notice of termination  (a) cease all further work, except for such work as the Purchaser may specify in the notice of termination for the sole purpose of protecting that part of the System already executed, or any work required to leave the site in a clean and safe condition;  (b) terminate all subcontracts, except those to be assigned to the Purchaser pursuant to GCC Clause 41.1.2 (d) (ii) below;  (c) remove all Supplier’s Equipment from the site, repatriate the Supplier’s and its Subcontractors’ personnel from the site, remove from the site any wreckage, rubbish, and debris of any kind;  (d) in addition, the Supplier, subject to the payment specified in GCC Clause 41.1.3, shall  (i) deliver to the Purchaser the parts of the System executed by the Supplier up to the date of termination;  (ii) to the extent legally possible, assign to the Purchaser all right, title, and benefit of the Supplier to the System, or Subsystem, as at the date of termination, and, as may be required by the Purchaser, in any subcontracts concluded between the Supplier and its Subcontractors;  (iii) deliver to the Purchaser all nonproprietary drawings, specifications, and other documents prepared by the Supplier or its Subcontractors as of the date of termination in connection with the System.  41.1.3 In the event of termination of the Contract under GCC Clause 41.1.1, the Purchaser shall pay to the Supplier the following amounts:  (a) the Contract Price, properly attributable to the parts of the System executed by the Supplier as of the date of termination;  (b) the costs reasonably incurred by the Supplier in the removal of the Supplier’s Equipment from the site and in the repatriation of the Supplier’s and its Subcontractors’ personnel;  (c) any amount to be paid by the Supplier to its Subcontractors in connection with the termination of any subcontracts, including any cancellation charges;  (d) costs incurred by the Supplier in protecting the System and leaving the site in a clean and safe condition pursuant to GCC Clause 41.1.2 (a); and  (e) the cost of satisfying all other obligations, commitments, and claims that the Supplier may in good faith have undertaken with third parties in connection with the Contract and that are not covered by GCC Clauses 41.1.3 (a) through (d) above.  41.2 Termination for Supplier’s Default  41.2.1 The Purchaser, without prejudice to any other rights or remedies it may possess, may terminate the Contract forthwith in the following circumstances by giving a notice of termination and its reasons therefore to the Supplier, referring to this GCC Clause 41.2:  (a) if the Supplier becomes bankrupt or insolvent, has a receiving order issued against it, compounds with its creditors, or, if the Supplier is a corporation, a resolution is passed or order is made for its winding up (other than a voluntary liquidation for the purposes of amalgamation or reconstruction), a receiver is appointed over any part of its undertaking or assets, or if the Supplier takes or suffers any other analogous action in consequence of debt;  (b) if the Supplier assigns or transfers the Contract or any right or interest therein in violation of the provision of GCC Clause 42 (Assignment); or  (c) if the Supplier, in the judgment of the Purchaser has engaged in Fraud and Corruption, as defined in paragraph 2.2 a. of the Appendix to the GCC, in competing for or in executing the Contract, including but not limited to willful misrepresentation of facts concerning ownership of Intellectual Property Rights in, or proper authorization and/or licenses from the owner to offer, the hardware, software, or materials provided under this Contract.  41.2.2 If the Supplier:  (a) has abandoned or repudiated the Contract;  (b) has without valid reason failed to commence work on the System promptly;  (c) persistently fails to execute the Contract in accordance with the Contract or persistently neglects to carry out its obligations under the Contract without just cause;  (d) refuses or is unable to provide sufficient Materials, Services, or labor to execute and complete the System in the manner specified in the Agreed Project Plan furnished under GCC Clause 19 at rates of progress that give reasonable assurance to the Purchaser that the Supplier can attain Operational Acceptance of the System by the Time for Achieving Operational Acceptance as extended;  then the Purchaser may, without prejudice to any other rights it may possess under the Contract, give a notice to the Supplier stating the nature of the default and requiring the Supplier to remedy the same. If the Supplier fails to remedy or to take steps to remedy the same within thirty (30) days of its receipt of such notice, then the Purchaser may terminate the Contract forthwith by giving a notice of termination to the Supplier that refers to this GCC Clause 41.2.  41.2.3 Upon receipt of the notice of termination under GCC Clauses 41.2.1 or 41.2.2, the Supplier shall, either immediately or upon such date as is specified in the notice of termination:  (a) cease all further work, except for such work as the Purchaser may specify in the notice of termination for the sole purpose of protecting that part of the System already executed or any work required to leave the site in a clean and safe condition;  (b) terminate all subcontracts, except those to be assigned to the Purchaser pursuant to GCC Clause 41.2.3 (d) below;  (c) deliver to the Purchaser the parts of the System executed by the Supplier up to the date of termination;  (d) to the extent legally possible, assign to the Purchaser all right, title and benefit of the Supplier to the System or Subsystems as at the date of termination, and, as may be required by the Purchaser, in any subcontracts concluded between the Supplier and its Subcontractors;  (e) deliver to the Purchaser all drawings, specifications, and other documents prepared by the Supplier or its Subcontractors as at the date of termination in connection with the System.  41.2.4 The Purchaser may enter upon the site, expel the Supplier, and complete the System itself or by employing any third party. Upon completion of the System or at such earlier date as the Purchaser thinks appropriate, the Purchaser shall give notice to the Supplier that such Supplier’s Equipment will be returned to the Supplier at or near the site and shall return such Supplier’s Equipment to the Supplier in accordance with such notice. The Supplier shall thereafter without delay and at its cost remove or arrange removal of the same from the site.  41.2.5 Subject to GCC Clause 41.2.6 and without prejudice to the rights or remedies the Purchaser may possess, the Supplier shall be entitled to be paid the Contract Price attributable to the portion of the System executed as at the date of termination and the costs, if any, incurred in protecting the System and in leaving the site in a clean and safe condition pursuant to GCC Clause 41.2.3 (a). Any sums due the Purchaser from the Supplier accruing prior to the date of termination shall be deducted from the amount to be paid to the Supplier under this Contract.  41.2.6 If the Purchaser completes the System, the cost of completing the System by the Purchaser shall be determined. If the sum that the Supplier is entitled to be paid, pursuant to GCC Clause 41.2.5, plus the reasonable costs incurred by the Purchaser in completing the System, exceeds the Contract Price, the Supplier shall be liable for such excess. If such excess is greater than the sums due the Supplier under GCC Clause 41.2.5, the Supplier shall pay the balance to the Purchaser, and if such excess is less than the sums due the Supplier under GCC Clause 41.2.5, the Purchaser shall pay the balance to the Supplier. The Purchaser and the Supplier shall agree, in writing, on the computation described above and the manner in which any sums shall be paid.  41.3 Termination by Supplier  41.3.1 If:  (a) the Purchaser has failed to pay the Supplier any sum due under the Contract within the specified period, has failed to approve any invoice or supporting documents without just cause **pursuant to the SCC,** or commits a substantial breach of the Contract, the Supplier may give a notice to the Purchaser that requires payment of such sum, , requires approval of such invoice or supporting documents, or specifies the breach and requires the Purchaser to remedy the same, as the case may be. If the Purchaser fails to pay such sum, fails to approve such invoice or supporting documents or give its reasons for withholding such approval, fails to remedy the breach or take steps to remedy the breach within fourteen (14) days after receipt of the Supplier’s notice; or  (b) the Supplier is unable to carry out any of its obligations under the Contract for any reason attributable to the Purchaser, including but not limited to the Purchaser’s failure to provide possession of or access to the site or other areas or failure to obtain any governmental permit necessary for the execution and/or completion of the System;  then the Supplier may give a notice to the Purchaser of such events, and if the Purchaser has failed to pay the outstanding sum, to approve the invoice or supporting documents, to give its reasons for withholding such approval, or to remedy the breach within twenty-eight (28) days of such notice, or if the Supplier is still unable to carry out any of its obligations under the Contract for any reason attributable to the Purchaser within twenty-eight (28) days of the said notice, the Supplier may by a further notice to the Purchaser referring to this GCC Clause 41.3.1, forthwith terminate the Contract.  41.3.2 The Supplier may terminate the Contract immediately by giving a notice to the Purchaser to that effect, referring to this GCC Clause 41.3.2, if the Purchaser becomes bankrupt or insolvent, has a receiving order issued against it, compounds with its creditors, or, being a corporation, if a resolution is passed or order is made for its winding up (other than a voluntary liquidation for the purposes of amalgamation or reconstruction), a receiver is appointed over any part of its undertaking or assets, or if the Purchaser takes or suffers any other analogous action in consequence of debt.  41.3.3 If the Contract is terminated under GCC Clauses 41.3.1 or 41.3.2, then the Supplier shall immediately:  (a) cease all further work, except for such work as may be necessary for the purpose of protecting that part of the System already executed, or any work required to leave the site in a clean and safe condition;  (b) terminate all subcontracts, except those to be assigned to the Purchaser pursuant to Clause 41.3.3 (d) (ii);  (c) remove all Supplier’s Equipment from the site and repatriate the Supplier’s and its Subcontractor’s personnel from the site.  (d) In addition, the Supplier, subject to the payment specified in GCC Clause 41.3.4, shall:  (i) deliver to the Purchaser the parts of the System executed by the Supplier up to the date of termination;  (ii) to the extent legally possible, assign to the Purchaser all right, title, and benefit of the Supplier to the System, or Subsystems, as of the date of termination, and, as may be required by the Purchaser, in any subcontracts concluded between the Supplier and its Subcontractors;  (iii) to the extent legally possible, deliver to the Purchaser all drawings, specifications, and other documents prepared by the Supplier or its Subcontractors as of the date of termination in connection with the System.  41.3.4 If the Contract is terminated under GCC Clauses 41.3.1 or 41.3.2, the Purchaser shall pay to the Supplier all payments specified in GCC Clause 41.1.3 and reasonable compensation for all loss, except for loss of profit, or damage sustained by the Supplier arising out of, in connection with, or in consequence of such termination.  41.3.5 Termination by the Supplier pursuant to this GCC Clause 41.3 is without prejudice to any other rights or remedies of the Supplier that may be exercised in lieu of or in addition to rights conferred by GCC Clause 41.3.  41.4 In this GCC Clause 41, the expression “portion of the System executed” shall include all work executed, Services provided, and all Information Technologies, or other Goods delivered (or subject to a legally binding obligation to purchase) by the Supplier and used or intended to be used for the purpose of the System, up to and including the date of termination.  41.5 In this GCC Clause 41, in calculating any monies due from the Purchaser to the Supplier, account shall be taken of any sum previously paid by the Purchaser to the Supplier under the Contract, including any advance payment paid **pursuant to the SCC.** |
| 42. Assignment | 42.l Neither the Purchaser nor the Supplier shall, without the express prior written consent of the other, assign to any third party the Contract or any part thereof, or any right, benefit, obligation, or interest therein or thereunder, except that the Supplier shall be entitled to assign either absolutely or by way of charge any monies due and payable to it or that may become due and payable to it under the Contract. |

I. Settlement of Disputes

|  |  |
| --- | --- |
| 43. Settlement of Disputes | 43.1 Adjudication |
|  | 43.1.1 If any dispute of any kind whatsoever shall arise between the Purchaser and the Supplier in connection with or arising out of the Contract, including without prejudice to the generality of the foregoing, any question regarding its existence, validity, or termination, or the operation of the System (whether during the progress of implementation or after its achieving Operational Acceptance and whether before or after the termination, abandonment, or breach of the Contract), the parties shall seek to resolve any such dispute by mutual consultation. If the parties fail to resolve such a dispute by mutual consultation within fourteen (14) days after one party has notified the other in writing of the dispute, then, if the Contract Agreement in Appendix 2 includes and names an Adjudicator, the dispute shall, within another fourteen (14) days, be referred in writing by either party to the Adjudicator, with a copy to the other party. If there is no Adjudicator specified in the Contract Agreement, the mutual consultation period stated above shall last twenty-eight (28) days (instead of fourteen), upon expiry of which either party may move to the notification of arbitration pursuant to GCC Clause 43.2.1. |
|  | 43.1.2 The Adjudicator shall give his or her decision in writing to both parties within twenty-eight (28) days of the dispute being referred to the Adjudicator. If the Adjudicator has done so, and no notice of intention to commence arbitration has been given by either the Purchaser or the Supplier within fifty-six (56) days of such reference, the decision shall become final and binding upon the Purchaser and the Supplier. Any decision that has become final and binding shall be implemented by the parties forthwith.  43.1.3 The Adjudicator shall be paid an hourly fee at the rate specified in the Contract Agreement plus reasonable expenditures incurred in the execution of duties as Adjudicator, and these costs shall be divided equally between the Purchaser and the Supplier.  43.1.4 Should the Adjudicator resign or die, or should the Purchaser and the Supplier agree that the Adjudicator is not fulfilling his or her functions in accordance with the provisions of the Contract, a new Adjudicator shall be jointly appointed by the Purchaser and the Supplier. Failing agreement between the two within twenty-eight (28) days, the new Adjudicator shall be appointed at the request of either party by the Appointing Authority **specified in the SCC,** or, if no Appointing Authority is **specified in SCC,** the Contract shall, from this point onward and until the parties may otherwise agree on an Adjudicator or an Appointing Authority, be implemented as if there is no Adjudicator.  43.2 Arbitration  43.2.1 If  (a) the Purchaser or the Supplier is dissatisfied with the Adjudicator’s decision and acts before this decision has become final and binding pursuant to GCC Clause 43.1.2, or  (b) the Adjudicator fails to give a decision within the allotted time from referral of the dispute pursuant to GCC Clause 43.1.2, and the Purchaser or the Supplier acts within the following fourteen (14) days, or  (c) in the absence of an Adjudicator from the Contract Agreement, the mutual consultation pursuant to GCC Clause 43.1.1 expires without resolution of the dispute and the Purchaser or the Supplier acts within the following fourteen (14) days,  then either the Purchaser or the Supplier may act to give notice to the other party, with a copy for information to the Adjudicator in case an Adjudicator had been involved, of its intention to commence arbitration, as provided below, as to the matter in dispute, and no arbitration in respect of this matter may be commenced unless such notice is given.  43.2.2 Any dispute in respect of which a notice of intention to commence arbitration has been given, in accordance with GCC Clause 43.2.1, shall be finally settled by arbitration. Arbitration may be commenced prior to or after Installation of the Information System.  43.2.3 Arbitration proceedings shall be conducted in accordance with the rules of procedure **specified in the SCC.**  43.3 Notwithstanding any reference to the Adjudicator or arbitration in this clause,  (a) the parties shall continue to perform their respective obligations under the Contract unless they otherwise agree;  (b) the Purchaser shall pay the Supplier any monies due to the Supplier. |

**APPENDIX**

**IsDB’s Policy – Corrupt and Fraudulent Practices**

***(Text in this Appendix shall not be modified)***

Guidelines for Procurement of Goods, Works and related services under Islamic Development Project Financing, April 2019:

**Fraud and Corruption:**

1.39 It is IsDB’s policy to require that Beneficiaries as well as Firms, Contractors and their agents (whether declared or not), sub-contractors, sub-consultants, service providers or Suppliers, and any personnel, observe the highest standard of ethics during the selection and execution of IsDB financed contracts[[24]](#footnote-25). In pursuance of this policy, the requirements of *IsDB Group Anti-Corruption Guidelines on Preventing and Combating Fraud and Corruption in IsDB Group-Financed Projects* and sanctions procedures shall be observed at all times. IsDB:

1. defines, for the purposes of this provision, the terms set forth as follows:
2. “corrupt practice” is the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence improperly the actions of another party;
3. “fraudulent practice” is any act or omission, including misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain financial or other benefit or to avoid an obligation;
4. “collusive practices” is an arrangement between two or more parties designed to achieve an improper purpose, including to influence improperly the actions of another party;
5. “coercive practices” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party; and
6. “obstructive practice” is deliberately destroying, falsifying, altering, or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede an IsDB investigation into allegations of a corrupt, fraudulent, coercive, or collusive practice; and/or threatening, harassing, or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation; or acts intended to materially impede the exercise of IsDB inspection and audit rights provided for under Paragraph 1.39(e) below.
7. will reject a Bid for award if it determines that the Bidder recommended for award, or any of its personnel, or its agents, or its sub-consultants, sub-contractors, service providers, Suppliers and/or their employees, has, directly or indirectly, engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices in competing for the contract in question;
8. will declare misprocurement and cancel the portion of the Project Financing allocated to a contract if it determines at any time that representatives of the Beneficiary or of a recipient of any part of the proceeds of the Project Financing engaged in corrupt, fraudulent, collusive, coercive, or obstructive practices during the procurement or the implementation of the contract in question, without the Beneficiary having taken timely and appropriate action satisfactory to IsDB to address such practices when they occur, including by failing to inform IsDB in a timely manner at the time they knew of the practices;
9. will sanction a Firm or individual, at any time, in accordance with the prevailing IsDB sanctions procedures[[25]](#footnote-26), including by publicly declaring such Firm or individual ineligible, either indefinitely or for a stated period of time:
10. to be awarded a IsDB-financed contract; and
11. to be a nominated sub-contractor, consultant, sub-consultant, Contractor or Supplier of an otherwise eligible Firm being awarded a IsDB-financed contract; and
12. will require that a clause be included in Bidding Documents and in contracts financed by IsDB, requiring Bidders, including their agents (whether declared or not), sub-contractors, sub-consultants, service providers or Suppliers, to permit IsDB to inspect all accounts, records and other documents relating to the submission of Bids and contract performance, and to have them audited by auditors appointed by IsDB.

Section IX - Special Conditions of Contract

## Table of Clauses

[A. Contract and Interpretation 244](#_Toc42782247)

[Definitions (GCC Clause 1) 244](#_Toc42782248)

[Notices ( GCC Clause 4) 244](#_Toc42782249)

[B. Subject Matter of Contract 245](#_Toc42782250)

[Scope of the System ( GCC Clause 7) 245](#_Toc42782251)

[Time for Commencement and Operational Acceptance ( GCC Clause 8) 246](#_Toc42782252)

[Supplier’s Responsibilities ( GCC Clause 9) 246](#_Toc42782253)

[C. Payment 246](#_Toc42782254)

[Contract Price ( GCC Clause 11) 246](#_Toc42782255)

[Terms of Payment ( GCC Clause 12) 247](#_Toc42782256)

[Securities ( GCC Clause 13) 249](#_Toc42782257)

[D. Intellectual Property 250](#_Toc42782258)

[Copyright ( GCC Clause 15) 250](#_Toc42782259)

[Software License Agreements ( GCC Clause 16) 253](#_Toc42782260)

[Confidential Information ( GCC Clause 17) 254](#_Toc42782261)

[E. Supply, Installation, Testing, Commissioning, and Acceptance of the System 255](#_Toc42782262)

[Representatives ( GCC Clause 18) 255](#_Toc42782263)

[Project Plan ( GCC Clause 19) 255](#_Toc42782264)

[Design and Engineering ( GCC Clause 21) 256](#_Toc42782265)

[Product Upgrades ( GCC Clause 23) 257](#_Toc42782266)

[Inspections and Tests ( GCC Clause 25) 257](#_Toc42782267)

[Commissioning and Operational Acceptance ( GCC Clause 27) 258](#_Toc42782268)

[F. Guarantees and Liabilities 258](#_Toc42782269)

[Operational Acceptance Time Guarantee ( GCC Clause 28) 258](#_Toc42782270)

[Defect Liability ( GCC Clause 29) 259](#_Toc42782271)

[Functional Guarantees ( GCC Clause 30) 260](#_Toc42782272)

[G. Risk Distribution 260](#_Toc42782273)

[Insurances ( GCC Clause 37) 260](#_Toc42782274)

[H. Change in Contract Elements 261](#_Toc42782275)

[Changes to the System ( GCC Clause 39) 261](#_Toc42782276)

[I. Settlement of Disputes 261](#_Toc42782277)

[Settlement of Disputes (GCC Clause 43) 261](#_Toc42782278)

**Special Conditions of Contract**

The following Special Conditions of Contract (SCC) shall supplement or amend the General Conditions of Contract (GCC). Whenever there is a conflict, the provisions of the SCC shall prevail over those in the General Conditions of Contract. For the purposes of clarity, any referenced GCC clause numbers are indicated in the left column of the SCC.

A. Contract and Interpretation

Definitions (GCC Clause 1)

|  |  |
| --- | --- |
| GCC 1.1 (a) (ix) | The applicable edition of the Procurement Guidelinesis dated: [ insert: April 2019]. |
| GCC 1.1 (b) (i) | The Purchaser is: [ insert: complete legal name of the Purchaser ]. |
| GCC 1.1 (b) (ii) | The Project Manager is: [ insert: name and/or the official title of Project Manager ]. GCC |
| GCC 1.1 (e) (i) | The Purchaser’s Country is: [ insert: name of country ]. |
| GCC 1.1 (e) (x) | There are no Special Conditions associated with GCC 1.1 (e) (x).  [Note: ***The GCC default specifies the Contract Period as when all the Supplier’s obligations are completed. If there is a reason to set a hard-and-fast calendar date for the Contract Period to end, then specify here]*** |
| GCC 1.1 (e) (xiii) | The Post-Warranty Services Period is [insert: number of months] starting with the completion of the Warranty Period. |

Notices ( GCC Clause 4)

|  |  |
| --- | --- |
| GCC 4.3 | Address of the Project Manager: [ as appropriate, insert: personal delivery, postal, facsimile, email, and/or EDI addresses. ]  Fallback address of the Purchaser: [ as appropriate, insert: personal delivery, postal, facsimile, email, and/or EDI addresses. ]  ***[Note:*** *If the Purchaser wishes to use Electronic Data Interchange (EDI) to communicate with the Supplier, it should specify the standards and protocols (for example ANSI X12 or ISO EDIFACT). The details may then be revised at Contract finalization. If so, add the following text.]*  For Electronic Data Interchange (EDI) the Purchaser and Supplier will use the following standards, protocols, addresses, and procedures: [ insert: standards, protocols, addresses; also describe: any relevant procedures ] |

B. Subject Matter of Contract

Scope of the System ( GCC Clause 7)

|  |  |
| --- | --- |
| GCC 7.3 | The Supplier’s obligations under the Contract will include the following recurrent cost items, as identified in the Recurrent Cost tables in the Supplier’s Bid:  [specify: the recurrent cost items/services that are included in the Contract; also provide cross reference to the place in the Technical Requirements where each item/service is specified in detail.]  ***[Note****: The requirements in terms of recurrent cost items should be defined here, reflected in the Recurrent Cost Table for the Warranty period, and elaborated in the Technical Requirements. See also notes to SCC Clause 29.4 regarding services that are not typically included in commercial warranties.*  *If the Purchaser expects that wear and tear on System components will necessitate routine replacement of such components, and if Purchaser technical staff will perform these repair and replacement tasks, the Purchaser may wish to consider adding the following clause to the SCC that obligates the Supplier to stock and/or provide certain spare parts. ]*  The Supplier agrees to supply spare parts required for the operation and maintenance of the System, as stated below, for [ insert: number of years ]years beginning with Operational Acceptance. Moreover, the price of such spare parts shall be those specified in the spare parts price schedule submitted by the Suppler as part of its Bid. These prices shall include the purchase price for such spare parts and other costs and expenses (including the Supplier’s fees) relating to the supply of spare parts.  [list the spare parts needs, or reference the line items in the Spare Parts Price Schedule in the Supplier’s Bid, if the Supplier is the source of the identity of the spares, i.e., reflecting its own understanding of its own technologies.]  **[*Note:*** *The need to ensure the availability of spare parts sources, above and beyond those the Supplier would routinely and implicitly need to perform under its defect liability and/or maintenance responsibilities, generally is not a major issue for the Information Technologies available in the market today. A System is likely to become obsolete long before it begins to develop physical defects.]* |

Time for Commencement and Operational Acceptance ( GCC Clause 8)

|  |  |
| --- | --- |
| GCC 8.1 | The Supplier shall commence work on the System within: [ insert: number ***of*** ***days***] days from the Effective Date of the Contract. |

Supplier’s Responsibilities ( GCC Clause 9)

|  |  |
| --- | --- |
| GCC 9.8 | The following sustainable procurement contractual provisions, apply: *[specify:* ***sustainable procurement contractual******provisions*** *or state:* ***“none”.****]*  *[****Note****: Refer to the sustainable procurement guidance.]* |
| GCC 9.18 | The Supplier *[specify “****is required” / “not required”****]* to make security arrangements for the Project Site/s. |

C. Payment

Contract Price ( GCC Clause 11)

|  |  |
| --- | --- |
| GCC 11.2 | Adjustments to the Contract Price shall be as follows: [ state: “not applicable” or specify: the items, adjustment formula or formulas, and the relevant price indices ].  **[*Note:*** *Price adjustment is not generally associated with Information System procurements. Price adjustment may be appropriate when: (i) performance of the Contract is expected to last more than eighteen month; (ii) the cost of an important input, such as labor, is subject to inflation (or deflation); and (iii) meaningful price indices are readily available and well accepted. Thus, for example, if the Contract provides a substantial number of recurrent cost items following Operational Acceptance, would the inclusion of an SCC to permit adjustment be appropriate. In such cases, adjustment should be limited to those items only and use appropriate indices that accurately mirror the relevant price trends.]* |

Terms of Payment ( GCC Clause 12)

|  |  |
| --- | --- |
| GCC 12.1 | Subject to the provisions of GCC Clause 12 (Terms of Payment), the Purchaser shall pay the Contract Price to the Supplier according to the categories and in the manner specified below. Only the categories Advance Payment and Complete System Integration relate to the entire Contract Price. In other payment categories, the term "total Contract Price" means the total cost of goods or services under the specific payment category. Within each such category, the Contract Implementation Schedule may trigger pro-rata payments for the portion of the total Contract Price for the category corresponding to the goods or services actually Delivered, Installed, or Operationally Accepted, at unit prices and in the currencies specified in the Price Schedules of the Contract Agreement.  (a) Advance Payment  ten percent (10%) of the entire Contract Price, exclusive of all Recurrent Costs, shall be paid against receipt of a claim accompanied by the Advance Payment Security specified in GCC Clause 13.2.  ***[Note:*** *The advance payment may be higher than 10% in cases where Supplier's mobilization costs (i.e., costs between Contract effectiveness and the first scheduled Contract payment) are likely to be much larger than the advance payment, resulting in substantial negative cash flow for the Supplier. This happens primarily in projects where the Supplier must acquire expensive highly-specialized equipment to customize and configure a solution system prior to the first scheduled payment milestone. In these cases, the entire schedule of payments below obviously needs to be adjusted accordingly.]*  (b):  (i) for Information Technologies, Materials, and other Goods, with the exception of Custom Software and Custom Materials:  sixty percent (60%) of the total or pro-rata Contract Price for this category against Delivery  ten percent (10%) of the same price against Installation  ten percent (10%) of the same price against Operational Acceptance.  (ii)Custom Software and Custom Materials:  sixty percent (60%) of the total or pro-rata Contract Price for this category against Installation  twenty percent (20%) of the same price against Operational Acceptance.  ***[Note:*** *Large custom software development or system integration contracts (e.g., those taking longer than six months from Contract Effectiveness to Operational Acceptance of the Application Software subsystem) are usually paid in increments against Purchaser's acceptance of major intermediate deliverables defined in the implementation schedule as key milestones (e.g. a sequence of major system design documents, such as: software requirements specifications, software design document, development of a prototype for a major subsystem, delivery of a pilot implementation of the software for a subsystem or the entire system, etc ). In those cases, the above payment terms should be modified accordingly and refer to the milestones in the Implementation Schedule. The payment terms should allow the Supplier an adequate cash flow vis-à-vis the steps need to achieve an operational Information System. ]*  (iii)Services (other than Training):  eighty percent (80%) of the pro-rata Contract Price for services performed will be paid monthly in arrears, on submission and Purchaser’s approval of invoices:  ***[Note:*** *Some Contracts may involve considerable “Services other than Training” (and services other than software customization). For instance, there could be the digitization of maps using the procured Geographical Information System (GIS), or the scanning, indexing and conversion of paper documents, or the conversion or migration of existing electronic data sets. In these cases, payment may be keyed to acceptance of intermediate deliverables or completion of service delivery phases defined in the project implementation schedule, rather than merely to the passage of time, as illustrated. In designing this type of payment terms, the Purchaser has an obligation to balance and ensure consistency between its own interest to pay only against value received, the supplier's need for a reasonable cash flow, the design of the project implementation schedule, the specification of service milestones and even the process for acceptance testing of intermediate deliverables (when milestones completion would be subject to such testing).]*  (iv)Training  thirty percent (30%) of the total Contract Price for training services at the start of the full training program  fifty percent (50%) of the pro-rata Contract Price for training services performed will be paid monthly in arrears, on submission and approval of appropriate invoices.  (v)Complete System Integration  ten percent (10%) of the entire Contract Price, exclusive of all Recurrent Costs, as final payment against Operational Acceptance of the System as an integrated whole.  (vi)Recurrent Costs  one hundred percent (100%) of the price of the services actually delivered will be paid quarterly in arrears, on submission and Purchaser’s approval of invoices.  ***[Note:*** *If a separate Operational Acceptance for the System as an integrated whole is not required, increase by 10% points the final payment percentages of all other goods and services above.]* |
|  |  |
| GCC 12.4 | The Supplier will invoice the Purchaser in the currency used in the Contract Agreement and the Price Schedules it refers to, for Goods and Services supplied locally, and the conversion between this currency and *[ insert:* ***name of local currency****]* for payment purposes - in case the two currencies are different - will be made as of the actual payment date using the exchange rate found in *[ insert:* ***source of exchange rate****].* |

Securities ( GCC Clause 13)

|  |  |
| --- | --- |
| GCC 13.3.1 | The Performance Security shall be denominated in [ insert currency ]for an amount equal to [ insert: number ]percent of the Contract Price, excluding any Recurrent Costs.  *[****Note****: The general rule is that the Performance Security is denominated in the currency or currencies of the contract or in a freely convertible currency acceptable to the Purchaser. It should be set as no more than ten (10) percent of the Contract Price, including Recurrent Costs during the Warranty Period. Provision of the Performance Security increases the transaction costs incurred by the successful Bidder, which it can recover only by increasing its price. Therefore, for a simple system, Performance Security in an amount of only six (6) percent of the Contract Price would provide adequate protection while for a moderately complex system, eight (8) percent should be sufficient.]* |
| GCC 13.3.4 | During the Warranty Period (i.e., after Operational Acceptance of the System), the Performance Security shall be reduced to [ insert: number]percent of the Contract Price, excluding any Recurrent Costs.  *[****Note****: An appropriate amount for the Performance Security for a (three-year) Warranty Period would be between one (1) and two and a half (2.5) percent of the Contract Price including Recurrent Costs for the Warranty period.]* |

D. Intellectual Property

Copyright ( GCC Clause 15)

|  |  |
| --- | --- |
| GCC 15.3 | There are no Special Conditions of Contract applicable to GCC Clause 15.3  *[****Note****: If the Purchaser is a corporate or commercial entity, it may choose to specify the conditions under which contractual rights would be conveyed to any Purchaser of the concern, or any successor entities following a group reorganization or bankruptcy or other insolvency procedures. Purchasers with other organizational structures may need to add other similar provisions.]* |
| GCC 15.4 | Special Conditions of Contract applicable to GCC Clause 15.4, if any  ***[Note:*** *There is a broad spectrum of strategies that the Purchaser can adopt regarding Intellectual Property Rights in Custom Software (and in Custom Materials). One extreme case is that the Purchaser retains all Intellectual Property Rights and tightly restricts what the Supplier can do with the Custom Software and information related to it. This approach may be appropriate when the Purchaser has highly sensitive procedures embedded in the Custom Software (e.g., a central bank’s settlement system) or commercial competitive concerns regarding wider use of the Software, designs, or information, or where the Purchaser considers that it is contributing valuable know-how to the development of the Custom Software and wishes to share in future profits with the Supplier that derives from exploitation of that know-how. The other extreme case is where the Purchaser retains no Intellectual Property Rights in the Custom Software and only licenses its use from the Supplier. This approach is most appropriate when the Supplier wants to take advantage of the potential cost reduction in allowing the Supplier to commercialize the Custom Software (rather than sharing in future profits) and where the Purchaser has no proprietary or commercial concerns regarding its reuse.*  *A wide variety of intermediate arrangements can be appropriate, depending on the circumstances. These would entail variations of what the Purchaser is entitled to do with the software, designs, and related information (and under what conditions). These rights and obligations include the following: (i) duplicating and using the software on different equipment, such as back-ups, additional computers, replacements, upgraded units, etc.; (ii) transferring the license or sublicensing the software for other entities to use, modify, develop, commercialize, etc.; (iii) sharing proprietary information regarding the Custom Software with various parties. The Purchaser’s obligations and rights (and the conditions under which those rights and obligations apply) can vary substantially also. These include: (i) what the Purchaser must and can do with the CASE files, Source Code, and executable code of the Custom Software; (ii) sharing, reselling, and otherwise providing access to the software, designs and related information; and (iii) auditing for license compliance.*  *The Supplier’s rights in relation to the Custom Software may:*   * *Be limited to use in order to support the Purchaser; or* * *Extend to commercial exploitation by re-licensing to third-party customers.*   *If the Supplier’s rights extend to commercial exploitation, they may be limited as follows:*   * *There may be an interim period, designed to protect the Purchaser’s competitive edge, during which the Supplier is not permitted to exploit commercially; and/or* * *The Supplier may be prohibited from licensing the Custom Software to certain categories of customer (for example, direct competitors of the Purchaser) or in certain territories (for example, the Purchaser’s Country), either for a limited period or indefinitely; and/or* * *The Supplier may be required to pay royalties to the Purchaser when it licenses third parties to use the Custom Software.*   *The first two of these categories of limitation are intended to protect the Purchaser’s competitive edge. The third is intended to allow the Purchaser to share in future profits made by the Supplier through exploitation of the Custom Software. Royalty arrangements will have to be backed up by obligations to report to the Purchaser regarding future sales of products to which royalties apply and audit rights so that the Purchaser can check that the Supplier’s reports are accurate. Clearly, if royalty arrangements are put in place, the value of the Custom Software to the Supplier is reduced, so the Purchaser may not benefit from an up-front cost saving.*  *The Purchaser’s rights in relation to the Custom Software may also be restricted to “user” rights or extended to commercial exploitation. If the Purchaser is to be treated as a mere user of the Custom Software, it might accept restrictions on use similar to those imposed in relation to the Standard Software (indeed, the default position in the GCC is that the Custom Software will be licensed to the Purchaser on exactly the same terms as the Standard Software if the Intellectual Property Rights in the Custom Software does not vest in the Purchaser). It may, however, also expect to have access to, and a right to use, CASE files and Source Code to the Custom Software (whereas, at best, Source Code to the Standard Software is likely to be deposited in escrow).*  *If the Purchaser is to be permitted to exploit the Custom Software commercially, its exploitation rights may be limited in similar ways to the ways in which the Purchaser’s own usage rights to the Custom Software may be limited.*  *It may be appropriate to apply different arrangements to various elements of the Custom Software, according to their commercial sensitivity and potential for exploitation and the degree of competitive advantage that they afford to the Purchaser.*  *The various possible arrangements can be achieved by a variety of contractual mechanisms. Ownership of Intellectual Property Rights in the Custom Software may vest the Supplier or the Purchaser, with the owner of those rights granting an appropriate license to the other party. This license may be subject to various degrees of exclusivity, depending on the desired commercial outcome (for example, the Supplier may own the Intellectual Property Rights in the Custom Software by granting to the Purchaser a license that is exclusive, in relation to exploitation in the Purchaser’s Country, for two years).*  *If an exclusive license is to be granted, competition law issues will need to be considered in some jurisdictions.*  *Each is sufficiently different as to render virtually all sample text inappropriate in numerous cases. Accordingly, the Purchaser of Custom Software will, in most instances, require the services of an appropriately skilled lawyer to draft SCC for the rights and obligations regarding Custom Software (more particularly, the variety of rights and obligations that potentially apply to different items of Custom Software).]* |
| GCC 15.5 | Special Conditions of Contract applicable to GCC Clause 15.5, if any  ***[Note:*** *Special software escrow arrangements are generally needed in relation to Contracts for the supply of Software, particularly Application Software, where there is concern about the ability of the Supplier to provide ongoing support throughout the life of the System. The protection provided by an escrow arrangement, however, should be weighed against the costs of administering it. The actual language of the escrow contract will vary depending on the laws of the country in which the escrow deposit is to be made (which may be the Purchaser’s Country or another country with a suitable legal regime) and the escrow agent selected (escrow agents generally have their own standard form contracts). Provisions may cover:*  *(i) the Supplier’s obligations to deliver the Source Code to the escrow agent and make replacement deposits to ensure that the Source Code is up to date;*  *(ii) the Supplier’s warranties that the Source Code is at all times capable of being used to generate the latest version of the executable code to the relevant Software in use by the Purchaser and suitable to enable the Purchaser to support and develop the Software;*  *(iii) the escrow agent’s obligations to keep the Source Code secure and confidential;*  *(iv) the escrow agent’s obligations in relation to verification of the Source Code (to ensure that it is Source Code and that it is capable of generating the executable code);*  *(v) the obligations of the Supplier and the Purchaser in relation to payment of the escrow agent’s fee;*  *(vi) the escrow agent’s right and obligation to release the Source Code to the Purchaser in certain specified “release events” (e.g., bankruptcy or insolvency of the Supplier or the Supplier’s failure to make deposits or to support the Software);*  *(vii) limitations and exclusions of the escrow agent’s liability;*  *(viii) the circumstances in which the escrow arrangement will terminate, and what will happen to the deposited Source Code on termination; and*  *(ix) confidentiality undertakings to be given by the Purchaser on release of the Source Code.]* |

Software License Agreements ( GCC Clause 16)

|  |  |
| --- | --- |
| GCC 16.1 (a) (iv) | Special Conditions of Contract applicable to GCC Clause 16.1 (a) (iv, if any  ***[Note:*** *In the interest of soliciting lower Bid prices, Purchasers may wish to consider defining limitations in the use of the software. For example:*  *(a) restrictions on the number of records in particular categories that may be held by the System;*  *(b) restrictions on the numbers of transactions in particular categories that may be processed by the System in any day, week, month, or other specified period;*  *(c) restrictions on the number of persons who may be authorized to use the System at any time;*  *(d) restrictions on the number of persons who may access the System simultaneously at any time; or*  *(e) restrictions on the number of workstations that may be connected to the System at any time.]*  *[****Note****: From the point of view of the Purchaser, if restrictions of any of these kinds (or any similar kind) are to be imposed and there is a real likelihood that the limits may be reached, it would be better to specify additional license fees that are payable when the limits are reached rather than imposing an absolute prohibition on exceeding the limits.]* |
| GCC 16.1 (b) (vi) | Special Conditions of Contract applicable to GCC Clause 16.1 (b) (vi), if any  *[****Note****: The Purchaser may also wish to specify, for example, that such entities shall be not direct competitors of the Supplier.]* |
| GCC 16.1 (b) (vii) | Special Conditions of Contract applicable to GCC Clause 16.1 (b) (vii), if any  *[****Note****: The Purchaser may, for example, wish to specify the members of the Purchaser’s business group that are not direct competitors of the Supplier and that the Purchaser must obtain and provide the Supplier written evidence from such parties that such parties will abide by the terms of the Contract as if they were party to the Contract.]* |
| GCC 16.2 | Special Conditions of Contract applicable to GCC Clause 16.2, if any  *[****Note****: If on-site audits are acceptable, the Purchaser may specify conditions on the duration and number of audits per year; the hours or days during which audits may be conducted; the categories of software subject to audit; the procedures for access to Purchaser’s hardware or software; the number and affiliation of individual auditors; the timing and terms of advance notice; the indemnity by Supplier for losses, liabilities, and costs incurred by the Purchaser as a direct result of the audit; etc].* |

Confidential Information ( GCC Clause 17)

|  |  |
| --- | --- |
| GCC 17.1 | Special Conditions of Contract applicable to GCC Clause 17.1, if any  *[****Note****: The Purchaser may wish to give members of its business group or related agencies, for example, access to certain specific types of technical and / or financial information it obtains or develops with respect to the Supplier and its Information Technologies. The SCC covering such an exemption should define the individuals covered and generally provide that the Purchaser will ensure that such parties are aware of and will abide by the Purchaser’s obligations under GCC Clause 17 as if such party were a party to the Contract in place of the Purchaser.*  if necessary and appropriate, specify: persons, topics, and conditions for which the confidentiality clause does not apply.] |

E. Supply, Installation, Testing, Commissioning, and Acceptance of the System

Representatives ( GCC Clause 18)

|  |  |
| --- | --- |
| GCC 18.1 | Special Conditions of Contract applicable to GCC Clause 18, if any  ***[Note:*** *If appropriate specify additional powers or limitations.]*  The Purchaser’s Project Manager shall have the following additional powers and / or limitations to his or her authority to represent the Purchaser in matters relating to the Contract [ state necessary and appropriate clauses]. |
| GCC 18.2.2 | Special Conditions of Contract applicable to GCC Clause 18.2.2, if any  ***[Note:*** *If appropriate specify additional powers or limitations.]*  The Supplier’s Representative shall have the following additional powers and / or limitations to his or her authority to represent the Supplier in matters relating to the Contract [ state necessary and appropriate clauses ].  *[****Note:*** *Any additional powers or limitations of the Supplier’s Representative will, of necessity, be subject to discussions at Contract finalization and the SCC amended accordingly.]* |

Project Plan ( GCC Clause 19)

|  |  |
| --- | --- |
| GCC 19.1 | Chapters in the Project Plan shall address the following subject**:**  (a) Project Organization and Management Sub-Plan, including management authorities, responsibilities, and contacts, as well as task, time and resource-bound schedules (in GANTT format);  (b) Implementation Sub-Plan;  (c) Training Sub-Plan;  (d) Testing and Quality Assurance Sub-Plan;  (e) Warranty Defect Repair and Technical Support Service Sub-Plan  Further details regarding the required contents of each of the above chapters are contained in the Technical Requirements, [insert: cross references]. |
| GCC 19.6 | ***The Supplier shall submit to the Purchaser:***  ***(i) monthly inspection and quality assurance reports***  ***(ii) monthly training participants test results***  ***(iii) monthly log of service calls and problem resolutions*** |

Design and Engineering ( GCC Clause 21)

|  |  |
| --- | --- |
| GCC 21.3.1 | Special Conditions of Contract applicable to GCC Clause 21.3.1., if any  ***[Note:*** *If necessary and appropriate, specify the Controlling Technical Documents (i.e., document that must be approved by the Purchaser’s Project Manager before any relevant downstream work can be undertaken by the Supplier).]*  *[If appropriate, insert “The Supplier shall prepare and furnish to the Project Manager the following documents for which the Supplier must obtain the Project Manager’s approval before proceeding with work on the System or any Subsystem covered by the documents.* [ state “none” or specify, for example:  (\*) detailed site surveys;  (\*) final Subsystem configurations;  (\*) etc. ]]” |

Product Upgrades ( GCC Clause 23)

|  |  |
| --- | --- |
| GCC 23.4 | Special Conditions of Contract applicable to GCC Clause 23.4., if any  *[****Note****: Mandating that all new versions, releases, and updates of Standard Software will be passed on for free during the Warranty Period is a comprehensive requirement, the benefits of which must be balanced against the perceived costs in the mind of the successful Bidder at the time of bid submission. To require the Supplier to provide for free only new releases and updates, but agreeing that it would be reimbursed for the supply of complete new versions might be more cost-effective. For example, this may be particularly appropriate when the Purchaser would not benefit from costs of migrating its business applications to an entirely new version of the underlying database system if such a version came out during a three Warranty Period. Another approach may be to shorten the time period during which updates, etc., would have to be supplied for free, for example, to only the first year of the Warranty Period; or alternatively, a more narrow set of Standard Software could be covered.*  *Also, note that the GCC only specifies the obligations “to provide” software updates. If the Purchaser needs to have the Supplier perform installation and configuration services associated with software updates, this needs to be clearly stated in the relevant service specifications in the Technical Requirements and text added to this SCC indicating the need for the Supplier to maintain such a service capacity: e.g., “The Supplier must maintain a service capacity to promptly deliver, provide, install and configure the provided versions, releases, and updates for all Standard Software that are used in the System at no additional cost to the Purchaser.” ]* |

Inspections and Tests ( GCC Clause 25)

|  |  |
| --- | --- |
| GCC 25 | Special Conditions of Contract applicable to GCC Clause 25., if any  *[****Note****: Purchasers may wish to consider employing qualified inspectors to inspect and certify the Information Technologies, Materials, and other Goods prior to shipment. This can minimize the number of cases where the Purchaser receives shipped goods that do not conform to the Technical Requirements and shorten the repair or replacement time.]* |

Commissioning and Operational Acceptance ( GCC Clause 27)

|  |  |
| --- | --- |
| GCC 27.2.1 | Special Conditions of Contract applicable to GCC Clause 27.2.1., if any  *[****Note****: Few aspects of Information Technology procurement are more critical to the successful implementation of a System than the specification of Operational Acceptance Tests. It is imperative that the Purchaser prepare the specification for these tests as carefully as the overall specification of the System itself. The description should be sufficiently comprehensive, unambiguous, and verifiable to result in proper operation of the System with minimal confusion or controversy between the Purchaser and its management, the Supplier, and any users.*  *In addition, where the Contract covers the Installation and acceptance testing of a number of Subsystems, the nature of the acceptance tests required for each Subsystem, and for the final tests to be carried out on the entire System once all Subsystems have been completed, needs to be clearly specified here and/or in the Technical Requirements and which party bears responsibility for correcting any defects discovered during the final tests of the entire System needs to be identified.]* |

F. Guarantees and Liabilities

Operational Acceptance Time Guarantee ( GCC Clause 28)

|  |  |
| --- | --- |
| GCC 28.2 | Special Conditions of Contract applicable to GCC Clause 28.2., if any  ***[Note:*** *Typical percentages are, respectively, one half of one percent (0.5%) per week and ten percent (10%) of the total. In some instances, the Purchaser may wish to consider specifying liquidated damages on a daily basis. If so, specify this in the SCC].* |
| GCC 28.3 | Special Conditions of Contract applicable to GCC Clause 28.3, if any.  *[****Note****: Establishing more milestones for liquidated damages may provide a somewhat greater degree of control and assurances regarding the pace of the implementation of the System. However, this will come at a price of increased complexity of Contract management and increased perceptions of financial risks on the part of Bidders. This most likely will lead to higher bid prices. In most cases, Operational Acceptance should be the most appropriate financial control for ensuring the timeliness of implementation, since it captures the impact of earlier delays and is, in the final analysis, the milestone that truly matters. Whatever milestones are selected, it is critical that the Implementation Schedule precisely specify what Subsystems or other components are covered and when the milestone is set. These, of course, can be refined and revised through the Agreed Project Plan.]* |

Defect Liability ( GCC Clause 29)

|  |  |
| --- | --- |
| GCC 29.1 | There are no Special Conditions of Contract applicable to GCC Clause 29.1.  *[****Note****: Software is never completely error or “bug” free. Thus, the Purchaser may wish to refine or to limit the Supplier’s warranty obligations. Properly done, this can reduce Bidder’s perceptions of financial risk and help lower bid prices. However, the Purchaser should balance the potential savings against the risks to reliable and effective operation of the System and the related costs to the Purchaser. These tradeoffs are very specific to the type of the System and its uses. These tradeoffs are also changing very rapidly with technological development. Accordingly, the IsDB recommends that Purchaser’s consult experts in the relevant areas for an up-to-date assessment of the risks and the most appropriate text to express any such exceptions and limitations.]* |
| GCC 29.4 | Special Conditions of Contract applicable to GCC Clause 29.4., if any  ***[Note:*** *When defining the Warranty period, Purchasers should be careful to recognize that services such as resident engineer support, new software releases and end-user help desk support are not typically included in commercial warranties and should be priced separately in the Recurrent Cost Table].* |
| GCC 29.10 | Special Conditions of Contract applicable to GCC Clause 29.10, if any  ***[Note:*** *Typically, the Purchaser should develop a set of response times for different degrees of seriousness of the defects and/or categories of IT and/or specific Subsystems. The most appropriate and economical set of response times are highly dependent on the specific System, its use, and the relevant conditions in the Purchaser’s Country.*  *The GCC specifies that the Supplier must commence work on warranty defects within a maximum of two weeks; else the Purchaser may contract-in such services at the Supplier’s expense. The Purchaser may wish to shorten or lengthen this period in the SCC. The time specified must strike a reasonable balance between the response time the typical qualified Supplier can physically achieve and the importance of maintaining continued System operation. If too short a time period is specified, Suppliers will need to protect themselves by adding a contingency to their bid prices. ]* |

Functional Guarantees ( GCC Clause 30)

|  |  |
| --- | --- |
| GCC 30 | Special Conditions of Contract applicable to GCC Clause 30., if any  *[****Note****: In the event that Information Systems and Technologies would have to conform to other calendar system(s), here would be the place to specify related requirements in addition to, or in variation of, the requirements in GCC clause 30.2.]* |

G. Risk Distribution

Insurances ( GCC Clause 37)

|  |  |
| --- | --- |
| GCC 37.1 (c) | The Supplier shall obtain Third-Party Liability Insurance in the amount of [ insert: monetary value] with deductible limits of no more than [ insert: monetary value]. The insured Parties shall be [ list insured parties ]. The Insurance shall cover the period from [ insert: beginning date, relative to the Effective Date of the Contract ]until [ insert: expiration date, relative to the Effective Date of the Contract or its completion ]. |
| GCC 37.1 (e) | Special Conditions of Contract applicable to GCC Clause 37.1 (e)., if any  [Note: Many countries have statutory requirements for various insurances. These should be reviewed with the Purchaser’s legal department.  *For example:*  *The Supplier shall obtain Worker’s Compensation Insurance in accordance with the statutory requirements of [ insert:*  ***the Purchaser’s Country****]. Specifically: [ insert****: requirements****]. The Insurance shall cover the period from [ insert:* ***beginning date, relative to the Effective Date of the Contract****] until [ insert:* ***expiration date, relative to the Effective Date of the Contract or its completion****].*  *The Supplier shall obtain Employer’s Liability Insurance in accordance with the statutory requirements of* [ insert: the Purchaser’s Country ].  *Specifically:* [ insert: requirements ]. *The Insurance shall cover the period from* [ insert: beginning date, relative to the Effective Date of the Contract ]*until* [ insert: expiration date, relative to the Effective Date of Contract or its completion ].] |

H. Change in Contract Elements

Changes to the System ( GCC Clause 39)

|  |  |
| --- | --- |
| GCC 39.4 | Value Engineering  The Purchaser ***[****specify:* ***will / will not]*** consider a Value Engineering Proposal.  When the Purchaser will consider a Value Engineering Proposal and if the value engineering proposal is approved by the Purchaser the amount to be paid to the Supplier shall be *[insert* ***appropriate percentage****, up to 50%]* percent of the reduction in the Contract Price. |

I. Settlement of Disputes

Settlement of Disputes (GCC Clause 43)

|  |  |
| --- | --- |
| GCC 43.1.4 | The Appointing Authority for the Adjudicator is: [ insert: the name of an impartial international technical organization in the information technology sector, or, if no Adjudicator is used in this Contract Agreement or no organization has been identified and agreed to serve as Appointing Authority for the Adjudicator, state “not applicable.”]. |
| GCC 43.2.3 | If the Supplier is from outside the Purchaser’s Country arbitration proceedings shall be conducted in accordance with the rules of arbitration of *[select one of the following:* ***UNCITRAL*** */* ***the International Chamber of Commerce (ICC)*** */* ***the Arbitration Institute of the Stockholm Chamber of Commerce*** */* ***the London Court of International Arbitration****].* These rules, in the version in force at the time of the request for arbitration, will be deemed to form part of this Contract.  If the Supplier is a national of the Purchaser’s Country, any dispute between the Purchaser and a Supplier arising in connection with the present Contract shall be referred to arbitration in accordance with the laws of the Purchaser’s country. |

Section X - Contract Forms

## Notes to the Purchaser on preparing the Contract Forms

Performance Security: Pursuant to GCC Clause 13.3, the successful Bidder is required to provide the Performance Security within twenty-eight (28) days of notification of Contract award.

Advance Payment Security: Pursuant to Clause 13.2, the successful Bidder is required to provide a bank guarantee securing the Advance Payment, if the SCC related to GCC Clause 12.1 provides for an Advance Payment.

Installation and Operational Acceptance Certificates: Recommended formats for these certificates are included in this SPD. Unless the Purchaser has good reason to require procedures that differ from those recommended, or to require different wording in the certificates, the procedures and forms shall be included unchanged. If the Purchaser wishes to amend the recommended procedures and/or certificates, it may propose alternatives for the approval of the IsDB before release of the bidding document to potential Bidders.

Change Order Procedures and Forms: Similar to the Installation and Operational Acceptance Certificates, the Change Estimate Proposal, Estimate Acceptance, Change Proposal, Change Order, and related Forms should be included in the bidding document unaltered. If the Purchaser wishes to amend the recommended procedures and/or certificates, it may propose alternatives for the approval of the IsDB before release of the bidding document.

## Notes to Bidders on working with the Sample Contractual Forms

The following forms are to be completed and submitted by the successful Bidder following receipt of the Letter of Acceptance from the Purchaser: (i) Contract Agreement, with all Appendices; (ii) Performance Security; and (iii) Advance Payment Security.

• Contract Agreement: In addition to specifying the parties and the Contract Price, the Contract Agreement is where the: (i) Supplier Representative; (ii) if applicable, agreed Adjudicator and his/her compensation; and (iii) the List of Approved Subcontractors are specified. In addition, modifications to the successful Bidder’s Bid Price Schedules are attached to the Agreement. These contain corrections and adjustments to the Supplier’s bid prices to correct errors, adjust the Contract Price to reflect – if applicable - any extensions to bid validity beyond the last day of original bid validity plus 56 days, etc.

• Performance Security: Pursuant to GCC Clause 13.3, the successful Bidder is required to provide the Performance Security in the form contained in this section of these bidding documents and in the amount specified in accordance with the SCC.

• Advance Payment Security: Pursuant to GCC Clause 13.2, the successful Bidder is required to provide a bank guarantee for the full amount of the Advance Payment - if an Advance Payment is specified in the SCC for GCC Clause 12.1 - in the form contained in this section of these bidding documents or another form acceptable to the Purchaser. If a Bidder wishes to propose a different Advance Payment Security form, it should submit a copy to the Purchaser promptly for review and confirmation of acceptability before the bid submission deadline.

The Purchaser and Supplier will use the following additional forms during Contract implementation to formalize or certify important Contract events: (i) the Installation and Operational Acceptance Certificates; and (ii) the various Change Order forms. These and the procedures for their use during performance of the Contract are included in the bidding documents for the information of Bidders.

Table of Contract Forms

[Notification of Intention to Award 268](#_Toc42264403)

[Beneficial Ownership Disclosure Form 272](#_Toc42264404)

[Letter of Acceptance 274](#_Toc42264405)

[1. Contract Agreement 275](#_Toc42264406)

[Appendix 1. Supplier’s Representative 279](#_Toc42264407)

[Appendix 2. Adjudicator 280](#_Toc42264408)

[Appendix 3. List of Approved Subcontractors 281](#_Toc42264409)

[Appendix 4. Categories of Software 282](#_Toc42264410)

[Appendix 5. Custom Materials 283](#_Toc42264411)

[Appendix 6. Revised Price Schedules 284](#_Toc42264412)

[Appendix 7. Minutes of Contract Finalization Discussions and Agreed-to Contract Amendments 285](#_Toc42264413)

[2. Performance and Advance Payment Security Forms 286](#_Toc42264414)

[2.1 Performance Security Form (Bank Guarantee) 287](#_Toc42264415)

[2.2 Advance Payment Security 289](#_Toc42264416)

[Bank Guarantee 289](#_Toc42264417)

[3. Installation and Acceptance Certificates 291](#_Toc42264418)

[3. Installation and Acceptance Certificates 291](#_Toc42264419)

[3.1 Installation Certificate 292](#_Toc42264420)

[3.2 Operational Acceptance Certificate 293](#_Toc42264421)

[4. Change Order Procedures and Forms 294](#_Toc42264422)

[4.1 Request for Change Proposal Form 295](#_Toc42264423)

[4.2 Change Estimate Proposal Form 297](#_Toc42264424)

[4.3 Estimate Acceptance Form 299](#_Toc42264425)

[4.4 Change Proposal Form 301](#_Toc42264426)

[4.5 Change Order Form 303](#_Toc42264427)

[4.6 Application for Change Proposal Form 305](#_Toc42264428)

Notification of Intention to Award

*[This Notification of Intention to Award shall be sent to each Bidder that submitted a Bid.]*

*[Send this Notification to the Bidder’s Authorized Representative named in the Bidder Information Form]*

For the attention of Bidder’s Authorized Representative

Name: *[insert* ***Authorized Representative’s name****]*

Address: *[insert* ***Authorized Representative’s Address****]*

Telephone/Fax numbers: *[insert* ***Authorized Representative’s telephone/fax numbers****]*

Email Address: *[insert* ***Authorized Representative’s email addres****s]*

*[IMPORTANT: insert the date that this Notification is transmitted to all participating Bidders. The Notification must be sent to all Bidders simultaneously. This means on the same date and as close to the same time as possible.]*

DATE OF TRANSMISSION: This Notification is sent by: *[specify* ***email*** */* ***fax****]* on *[specify* ***date****]* (local time)

**Notification of Intention to Award**

Purchaser:*[insert* ***the name of the Purchaser****]*

Project:*[insert* ***name of project****]*

Contract title:*[insert the* ***name of the contract****]*

Country:*[insert* ***country where IFB is issued****]*

Financing / Grant No.: *[insert* ***reference number for Financing/grant****]*

IFB No:*[insert IFB* ***reference number from Procurement Plan****]*

This Notification of Intention to Award (Notification) notifies you of our decision to award the above contract. The transmission of this Notification begins the Standstill Period. During the Standstill Period you may:

1. request a debriefing in relation to the evaluation of your Bid, and/or
2. submit a Procurement-related Complaint in relation to the decision to award the contract.
3. **The successful Bidder**

|  |  |
| --- | --- |
| Name: | [*insert name* *of successful Bidder*] |
| Address: | [*insert address* *of the successful Bidder*] |
| Contract price: | [*insert contract price* *of the successful Bidder*] |
| Total combined score: | [*insert the total combined score of the successful Bidder*] |

1. **Other Bidders** *[INSTRUCTIONS: insert names of all Bidders that submitted a Bid. If the Bid’s price was evaluated include the evaluated price as well as the Bid price as read out.]*

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of Bidder | Technical Score  (If applicable) | Bid price | Evaluated Bid Cost | Combined Score (if applicable) |
| [*insert name*] | [*insert Technical score*] | [*insert Bid price*] | [*insert evaluated cost*] | [*insert combined score*] |
| [*insert name*] | [*insert Technical score*] | [*insert Bid price*] | [*insert evaluated cost*] | [*insert combined score*] |
| [*insert name*] | [*insert Technical score*] | [*insert Bid price*] | [*insert evaluated cost*] | [*insert combined score*] |

1. **Reason/s why your Bid was unsuccessful** *[Delete if the combined score already reveals the reason]*

|  |
| --- |
| *[INSTRUCTIONS; State the reason/s why this Bidder’s Bid was unsuccessful. Do NOT include: (a) a point by point comparison with another Bidder’s Bid or (b) information that is marked confidential by the Bidder in its Bid.]* |

1. **How to request a debriefing**

|  |
| --- |
| DEADLINE: The deadline to request a debriefing expires at midnight on *[insert date]* (local time).  You may request a debriefing in relation to the results of the evaluation of your Bid. If you decide to request a debriefing your written request must be made within three (3) Business Days of receipt of this Notification of Intention to Award.  Provide the contract name, reference number, name of the Bidder, contact details; and address the request for debriefing as follows:  Attention: [*insert full name of person, if applicable*]  Title/position: [*insert title/position*]  Agency: [*insert name of Purchaser*]  Email address: [*insert email address*]  Fax number: [*insert fax number or state “not applicable”*]  If your request for a debriefing is received within the 3 Business Days deadline, we will provide the debriefing within five (5) Business Days of receipt of your request. If we are unable to provide the debriefing within this period, the Standstill Period shall be extended by five (5) Business Days after the date that the debriefing is provided. If this happens, we will notify you and confirm the date that the extended Standstill Period will end.  The debriefing may be in writing, by phone, video conference call or in person. We shall promptly advise you in writing how the debriefing will take place and confirm the date and time.  If the deadline to request a debriefing has expired, you may still request a debriefing. In this case, we will provide the debriefing as soon as practicable, and normally no later than fifteen (15) Business Days from the date of publication of the Contract Award Notice. |

1. **How to make a complaint**

|  |
| --- |
| DEADLINE: The deadline for submitting a Procurement-related Complaint challenging the decision to award the contract expires on midnight, *[insert date]* (local time).  Provide the contract name, reference number, name of the Bidder, contact details; and address the Procurement-related Complaint as follows:  Attention: [*insert full name of person, if applicable*]  Title/position: [*insert title/position*]  Agency: [*insert name of Purchaser*]  Email address: [*insert email address*]  Fax number: [*insert fax number or state “not applicable”*]  At this point in the procurement process, you may submit a Procurement-related Complaint challenging the decision to award the contract. You do not need to have requested, or received, a debriefing before making this complaint. Your complaint must be submitted within the Standstill Period and received by us before the Standstill Period ends.  For more information, see the **Procurement Guidelines (Annex C)**.” You should read these provisions before preparing and submitting your complaint.  In summary, there are four essential requirements:   1. You must be an ‘interested party’. In this case, that means a Bidder who submitted a Bid in this procurement, and is the recipient of a Notification of Intention to Award. 2. The complaint can only challenge the decision to award the contract. 3. You must submit the complaint within the deadline stated above. 4. You must include, in your complaint, all of the information required by the Procurement Guidelines (as described in Annex C). |

1. **Standstill Period**

|  |
| --- |
| DEADLINE: The Standstill Period is due to end at midnight on *[insert date]* (local time).  The Standstill Period lasts ten (10) Business Days after the date of transmission of this Notification of Intention to Award.  The Standstill Period may be extended. This may happen where we are unable to provide a debriefing within the five (5) Business Day deadline. If this happens we will notify you of the extension. |

If you have any questions regarding this Notification please do not hesitate to contact us.

On behalf of the Purchaser:

**Signature:** \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Title/position: [*insert* ***title/position***]

Agency: [*insert* ***name of Purchaser***]

Email address: [*insert* ***email address***]

Telephone number: [insert ***telephone number****]*

Letter of Acceptance

Purchaser:*[insert* ***the name of the Purchaser****]*

Project:*[insert* ***name of project****]*

Contract title:*[insert the* ***name of the contract****]*

Country:*[insert* ***country where IFB is issued****]*

Financing No.: *[insert* ***reference number for financing agreement****]*

IFB No:*[insert IFB* ***reference number from Procurement Plan****]*

Date: *[insert* ***Date****]*

To: *[insert* ***Name of Bidder****]*

This is to notify you that your Bid dated *[insert* ***Date****]* for execution of the *[insert* ***brief description of the Information System****]* for the Contract Price in the aggregate of *[insert* ***amount in figures]*** (*[insert* ***amount in words****]*), as corrected and modified in accordance with the Instructions to Bidders is hereby accepted by our Agency.

You are requested to furnish the Performance Security within 28 days in accordance with the Conditions of Contract, using for that purpose one of the Performance Security Form*s* included in Section X, - Contract Forms, of the Bidding Document.

Authorized Signature:

Name and Title of Signatory: *[insert* ***Name and Title****]*

Name of Agency: *[insert* ***Purchaser Name****]*

Attachment: Contract Agreement

1. Contract Agreement

THIS CONTRACT AGREEMENT is made

the [ insert: ordinal number ] day of [ insert: month ], [ insert: year ].

BETWEEN

(1) [ insert: Name of Purchaser ],a[ insert: description of type of legal entity, for example, an agency of the Ministry of . . . ] of the Government of [ insert: country of Purchaser ], or corporation incorporated under the laws of [ insert: country of Purchaser ] and having its principal place of business at [ insert: address of Purchaser ] (hereinafter called “the Purchaser”), and

(2) [ insert: name of Supplier], a corporation incorporated under the laws of [ insert: country of Supplier] and having its principal place of business at [ insert: address of Supplier ] (hereinafter called “the Supplier”).

WHEREAS the Purchaser desires to engage the Supplier to supply, install, achieve Operational Acceptance of, and support the following Information System [ insert: brief description of the Information System ](“the System”), and the Supplier has agreed to such engagement upon and subject to the terms and conditions appearing below in this Contract Agreement.

NOW IT IS HEREBY AGREED as follows:

|  |  |
| --- | --- |
| Article 1.   Contract Documents | 1.1 Contract Documents (Reference GCC Clause 1.1 (a) (ii))  The following documents shall constitute the Contract between the Purchaser and the Supplier, and each shall be read and construed as an integral part of the Contract: |
|  | (a) This Contract Agreement and the Appendices attached to the Contract Agreement  (b) Special Conditions of Contract  (c) General Conditions of Contract  (d) Technical Requirements (including Implementation Schedule)  (e) The Supplier’s bid and original Price Schedules  (f) Code of Conduct for Supplier’s and its Subcontractors’ personnel  (g) [ Add here: any other documents ] |
|  | 1.2 Order of Precedence (Reference GCC Clause 2)  In the event of any ambiguity or conflict between the Contract Documents listed above, the order of precedence shall be the order in which the Contract Documents are listed in Article 1.1 (Contract Documents) above, provided that Appendix 7 shall prevail over all provisions of the Contract Agreement and the other Appendices attached to the Contract Agreement and all the other Contract Documents listed in Article 1.1 above.  1.3 Definitions (Reference GCC Clause 1)  Capitalized words and phrases used in this Contract Agreement shall have the same meanings as are ascribed to them in the General Conditions of Contract. |
| Article 2.   Contract Price and Terms of Payment | 2.1 Contract Price (Reference GCC Clause 1.1(a)(viii) and GCC Clause 11)  The Purchaser hereby agrees to pay to the Supplier the Contract Price in consideration of the performance by the Supplier of its obligations under the Contract. The Contract Price shall be the aggregate of: [ insert: amount of foreign currency A in words ],[insert: amount in figures ],plus[ insert: amount of foreign currency B in words ],[insert: amount in figures ], plus [ insert: amount of foreign currency C in words ], [insert: amount in figures ], [ insert: amount of local currency in words ], [ insert: amount in figures ], as specified in the Grand Summary Price Schedule.  The Contract Price shall be understood to reflect the terms and conditions used in the specification of prices in the detailed price schedules, including the terms and conditions of the associated Incoterms, and the taxes, duties and related levies if and as identified. |
| Article 3.   Effective Date | 3.1 Effective Date (Reference GCC Clause 1.1 (e) (ix))  The time allowed for supply, installation, and achieving Operational Acceptance of the System shall be determined from the date when all of the following conditions have been fulfilled:  (a) This Contract Agreement has been duly executed for and on behalf of the Purchaser and the Supplier;  (b) The Supplier has submitted to the Purchaser the performance security and the advance payment security, in accordance with GCC Clause 13.2 and GCC Clause 13.3; |
|  | (c) The Purchaser has paid the Supplier the advance payment, in accordance with GCC Clause 12;  Each party shall use its best efforts to fulfill the above conditions for which it is responsible as soon as practicable.  3.2 If the conditions listed under 3.1 are not fulfilled within two (2) months from the date of this Contract Agreement because of reasons not attributable to the Supplier, the parties shall discuss and agree on an equitable adjustment to the Contract Price and the Time for Achieving Operational Acceptance and/or other relevant conditions of the Contract. |
| Article 4.   Appendixes | 4.1 The Appendixes listed below shall be deemed to form an integral part of this Contract Agreement. |
|  | 4.2 Reference in the Contract to any Appendix shall mean the Appendixes listed below and attached to this Contract Agreement, and the Contract shall be read and construed accordingly. |

APPENDIXES

Appendix 1. Supplier’s Representative

Appendix 2. Adjudicator *[if there is no Adjudicator, state* ***“not applicable”****]*

Appendix 3. List of Approved Subcontractors

Appendix 4. Categories of Software

Appendix 5. Custom Materials

Appendix 6. Revised Price Schedules (if any)

Appendix 7. Minutes of Contract Finalization Discussions and Agreed-to Contract Amendments

IN WITNESS WHEREOF the Purchaser and the Supplier have caused this Agreement to be duly executed by their duly authorized representatives the day and year first above written.

For and on behalf of the Purchaser

Signed:

in the capacity of [ insert: title or other appropriate designation ]

in the presence of

For and on behalf of the Supplier

Signed:

in the capacity of [ insert: title or other appropriate designation ]

in the presence of

CONTRACT AGREEMENT

dated the [ insert: number ]day of [ insert: month ], [ insert: year ]

BETWEEN

[ insert: name of Purchaser ],“the Purchaser”

and

[ insert: name of Supplier ], “the Supplier”

Appendix 1. Supplier’s Representative

In accordance with GCC Clause 1.1 (b) (iv), the Supplier’s Representative is:

Name: [ insert: name and provide title and address further below, or state “to be nominated within fourteen (14) days of the Effective Date” ]

Title: [ if appropriate, insert: title ]

In accordance with GCC Clause 4.3, the Supplier's addresses for notices under the Contract are:

Address of the Supplier's Representative: [ as appropriate, insert: personal delivery, postal, cable, facsimile, electronic mail, and/or EDI addresses. ]

Fallback address of the Supplier: [ as appropriate, insert: personal delivery, postal, cable, facsimile, electronic mail, and/or EDI addresses. ]

Appendix 2. Adjudicator

In accordance with GCC Clause 1.1 (b) (vi), the agreed-upon Adjudicator is:

Name: [ insert: name ]

Title: [ insert: title ]

Address: [ insert: postal address ]

Telephone: [ insert: telephone ]

In accordance with GCC Clause 43.1.3, the agreed-upon fees and reimbursable expenses are:

Hourly Fees: [ insert: hourly fees ]

Reimbursable Expenses: [ list: reimbursables ]

Pursuant to GCC Clause 43.1.4, if at the time of Contract signing, agreement has not been reached between the Purchaser and the Supplier, an Adjudicator will be appointed by the Appointing Authority named in the SCC.

Appendix 3. List of Approved Subcontractors

The Purchaser has approved use of the following Subcontractors nominated by the Supplier for carrying out the item or component of the System indicated. Where more than one Subcontractor is listed, the Supplier is free to choose between them, but it must notify the Purchaser of its choice sufficiently in advance of the time when the subcontracted work needs to commence to give the Purchaser reasonable time for review. In accordance with GCC Clause 20.1, the Supplier is free to submit proposals for Subcontractors for additional items from time to time. No subcontracts shall be placed with any such Subcontractors for additional items until the Subcontractors have been approved in writing by the Purchaser and their names have been added to this list of Approved Subcontractors, subject to GCC Clause 20.3.

[ specify: item, approved Subcontractors, and their place of registration that the Supplier proposed in the corresponding attachment to its bid and that the Purchaser approves that the Supplier engage during the performance of the Contract. Add additional pages as necessary. ]

|  |  |  |
| --- | --- | --- |
| Item | Approved Subcontractors | Place of Registration |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

Appendix 4. Categories of Software

The following table assigns each item of Software supplied and installed under the Contract to one of the three categories: (i) System Software, (ii) General-Purpose Software, or (iii) Application Software; and to one of the two categories: (i) Standard Software or (ii) Custom Software and to one of the two categories: (i) Proprietary or (ii) Open Source.

|  | (select one per title) | | | (select one per title) | | (select one per title) | |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Title | System | General-Purpose | Application | Standard | Custom | Proprietary | Open Source |
| [insert Title] |  |  |  |  |  |  |  |
| [insert Title] |  |  |  |  |  |  |  |
| [insert Title] |  |  |  |  |  |  |  |
| [insert Title] |  |  |  |  |  |  |  |
| [insert Title] |  |  |  |  |  |  |  |
| [insert Title] |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |

Appendix 5. Custom Materials

The follow table specifies the Custom Materials the Supplier will provide under the Contract.

|  |
| --- |
| Custom Materials |
| *[insert* ***Title and description****]* |
| *[insert* ***Title and description****]* |
| *[insert* ***Title and description****]* |
| *[insert* ***Title and description****]* |
| *[insert* ***Title and description****]* |
|  |

Appendix 6. Revised Price Schedules

The attached Revised Price Schedules (if any) shall form part of this Contract Agreement and, where differences exist, shall supersede the Price Schedules contained in the Supplier’s Bid. These Revised Price Schedules reflect any corrections or adjustments to the Supplier’s bid price, pursuant to the ITB Clauses 30.3 and 38.2.

Appendix 7. Minutes of Contract Finalization Discussions and Agreed-to Contract Amendments

The attached Contract amendments (if any) shall form part of this Contract Agreement and, where differences exist, shall supersede the relevant clauses in the GCC, SCC, Technical Requirements, or other parts of this Contract as defined in GCC Clause 1.1 (a) (ii).

2. Performance and Advance Payment Security Forms

2.1 Performance Security Form (Bank Guarantee)

**(Bank Guarantee)**

*[The bank, as requested by the successful Bidder, shall fill in this form in accordance with the instructions indicated]*

*[Guarantor letterhead or SWIFT identifier code]*

*[insert:* ***Bank’s Name, and Address of Issuing Branch or Office****]*

Beneficiary: *[insert:* ***Name and Address of Purchaser****]*

Date: *[insert:* ***date****]*

PERFORMANCE GUARANTEE No.: *[insert:* ***Performance Guarantee Number****]*

Guarantor: *[Insert name and address of place of issue, unless indicated in the letterhead]*

We have been informed that on *[insert:* ***date of award****]* you awarded Contract No. *[insert:* ***Contract number****]* for *[insert:* ***title and/or brief description of the Contract****]* (hereinafter called "the Contract") to *[insert:* ***complete name of Supplier which in the case of a joint venture shall be in the name of the joint venture****]* (hereinafter called "the Applicant"). Furthermore, we understand that, according to the conditions of the Contract, a performance guarantee is required.

At the request of the Applicant, we as Guarantor hereby irrevocably undertake to pay you any sum(s) not exceeding *[insert:* ***amount(s)****[[26]](#footnote-27)* ***in figures and words****]* such sum being payable in the types and proportions of currencies which the Contract Price is payableupon receipt by us of the Beneficiary’s first demand without the Beneficiary needing to prove or to show grounds or reasons for their demand or the sum specified therein.

On the date of your issuing, to the Supplier, the Operational Acceptance Certificate for the System, the value of this guarantee will be reduced to any sum(s) not exceeding *[insert:* ***amount(s)***1 ***in figures and words****].* This remaining guarantee shall expire no later than *[insert:* ***number*** *and select:* ***of months/of years*** *(of the Warranty Period that needs to be covered by the remaining guarantee)]* from the date of the Operational Acceptance Certificate for the System,*[[27]](#footnote-28)* and any demand for payment under it must be received by us at this office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, (URDG) 2010 Revision, ICC Publication No. 758, except that the supporting statement under 15 (a) is hereby excluded.

*\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*

*[Signature(s)]*

*[****Note****: All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.]*

2.2 Advance Payment Security

Bank Guarantee

*[Guarantor letterhead or SWIFT identifier code]*

Beneficiary: *[insert:* ***Name and Address of Purchaser****]*

Date: *[****insert date of issue****]*

ADVANCE PAYMENT GUARANTEE No.: *[insert:* ***Advance Payment Guarantee Number****]*

Guarantor:  *[Insert name and address of place of issue, unless indicated in the letterhead]*

We have been informed that on *[insert:* ***date of award****]* you awarded Contract No. *[insert:* ***Contract number****]* for *[insert:* ***title and/or brief description of the Contract****]* (hereinafter called "the Contract") to *[insert:* ***complete name of Supplier, which in the case of a joint venture shall be the name of the joint venture****]* (hereinafter called "the Applicant").

Furthermore, we understand that, according to the conditions of the Contract, an advance payment in the sum of [insert: amount in numbers and words, for each currency of the advance payment] is to be made to the Supplier against an advance payment guarantee.

At the request of the Applicant, we as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of *[insert* ***amount in figures****]   
([insert* ***amount in words****])[[28]](#footnote-29)1* upon receipt by us of the Beneficiary’s first demand supported by the Beneficiary’s statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, stating either that the Applicant:

* + 1. has used the advance payment for purposes other than toward delivery of Goods; or
    2. has failed to repay the advance payment in accordance with the Contract conditions, specifying the amount which the Applicant has failed to repay.

A demand under this guarantee may be presented as from the presentation to the Guarantor of a certificate from the Beneficiary’s bank stating that the advance payment referred to above has been credited to the Applicant on its account number *[insert* ***number****]* at *[insert* ***name and address of Applicant’s bank****]*.

The maximum amount of this guarantee shall be progressively reduced by the amount of the advance payment repaid by the Applicant as specified in copies of interim statements or payment certificates which shall be presented to us. This guarantee shall expire, at the latest, upon our receipt of a copy of the interim payment certificate indicating that ninety (90) percent of the Accepted Contract Amount, has been certified for payment, or on the *[insert* ***day****]* day of *[insert* ***month****]*, *[insert* ***year****]*, whichever is earlier. Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No.758, except that the supporting statement under Article 15(a) is hereby excluded.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_   
*[signature(s)]*

*[****Note****: All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.]*

3. Installation and Acceptance Certificates

3. Installation and Acceptance Certificates

3.1 Installation Certificate

Date: [ insert: date ]

Financing Number: [ insert: Financing number from IFB ]

IFB: [ insert: title and number of IFB ]

Contract: [ insert: name and number of Contract ]

To: [ insert: name and address of Supplier ]

Dear Sir or Madam:

Pursuant to GCC Clause 26 (Installation of the System) of the Contract entered into between yourselves and the [ insert: name of Purchaser ](hereinafter the “Purchaser”) dated [ insert: date of Contract ], relating to the [ insert: brief description of the Information System ], we hereby notify you that the System (or a Subsystem or major component thereof) was deemed to have been correctly installed on the date specified below.

1. Description of the System (or relevant Subsystem or major component: [ insert: description ]

2. Date of Installation: [ insert: date ]

Notwithstanding the above, you are required to complete the outstanding items listed in the attachment to this certificate as soon as practicable. This letter shall not relieve you of your obligation to achieve Operational Acceptance of the System in accordance with the Contract nor of your obligations during the Warranty Period.

For and on behalf of the Purchaser

Signed:

Date:

in the capacity of: [ state: “Project Manager” or specify a higher level authority in the Purchaser’s organization ]

3.2 Operational Acceptance Certificate

Date: [ insert: date ]

Financing Number: [ insert: Financing number from IFB ]

IFB: [ insert: title and number of IFB ]

Contract: [ insert: name of System or Subsystem and number of Contract ]

To: [ insert: name and address of Supplier ]

Dear Sir or Madam:

Pursuant to GCC Clause 27 (Commissioning and Operational Acceptance) of the Contract entered into between yourselves and the [ insert: name of Purchaser ](hereinafter the “Purchaser”) dated [ insert: date of Contract ], relating to the [ insert: brief description of the Information System ],we hereby notify you the System (or the Subsystem or major component identified below) successfully completed the Operational Acceptance Tests specified in the Contract. In accordance with the terms of the Contract, the Purchaser hereby takes over the System (or the Subsystem or major component identified below), together with the responsibility for care and custody and the risk of loss thereof on the date mentioned below.

1. Description of the System (or Subsystem or major component): [ insert: description ]

2. Date of Operational Acceptance: [ insert: date ]

This letter shall not relieve you of your remaining performance obligations under the Contract nor of your obligations during the Warranty Period.

For and on behalf of the Purchaser

Signed:

Date: *[ insert:* ***date*** *]*

in the capacity of: [ state: “Project Manager” or specify a higher level authority in the Purchaser’s organization ]

4. Change Order Procedures and Forms

Date: [ insert: date ]

Financing Number: [ insert: Financing number from IFB ]

IFB: [ insert: title and number of IFB ]

Contract: [ insert: name or System or Subsystem and number of Contract ]

**General**

This section provides samples of procedures and forms for carrying out changes to the System during the performance of the Contract in accordance with GCC Clause 39 (Changes to the System) of the Contract.

**Change Order Log**

The Supplier shall keep an up-to-date Change Order Log to show the current status of Requests for Change and Change Orders authorized or pending. Changes shall be entered regularly in the Change Order Log to ensure that the log is kept up-to-date. The Supplier shall attach a copy of the current Change Order Log in the monthly progress report to be submitted to the Purchaser.

**References to Changes**

(1) Request for Change Proposals (including Application for Change Proposals) shall be serially numbered CR-nnn.

(2) Change Estimate Proposals shall be numbered CN-nnn.

(3) Estimate Acceptances shall be numbered CA-nnn.

(4) Change Proposals shall be numbered CP-nnn.

(5) Change Orders shall be numbered CO-nnn.

On all forms, the numbering shall be determined by the original CR-nnn.

**Annexes**

4.1 Request for Change Proposal Form

4.2 Change Estimate Proposal Form

4.3 Estimate Acceptance Form

4.4 Change Proposal Form

4.5 Change Order Form

4.6 Application for Change Proposal Form

4.1 Request for Change Proposal Form

(Purchaser’s Letterhead)

Date: [ insert: date ]

Financing Number: [ insert: Financing number from IFB ]

IFB: [ insert: title and number of IFB ]

Contract: [ insert: name of System or Subsystem or number of Contract ]

To: [ insert: name of Supplier and address ]

Attention: [ insert: name and title ]

Dear Sir or Madam:

With reference to the above-referenced Contract, you are requested to prepare and submit a Change Proposal for the Change noted below in accordance with the following instructions within [ insert: number ] days of the date of this letter.

1. Title of Change: [ insert: title ]

2. Request for Change No./Rev.: [ insert: number ]

3. Originator of Change: [ select Purchaser / Supplier (by Application for Change Proposal), and add: name of originator ]

4. Brief Description of Change: [ insert: description ]

5. System (or Subsystem or major component affected by requested Change): [ insert: description ]

6. Technical documents and/or drawings for the request of Change:

Document or Drawing No. Description

7. Detailed conditions or special requirements of the requested Change: [ insert: description ]

8. Procedures to be followed:

(a) Your Change Proposal will have to show what effect the requested Change will have on the Contract Price.

(b) Your Change Proposal shall explain the time it will take to complete the requested Change and the impact, if any, it will have on the date when Operational Acceptance of the entire System agreed in the Contract.

(c) If you believe implementation of the requested Change will have a negative impact on the quality, operability, or integrity of the System, please provide a detailed explanation, including other approaches that might achieve the same impact as the requested Change.

(d) You should also indicate what impact the Change will have on the number and mix of staff needed by the Supplier to perform the Contract.

(e) You shall not proceed with the execution of work related to the requested Change until we have accepted and confirmed the impact it will have on the Contract Price and the Implementation Schedule in writing.

9. As next step, please respond using the Change Estimate Proposal form, indicating how much it will cost you to prepare a concrete Change Proposal that will describe the proposed approach for implementing the Change, all its elements, and will also address the points in paragraph 8 above pursuant to GCC Clause 39.2.1. Your Change Estimate Proposal should contain a first approximation of the proposed approach, and implications for schedule and cost, of the Change.

For and on behalf of the Purchaser

Signed:

Date:

in the capacity of: [ state: “Project Manager” or specify a higher level authority in the Purchaser’s organization  ]

4.2 Change Estimate Proposal Form

(Supplier’s Letterhead)

Date: [ insert: date ]

Financing Number: [ insert: Financing number from IFB ]

IFB: [ insert: title and number of IFB ]

Contract: [ insert: name of System or Subsystem and number of Contract ]

To: [ insert: name of Purchaser and address ]

Attention: [ insert: name and title ]

Dear Sir or Madam:

With reference to your Request for Change Proposal, we are pleased to notify you of the approximate cost of preparing the below-referenced Change in accordance with GCC Clause 39.2.1 of the Contract. We acknowledge that your agreement to the cost of preparing the Change Proposal, in accordance with GCC Clause 39.2.2, is required before we proceed to prepare the actual Change Proposal including a detailed estimate of the cost of implementing the Change itself.

1. Title of Change: [ insert: title ]

2. Request for Change No./Rev.: [ insert: number ]

3. Brief Description of Change (including proposed implementation approach): [ insert: description ]

4. Schedule Impact of Change (initial estimate): [ insert: description ]

5. Initial Cost Estimate for Implementing the Change: *[insert:* ***initial cost estimate****]*

6. Cost for Preparation of Change Proposal: [ insert: cost in the currencies of the Contract ], as detailed below in the breakdown of prices, rates, and quantities.

For and on behalf of the Supplier

Signed:

Date:

in the capacity of: [ state: “Supplier’s Representative” or specify a other higher level authority in the Supplier’s organization ]

4.3 Estimate Acceptance Form

(Purchaser’s Letterhead)

Date: [ insert: date ]

Financing Number: [ insert: Financing number from IFB ]

IFB: [ insert: title and number of IFB ]

Contract: [ insert: name of System or Subsystem and number of Contract ]

To: [ insert: name of Supplier and address ]

Attention:[ insert: name and title ]

Dear Sir or Madam:

We hereby accept your Change Estimate and agree that you should proceed with the preparation of a formal Change Proposal.

1. Title of Change: [ insert: title ]

2. Request for Change No./Rev.: [ insert: request number / revision ]

3. Change Estimate Proposal No./Rev.: [ insert: proposal number / revision ]

4. Estimate Acceptance No./Rev.: [ insert: estimate number / revision ]

5. Brief Description of Change: [ insert: description ]

6. Other Terms and Conditions: [ insert: other terms and conditions ]

In the event that we decide not to order the Change referenced above, you shall be entitled to compensation for the cost of preparing the Change Proposal up to the amount estimated for this purpose in the Change Estimate Proposal, in accordance with GCC Clause 39 of the General Conditions of Contract.

For and on behalf of the Purchaser

Signed:

Date:

in the capacity of: [ state: “Project Manager” or specify a higher level authority in the Purchaser’s organization ]

4.4 Change Proposal Form

(Supplier’s Letterhead)

Date: [ insert: date ]

Financing Number: [ insert: Financing number from IFB ]

IFB: [ insert: title and number of IFB ]

Contract: [ insert: name of System or Subsystem and number of Contract ]

To: [ insert: name of Purchaser and address ]

Attention: [ insert: name and title ]

Dear Sir or Madam:

In response to your Request for Change Proposal No. [ insert: number ],we hereby submit our proposal as follows:

1. Title of Change: [ insert: name ]

2. Change Proposal No./Rev.: [ insert: proposal number/revision ]

3. Originator of Change: [ select: Purchaser / Supplier; and add: name]

4. Brief Description of Change: [ insert: description ]

5. Reasons for Change: [ insert: reason ]

6. The System Subsystem, major component, or equipment that will be affected by the requested Change: [ insert: description ]

7. Technical documents and/or drawings for the requested Change:

Document or Drawing No. Description

8. Estimate of the increase/decrease to the Contract Price resulting from the proposed Change: [ insert: amount in currencies of Contract ], as detailed below in the breakdown of prices, rates, and quantities.

Total lump sum cost of the Change:

Cost to prepare this Change Proposal (i.e., the amount payable if the Change is not accepted, limited as provided by GCC Clause 39.2.6):

9. Additional Time for Achieving Operational Acceptance required due to the Change: [ insert: amount in days / weeks ]

10. Effect on the Functional Guarantees: [ insert: description ]

11. Effect on the other terms and conditions of the Contract: [ insert: description ]

12. Validity of this Proposal: for a period of [ insert: number ] days after receipt of this Proposal by the Purchaser

13. Procedures to be followed:

(a) You are requested to notify us of your acceptance, comments, or rejection of this detailed Change Proposal within [ insert: number ] days from your receipt of this Proposal.

(b) The amount of any increase and/or decrease shall be taken into account in the adjustment of the Contract Price.

For and on behalf of the Supplier

Signed:

Date:

in the capacity of: [ state: “Supplier’s Representative” or specify a other higher level authority in the Supplier’s organization ]

4.5 Change Order Form

(Purchaser’s Letterhead)

Date: [ insert: date ]

Financing Number: [ insert: Financing number from IFB ]

IFB: [ insert: title and number of IFB ]

Contract: [ insert: name of System or Subsystem and number of Contract ]

To: [ insert: name of Supplier and address ]

Attention: [ insert: name and title ]

Dear Sir or Madam:

We hereby approve the Change Order for the work specified in Change Proposal No. [ insert: number ], and agree to adjust the Contract Price, Time for Completion, and/or other conditions of the Contract in accordance with GCC Clause 39 of the Contract.

1. Title of Change: [ insert: name ]

2. Request for Change No./Rev.: [ insert: request number / revision ]

3. Change Order No./Rev.: [ insert: order number / revision ]

4. Originator of Change: [ select: Purchaser / Supplier; and add: name ]

5. Authorized Price for the Change:

Ref. No.: [ insert: number ] Date: [ insert: date ]

[ insert: amount in foreign currency A ] plus [ insert: amount in foreign currency B ] plus [ insert: amount in foreign currency C ] plus [ insert: amount in local currency ]

6. Adjustment of Time for Achieving Operational Acceptance: [ insert: amount and description of adjustment ]

7. Other effects, if any: [ state: “none” or insert description ]

For and on behalf of the Purchaser

Signed:

Date*: [ insert* ***date*** *]*

in the capacity of: [ state: “Project Manager” or higher level authority in the Purchaser’s organization ]

For and on behalf of the Supplier

Signed:

Date:  *[ insert* ***date*** *]*

in the capacity of: [ state “Supplier’s Representative” or specify a higher level authority in the Supplier’s organization ]

4.6 Application for Change Proposal Form

(Supplier’s Letterhead)

Date: [ insert: date ]

Financing Number: [ insert: Financing number from IFB ]

IFB: [ insert: title and number of IFB ]

Contract: [ insert: name of System or Subsystem and number of Contract ]

To: [ insert: name of Purchaser and address ]

Attention**:** [ insert: name and title]

Dear Sir or Madam:

We hereby propose that the below-mentioned work be treated as a Change to the System.

1. Title of Change: [ insert: name ]

2. Application for Change Proposal No./Rev.: [ insert: number / revision] dated: [ insert: date ]

3. Brief Description of Change: [ insert: description ]

4. Reasons for Change: [insert: description]

5. Order of Magnitude Estimation: [ insert: amount in currencies of the Contract ]

6. Schedule Impact of Change: [ insert: description ]

7. Effect on Functional Guarantees, if any: [ insert: description]

8. Appendix: [ insert: titles (if any); otherwise state “none”]

For and on behalf of the Supplier

Signed:

Date:

in the capacity of: [ state: “Supplier’s Representative” or specify a higher level authority in the Supplier’s organization ]

Annex:  **IsDB Group AML/CFT & KYC Questionnaire**

**IsDB Group1 AML & KYC Questionnaire (Non-Financial Institutions)**

The following questions are intended to assist the Members of the Islamic Development Bank Group (*hereinafter referred to as” IDBG*”) in their respective customers due diligence. It seeks to collate and document information on the Anti-Money Laundering & Financing of Terrorism Policies & Procedures implemented by their respective customers, professional intermediaries, correspondent banks, consultants and non-governmental organizations.

# General Information

* 1. **General Entity Information**

|  |  |
| --- | --- |
| Name of the institution |  |
| Country of incorporation or registration |  |
| Registration / License Number |  |
| Legal Form  *(for example Public Limited Company, Joint Stock Company, Partnership,* limited or unlimited liability etc.) |  |
| Address of Head Office |  |
| Website addresses |  |
| Main activities |  |
| Telephone |  |
| Fax |  |
| Name |  |
| Email Address |  |

* 1. **Ownership Structure**
     1. What is the authorized and issued share capital of your institution? Authorised Capital: Issued Share Capital:
     2. Name of persons or any legal entity who owns or control more than 10% of the shares of you institution.
     3. Are the shares of the institution divided in to several classes? Yes No NA If yes, list the classes of shares (whether ordinary, preferred, bearer or registered shares):

1 Each of the Islamic Development Bank (IsDB), Islamic Corporation for the Insurance of Investment and Export Credit (ICIEC), Islamic Corporation for the Development of the Private Sector (ICD), and International Islamic Trade Finance Corporation (ITFC); is a supra-national, inter-governmental self-regulated of international financial institutions established under its respective Articles of Agreements, having their headquarters in Jeddah, Kingdom of Saudi Arabia (all together are refer to as IsDB Group).

* + 1. Is your institution publicly traded? Yes No NA
    2. If your answer is “Yes,” please list Exchange & Symbol of your institution.
    3. Does your Entity have branches or subsidiaries? If so, does this questionnaire apply also to your Branches/subsidiaries?
    4. Have there been any significant changes in ownership (exceeding 25%) over the last five years? If yes, please provide details.

# Anti-Money Laundering & Financing Terrorism Controls (AML/CFT)

|  |  |  |  |
| --- | --- | --- | --- |
| **I. *General AML Policies, Practices and Procedures*** | YES | NO | N/A |
| 1. Are there laws / regulations designed to prevent and deal with money laundering and terrorist financing in the country of incorporation of your company or institution?  If yes, please list the names of the relevant laws: |  |  |  |
| 2. Has your institution developed written policies and procedures to prevent detect and report suspicious transactions/terrorist financing activities? |  |  |  |
| 3.Does your AML/CFT policy meet the requirement of local laws and the FATF standards? |  |  |  |
| 4.Does these laws and regulations prohibit your institution from conducting business with or on behalf shell companies. |  |  |  |
| 5.Is your AML/CFT policy approved by the board of your institution or by a senior committee? |  |  |  |
| 6. Does your policy require you to identify the source of your customers’ funds or income? |  |  |  |
| 7. Does your institution collect information regarding its customers’ business activities and assess its customers’ AML policies or practices? |  |  |  |
| 8. Is your institution subject to the supervision of any regulatory authority? If yes, please give the name of the supervisory/regulatory authority. |  |  |  |
| 9. Please give the name of the authority to which you must report in case of a suspicion of money laundering and terrorist financing: |  |  |  |
| 10. In addition to inspections by the government supervisors/regulators, does your institution have an internal audit function or other independent third party that assesses AML policies and practices on a regular basis? |  |  |  |
| 11. Does your Entity have an established Anti-bribery and corruption Policy (If yes, please provide a copy) |  |  |  |
| 12. Does your institution have policies to cover relationships with Politically Exposed Persons (PEPs), their families and close associates? |  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
|  |  |  |  |
| 13. Does your institution have appropriate record retention procedures pursuant to applicable laws?  If yes, please state the period of time for which records are kept. |  |  |  |
| **II. *Risk Assessment*** | YES | NO | N/A |
| 14. Does your institution have a risk-based assessment of customer base and their transactions? |  |  |  |
| 15. Does your institution determine the appropriate level of enhanced due diligence necessary for those categories of customers and transactions that your institution has reason to believe pose a heightened risk of illicit activities? |  |  |  |
| **III. *Know Your Customer, Due Diligence and Enhanced Due Diligence*** | YES | NO | N/A |
| 16. Does your institution require the verification of identification information for all customers and counterparties (individuals or entities) at the establishment of the relationship? (such as; name, nationality, address, telephone number, occupation, age/date of birth, number and type of valid official identification, as well as the name of the country/state that issued it)? |  |  |  |
| 17. Does your institution have procedures to establish a record for each new customer that contains their respective identification documents and ‘Know Your Customer’ information? |  |  |  |
| 18. Does your customer identification program require that enhanced due diligence be conducted regarding certain customers that may present a heightened level of money laundering and terrorist financing risk to your institution, such as international private banking and correspondent banking customers, or customers from high risk money laundering and terrorist financing jurisdictions? |  |  |  |
| 19. Does your institution have a periodic process to review and, where appropriate, update high-risk customer information? |  |  |  |
| ***IV. Reportable Transactions and Prevention and Detection of Transactions with Illegally Obtained Funds*** | YES | NO | N/A |
| 20. Does your institution have policies or practices for the identification and reporting of transactions that are required to be reported to the authorities? |  |  |  |
| **V. *Transaction Monitoring*** |  |  |  |
| 21. Does your institution have a monitoring program for unusual and potentially suspicious activities that could expose your institution to any ML/FT risks. |  |  |  |
| 22. Does your institution filter payments against relevant United Nations sanctions lists? |  |  |  |
| **VI. *AML Training*** | YES | NO | N/A |
| 1. Does your Institution provide AML/CTF/Sanctions & Embargoes training to relevant employees that includes:    * Identification and reporting of transactions that must be reported to government authorities. |  |  |  |
| * Examples of different forms of money laundering involving the institution’s products and services. * International, national, and internal policies to prevent money laundering. If yes, how frequent are these trainings? |  |  |  |
| 24 Does your institution retain records of its training sessions including attendance records and relevant training materials used? |  |  |  |
| 25. Does your institution have policies to communicate new AML/CTF/Sanctions & Embargoes related laws or changes to existing AML/CTF/Sanctions & Embargoes related policies or practices to relevant employees? |  |  |  |
| 26. Does your Institution employ third parties to carry out some of the AML/CFT/ Sanctions & Embargoes functions of the institution?  If YES Kindly answer below question. |  |  |  |
| **VI. Additional Information/documents** | | | |
| Please attach the following documents along with this form:   * License /Certificate of Registration; * By-law / Articles of Association. * AML / CFT / KYC Policy / Guidelines; * List of Shareholders / owners and their respective shareholding percentage * List of Board of Directors (or Trustees) including their nationalities & shareholders they represent * List of Management Team indicating their respective positions and the number of years of service. * Annual Report & Financial Statement. | | | |

I hereby confirm that the statements given above are true and correct. I also confirm that I am authorized to complete this document.

Name : Signature :

Title

Date : Official Seal

(P.S. Please ensure that this form is fully filled, duly signed and stamped in order to complete the required onboarding processes).

1. Substitute “contracts” where Bids are called concurrently for multiple contracts. Add a new para. 3 and renumber paras 3 - 8 as follows: “Bidders may Bid for one or several contracts, as further defined in the bidding document. Bidders wishing to offer discounts in case they are awarded more than one contract will be allowed to do so, provided those discounts are included in the Letter of Bid.” [↑](#footnote-ref-2)
2. Insert if applicable: “This contract will be jointly financed by [insert name of cofinancing agency]. Procurement process will be governed by the IsDB Guidelines.” [↑](#footnote-ref-3)
3. A brief description of the type(s) of information systems should be provided, including location, quantities, installation and delivery period and other information necessary to enable potential Bidders to decide whether or not to respond to the Request for Bids. Bidding document may require Bidders to have specific experience or capabilities; such qualification requirements should also be included in this paragraph. [↑](#footnote-ref-4)
4. The office for inquiry and issuance of the bidding document and that for Bid submission may or may not be the same. [↑](#footnote-ref-5)
5. The fee chargeable should only be nominal to defray reproduction and mailing costs. An amount between US$50 and US$300 or equivalent is deemed appropriate. [↑](#footnote-ref-6)
6. For example, cashier’s check, direct deposit to specified account number, etc. [↑](#footnote-ref-7)
7. The delivery procedure is usually airmail for overseas delivery and surface mail or courier for local delivery. If urgency or security dictates, courier services may be required for overseas delivery. With the agreement of the IsDB, documents may be distributed by e-mail, downloading from authorized web site(s) or electronic procurement system. [↑](#footnote-ref-8)
8. Substitute the address for Bid submission if it is different from address for inquiry and issuance of the bidding document. [↑](#footnote-ref-9)
9. Substitute “contracts” where Bids are called concurrently for multiple contracts. Add a new para. 3 and renumber paras 3 - 8 as follows: “Bidders may Bid for one or several contracts, as further defined in the bidding document. Bidders wishing to offer discounts in case they are awarded more than one contract will be allowed to do so, provided those discounts are included in the Letter of Bid.” [↑](#footnote-ref-10)
10. Insert if applicable: “This contract will be jointly financed by [insert name of cofinancing agency]. Procurement process will be governed by the IsDB Guidelines.” [↑](#footnote-ref-11)
11. A brief description of the type(s) of information systems should be provided, including location, quantities, delivery and installation period, and other information necessary to enable potential Bidders to decide whether or not to respond to the Request for Bids. Bidding document may require Bidders to have specific experience or capabilities; such qualification requirements should also be included in this paragraph. [↑](#footnote-ref-12)
12. The office for inquiry and issuance of Bidding document and that for Bid submission may or may not be the same. [↑](#footnote-ref-13)
13. The fee chargeable should only be nominal to defray reproduction and mailing costs. An amount between US$50 and US$300 or equivalent is deemed appropriate. [↑](#footnote-ref-14)
14. For example, cashier’s check, direct deposit to specified account number, etc. [↑](#footnote-ref-15)
15. The delivery procedure is usually airmail for overseas delivery and surface mail or courier for local delivery. If urgency or security dictates, courier services may be required for overseas delivery. With the agreement of the IsDB, documents may be distributed by e-mail, downloading from authorized web site(s) or electronic procurement system. [↑](#footnote-ref-16)
16. Substitute the address for Bid submission if it is different from address for inquiry and issuance of the bidding document. [↑](#footnote-ref-17)
17. Nonperformance, as decided by the Purchaser, shall include all contracts where (a) nonperformance was not challenged by the contractor, including through referral to the dispute resolution mechanism under the respective contract, and (b) contracts that were so challenged but fully settled against the contractor. Nonperformance shall not include contracts where Purchaser decision was overruled by the dispute resolution mechanism. Nonperformance must be based on all information on fully settled disputes or litigation, i.e. dispute or litigation that has been resolved in accordance with the dispute resolution mechanism under the respective contract and where all appeal instances available to the applicant have been exhausted. [↑](#footnote-ref-18)
18. This requirement also applies to contracts executed by the Applicant as JV member. [↑](#footnote-ref-19)
19. The Bidder shall provide accurate information on the related Letter of Bid about any litigation or arbitration resulting from contracts completed or ongoing under its execution over the last five years. A consistent history of awards against the Bidder or any member of a joint venture may result in failure of the Bid. [↑](#footnote-ref-20)
20. For contracts under which the Bidder participated as a joint venture member or sub-contractor, only the Bidder’s share, by value, and role and responsibilities shall be considered to meet this requirement. [↑](#footnote-ref-21)
21. The amount of the Bond shall be denominated in the currency of the *Purchaser*’s Country or the equivalent amount in a freely convertible currency. [↑](#footnote-ref-22)
22. In this context, any action taken by a Contractor or Consultant or any of its personnel, or its agents, or its sub-consultants, sub-contractors, service providers, Suppliers, and/or their employees, to influence the selection process or contract execution for undue advantage is improper. [↑](#footnote-ref-23)
23. A Firm or individual may be declared ineligible to be awarded a IsDB-financed contract upon: (i) completion of the IsDB’s sanctions proceedings as per its sanctions procedures, including, inter alia, cross-debarment as agreed with other International Financial Institutions, including Multilateral Development Banks; and (ii) as a result of temporary suspension or early temporary suspension in connection with an ongoing sanctions proceeding. [↑](#footnote-ref-24)
24. In this context, any action taken by a Contractor or Consultant or any of its personnel, or its agents, or its sub-consultants, sub-contractors, service providers, Suppliers, and/or their employees, to influence the selection process or contract execution for undue advantage is improper. [↑](#footnote-ref-25)
25. A Firm or individual may be declared ineligible to be awarded a IsDB-financed contract upon: (i) completion of the IsDB’s sanctions proceedings as per its sanctions procedures, including, inter alia, cross-debarment as agreed with other International Financial Institutions, including Multilateral Development Banks; and (ii) as a result of temporary suspension or early temporary suspension in connection with an ongoing sanctions proceeding. [↑](#footnote-ref-26)
26. *The bank shall insert the amount(s) specified and denominated in the SCC for GCC Clauses 13.3.1 and 13.3.4 respectively, either in the currency(ies) of the Contract or a freely convertible currency acceptable to the Purchaser.* [↑](#footnote-ref-27)
27. *In this sample form, the formulation of this paragraph reflects the usual SCC provisions for GCC Clause 13.3. However, if the SCC for GCC Clauses 13.3.1 and 13.3.4 varies from the usual provisions, the paragraph, and possibly the previous paragraph, need to be adjusted to precisely reflect the provisions specified in the SCC.* [↑](#footnote-ref-28)
28. 1 *The Guarantor shall insert an amount representing the amount of the advance payment and denominated either in the currency(ies) of the advance payment as specified in the Contract, or in a freely convertible currency acceptable to the Purchaser.* [↑](#footnote-ref-29)